## 計画書
OMZ Hangar Maintenance Plan & Report | [9 empty] | Plan No. OMZ/P-339 |  |  |  |  | Plan |  |  |  | Receipt | Completion |  |  |  |  | Planner Complete
| In-Charge | ( | OMA |  | ) | [9 empty] | Approval |  | In-Charge |  |  | DIC |  |  | OMA
JA216J _6C
Work Place: ITM HGR
■ 航空機整備改造認定 |  |  |  | □ 航空機整備検査認定
In-Out Plan |  | 2022-05-31 |  | (Tue) | S | ～ | 2022-06-25 |  | (Sat) | S | 26 |  | Days
① Schedule | [11 empty] | ② Aircraft Detail Data
|  | Arrival |  | Start |  | HGR |  | ALL | Departure |  |  |  | A/C Reg No. |  |  | Ship Type |  |  | Model |  | Serial No.
[6 empty] | Completion |  | Completion |  |  |  |  | JA216J |  |  | E170 |  |  | ERJ 170-100 STD |  | 17000299
| Plan | 2022-05-31 |  | 2022-05-31 |  | 2022-06-25 |  | 2022-06-25 | 2022-06-26
|  | TBD |  | 22:00 |  | 9:00 |  | 22:00 | TBD
|  | TBD | [6 empty] | TBD
| Actual | / |  | / |  | / |  | / | /
|  | ： |  | ： |  | ： |  | ： | ：
③ Topics | [8 empty] | ④ Elapse (Start～All Completion) | [8 empty] | ⑦ Planning Job & Manhour Info
| ENG CHG (LH) | [8 empty] | Plan |  | 600:00 |  | Hours |  |  |  |  | RTN | 839 |  | Item | 1900-05-22 08:20 | Manhour
| NHF GROUND TEST | [8 empty] | Actual |  |  |  | Hours |  |  |  |  | AP | 130 |  | Item | 1900-01-22 06:48 | Manhour
| A CHECK (G4A02) | [17 empty] | COA | 25 |  | Item | 1900-02-16 07:06 | Manhour
[9 empty] | ⑤ Work Place | [9 empty] | EV | 1 |  | Item | 4:00 | Manhour
[10 empty] | ITM #1 Bay | [8 empty] | C/O&MI | 11 |  | Item | 1900-01-01 16:00 | Manhour
[19 empty] | Planning Total | 1006 |  | Item | 1900-08-04 18:14 | Manhour
[9 empty] | ⑥ AMOS Info | [9 empty] | Estimated SQ |  |  |  | 1900-03-15 | Manhour
[10 empty] | Work Package |  |  | 216J/H-22 | [5 empty] | Estimated Total |  |  |  | 1900-10-18 18:14 | Manhour
Note: Planning section will fill in blanks above after maintenance completion.
Formulas:
OMA = AF21+AF22+AF23+AF24+[OMA, row above]
OMA = AF26+[OMA, row above]

## RTN
JA216J _6C_RTN List
No | Task Card | Order | Event Description | AD TCD | Plan | Trade | Remarks | TRADE表記 | MAKE ACC(AP CARD以外)
1 | 05-01-120-H001-U | 100411236 | General Visual Inspection of Forward Fuselage (below the Floor Line) Interface Connectors and Overbraids. |  | 0.027778 | ACS |  | ×, × | ×
2 | 05-12-500-H001-U | 100411240 | Detailed Inspection of RH and LH Wing Interface Connectors and Overbraids. |  | 0.13264 | ACS |  | ×, × | wing-root landing-light lens faring
3 | 05-14-710-H001-U | 100411244 | Detailed Inspection of NLG Interface Connectors and Overbraids. |  | 0.014583 | ACS |  | ×, × | ×
4 | 05-15-730-H001-U | 100411248 | Detailed Inspection of RH and LH MLG Interface Connectors and Overbraids. |  | 0.019444 | ACS |  | ×, × | ×
5 | 05-20-400-H001-U | 100411252 | Detailed Inspection of Pylons Interface Connectors and Overbraids. |  | 0.045833 | ACS |  | ×, × | ×
6 | 20-00-00-001F-LH | 100291148 | Detailed Inspection of Tank Unit wiring, Tank Unit wiring connections and electrical bonding features inside Wing Tank. |  | 0.025 | REI | NOTE: EWIS. This task complies with the Fuel Tank Safety Requirement. | ×, × | ×
7 | 20-00-00-001F-RH | 100291081 | Detailed Inspection of Tank Unit wiring, Tank Unit wiring connections and electrical bonding features inside Wing Tank. |  | 0.029167 | REI | NOTE: EWIS. This task complies with the Fuel Tank Safety Requirement. | ×, × | ×
8 | 20-00-00-002F-U | 800046764 | Detailed Inspection of Tank Unit wiring, Tank Unit wiring connections and electrical bonding features inside Wing Stub Tank. |  | 0.041667 | REI | NOTE: EWIS. This task complies with the Fuel Tank Safety Requirement. | ×, I | ×
9 | 20-00-00-003F-LH | 100291149 | Detailed Inspection of Fuel Quantity Gauging System Harness and Connectors. Examine installation, protection, segregation, identification, chaffing and superficial insulation damages of harness and connectors in the Fuel Tank adjacent areas and electronic Bay. |  | 0.027778 | REI |  | ×, × | ×
10 | 20-00-00-003F-RH | 100291150 | Detailed Inspection of Fuel Quantity Gauging System Harness and Connectors. Examine installation, protection, segregation, identification, chaffing and superficial insulation damages of harness and connectors in the Fuel Tank adjacent areas and electronic Bay. |  | 0.027778 | REI |  | ×, × | ×
11 | 20-00-00-004F-U | 100291034 | Detailed Inspection of Fuel Pump Connectors. Examine for electrical arcing signals, pins corrosion/discoloration and fuel leakage through the connector. |  | 0.048611 | REI |  | ×, × | ×
12 | 20-Z120-003-U | 100164961 | Cleaning of Fwd Fuselage Fwd Pressure Bulkhead Aft Face, Fwd Fuselage Bottom Front Area and NLG Wheel Well Bay (inside the fuselage), including the Bottom Surface of Floor Structure areas - Internal Side. |  | 0.033333 | REI | NOTE: EWIS. Cockpit Floor Panels have to be removed. | ×, × | ×
13 | 20-Z140-011-U | 100291085 | Cleaning of Center E-Bay Area and Aft Pressure Bulkhead Aft Face at Center Fuselage II - Inside Center E-Bay. |  | 0.092361 | REI |  | ×, × | ×
14 | 20-Z190-004-LH | 100411258 | General Visual Inspection of EWIS components of Wing Stub Lower Portion Harness for signs of damage, adequate installation, chafing and general condition. |  | 0.045139 | REI | NOTE: EWIS. | ×, × | ×
15 | 20-Z190-004-RH | 100411262 | General Visual Inspection of EWIS components of Wing Stub Lower Portion Harness for signs of damage, adequate installation, chafing and general condition. |  | 0.03125 | REI | NOTE: EWIS. | ×, × | ×
16 | 20-Z191-001-U | 100411266 | General Visual Inspection of EWIS components of Slat Power Drive Unit Harness at FWD Wing to Fuselage fairing for signs of damage, adequate installation, chafing and general condition. |  | 0.029167 | REI | NOTE: EWIS. | ×, × | ×
17 | 20-Z195-001-U | 100411270 | General Visual Inspection of EWIS components of Hydraulic AC Motor Pumps Systems 1 and 2 Harness at AFT Wing to Fuselage Fairing for signs of damage, adequate installation, chafing and general condition. |  | 0.039583 | REI | NOTE: EWIS. | ×, × | ×
18 | 20-Z230-001-FWDLH | 100411284 | Cleaning of Center Fuselage I Side Areas behind Dado Panels, from Forward Fuselage and Center Fuselage I Junction to Center Fuselage I and II Junction - Internal side of Fuselage. |  | 0.13681 | REI | NOTE: EWIS. | CBN, × | ×
19 | 20-Z230-001-FWDRH | 100411414 | Cleaning of Center Fuselage I Side Areas behind Dado Panels, from Forward Fuselage and Center Fuselage I Junction to Center Fuselage I and II Junction - Internal side of Fuselage. |  | 0.28472 | REI | NOTE: EWIS. | CBN, × | ×
20 | 20-Z240-001-FWDLH | 100411288 | Cleaning of Center Fuselage II Side Areas behind Dado Panels, from Center Fuselage I and II Junction to Center Fuselage II and III Junction - Internal Side of Fuselage. |  | 0.13264 | REI | NOTE: EWIS. | CBN, × | passenger seats
21 | 20-Z240-001-FWDRH | 100411410 | Cleaning of Center Fuselage II Side Areas behind Dado Panels, from Center Fuselage I and II Junction to Center Fuselage II and III Junction - Internal Side of Fuselage. |  | 0.16389 | REI | NOTE: EWIS. | CBN, × | passenger seats
22 | 20-Z250-001-AFTLH | 100411292 | Cleaning of Center Fuselage III Side Areas behind Dado Panels, from Center Fuselage II and III Junction to Region Ahead Galley / Toilet - Internal Side of Fuselage. |  | 0.1125 | REI | NOTE: EWIS. | CBN, × | passenger seats insulation blankets
23 | 20-Z250-001-AFTRH | 100411406 | Cleaning of Center Fuselage III Side Areas behind Dado Panels, from Center Fuselage II and III Junction to Region Ahead Galley / Toilet - Internal Side of Fuselage. |  | 0.18403 | REI | NOTE: EWIS. | CBN, × | passenger seats insulation blankets
24 | 20-Z310-001-U | 100411297 | General Visual Inspection of EWIS components of APU Electrical Power Harness, Hydraulic System Power Harness and Horizontal Stabilizer Power Harness at Rear Fuselage for signs of damage, adequate installation, chafing and general condition. |  | 0.052083 | REI | NOTE: EWIS. | ×, × | ×
25 | 20-Z419-001-U | 100411301 | General Visual Inspection of EWIS components of IDG power cables and the FADEC harness inside the Pylon for signs of damage, adequate installation, chafing and general condition. |  | 0.045833 | REI | NOTE: EWIS. | ×, × | ×
26 | 20-Z510-001-LH | 100871664 | General Visual Inspection of EWIS components of Wing Leading Edge Harness for signs of damage, adequate installation, chafing and general condition. |  | 0.076389 | REI | NOTE: EWIS. | ×, × | aft navigation/strobe light assembly(it is not necessary do disconnect) wing-root lens
27 | 20-Z510-001-RH | 100871642 | General Visual Inspection of EWIS components of Wing Leading Edge Harness for signs of damage, adequate installation, chafing and general condition. |  | 0.072917 | REI | NOTE: EWIS. | ×, × | aft navigation/strobe light assembly(it is not necessary do disconnect) wing-root lens
28 | 21-24-02-001-LH | 100796709 | Discard of Recirculation Fan Filters. |  | 0.0625 | CBN |  | ×, × | ×
29 | 21-24-02-001-RH | 100798111 | Discard of Recirculation Fan Filters. |  | 0.0625 | CBN |  | ×, × | ×
30 | 21-27-03-001-U | 100842204 | Operational Check of Forward Cargo Compartment Check Valve. |  | 0.013889 | CBN |  | ×, × | ×
31 | 21-27-03-002-U | 100687003 | Operational Check of Forward Cargo Compartment Check Valve. |  | 0.020833 | ACS |  | ×, × | ×
32 | 21-30-01-003-U | 800046930 | Operational Check of CPCS Power Supply and Pressurization Panel in Manual and Auto Mode (including Dump switch). |  | 0.054167 | CBN | NHF TASK | ×, × | ×
33 | 21-32-00-001-U | 100421027 | Functional Check of the positive pressure relief setting of the Positive Pressure Relief Valve. |  | 0.34236 | CBN |  | CBN, × | ×
34 | 21-32-04-001-U | 100411332 | Operational Check of Negative Pressure Relief Valve. |  | 0.027778 | CBN |  | ×, × | ×
35 | 21-33-00-002-AFT | 100686967 | Operational Check of Cargo Compartment Pressure Equalization Valves. |  | 0.034722 | CBN |  | ×, × | ×
36 | 21-33-00-002-FWD | 100686968 | Operational Check of Cargo Compartment Pressure Equalization Valves. |  | 0.034722 | CBN |  | ×, × | ×
37 | 21-51-10-001-RH | 800574356 | Restoration (cleaning) of Pack Bypass Valve Filter. |  | 0.041667 | CBN | FOR P/N:820914-7, S/N:2018040012
38 | 23-61-00-001-LH | 100411347 | Functional Check of Static Dischargers resistance insulation value. |  | 0.0625 | REI |  | ×, × | ×
39 | 23-61-00-001-RH | 100411351 | Functional Check of Static Dischargers resistance insulation value. |  | 0.0625 | REI |  | ×, × | ×
40 | 23-61-00-001-T | 100411355 | Functional Check of Static Dischargers resistance insulation value. |  | 0.078472 | REI |  | ×, × | ×
41 | 24-08-400-H001-U | 100411362 | Detailed Inspection of IDGs 1 and 2 Structural Bonding via V-BAND Clamp and Strain relief 360° Metallic backshell. |  | 0.036111 | ACS |  | ×, × | ×
42 | 24-21-00-001-LH | 100842205 | Servicing of IDG as required. |  | 0.013889 | ACS |  | ×, × | ×
43 | 24-21-00-001-RH | 100842206 | Servicing of IDG as required. |  | 0.013889 | ACS |  | ×, × | ×
44 | 24-23-00-002-U | 100573019 | Lubrication of RAT Pivot and Assembly. |  | 0.12708 | ACS |  | ACS, × | ×
45 | 24-23-00-004-U | 100573020 | Functional check of the RAT Generator. Deploy the RAT manually and carry out a functional check on the RAT Generation System for proper voltage and frequency, also perform automatic deployment of RAT. |  | 0.36181 | ACS | NHF TASK | ACS, × | ×
46 | 24-23-00-005-U | 100573021 | Functional Check of the RAT Generation System for proper voltage and frequency. |  | 0.35556 | ACS | NHF TASK NOTE: RAT should be deployed manually and also automatically. | ACS, × | ×
47 | 24-23-11-001-U | 100573022 | Inspect (General Visual) for damage, corrosion and bending of RAT Cable Rod End Assembly. |  | 0.14444 | ACS | NHF TASK | ACS, × | ×
48 | 25-11-01-001-FWDLH | 100411372 | Detailed Inspection of Pilot/Co-Pilot Seats Attachment to the Rail for security, general conditions, degradation, cracks, damage and wear. |  | 0.095833 | REI |  | REI, × | ×
49 | 25-11-01-001-FWDRH | 100411427 | Detailed Inspection of Pilot/Co-Pilot Seats Attachment to the Rail for security, general conditions, degradation, cracks, damage and wear. |  | 0.098611 | REI |  | REI, × | ×
50 | 25-11-01-002-FWDLH | 100411375 | Detailed Inspection of Pilot/Co-pilot Seats looking for possible degradation, cracks, damage, scratches and wear. |  | 0.031944 | REI |  | ×, × | ×
51 | 25-11-01-002-FWDRH | 100411422 | Detailed Inspection of Pilot/Co-pilot Seats looking for possible degradation, cracks, damage, scratches and wear. |  | 0.031944 | REI |  | ×, × | ×
52 | 25-11-01-003-FWDLH | 100411380 | Operational Check of Pilot/Co-pilot Seats Inertial Reel. |  | 0.020833 | REI |  | REI, × | ×
53 | 25-11-01-003-FWDRH | 100411419 | Operational Check of Pilot/Co-pilot Seats Inertial Reel. |  | 0.036111 | REI |  | REI, × | ×
54 | 25-11-01-004-U | 100308972 | Detailed Inspection of Pilot/Co-pilot Seats belts looking for possible damage and wear. |  | 0.0375 | REI |  | ×, × | ×
55 | 25-11-02-001-U | 800047044 | Detailed Inspection of Observer Seat (including Seat Belts) for possible degradation, cracks, damage, scratches and wear. |  | 0.020833 | REI |  | ×, × | ×
56 | 25-11-02-002-U | 100411385 | Operational Check of Observer Seat Inertial Reel and Buckle. |  | 0.034028 | REI |  | REI, × | ×
57 | 25-21-10-001-LH | 100411389 | Detailed Inspection of Passenger Seat, Seat Belt, Seat Buckle and Seat Belt Attachments, Seat Attachments and Food Table for integrity and general conditions. |  | 0.40833 | CBN |  | ×, × | ×
58 | 25-21-10-001-RH | 100411431 | Detailed Inspection of Passenger Seat, Seat Belt, Seat Buckle and Seat Belt Attachments, Seat Attachments and Food Table for integrity and general conditions. |  | 0.40833 | CBN |  | ×, × | ×
59 | 25-21-20-001-U | 100308892 | Detailed Inspection of Flight Attendant Seats (Cushions and Structures, including Seat Belts, Buckles and Shoulder Harness) for tears, loose stiches, wear, corrosion, defective parts and damage. |  | 0.027778 | CBN |  | ×, × | ×
60 | 25-21-20-002-U | 100411394 | Operational Check of Flight Attendant Seats Inertial Reel and Buckle. |  | 0.0375 | CBN |  | ×, × | ×
61 | 25-62-05-001-U | 100411434 | Inspect (General Visual) Cockpit Escape Rope. Inspect for integrity and general conditions. |  | 0.01875 | CBN |  | ×, × | ×
62 | 26-11-01-001-U | 800047086 | Operational Check of Engine Fire Detection Loop. |  | 0.041667 | REI |  | ×, × | ×
63 | 26-12-01-001-U | 800047089 | Operational Check of APU Fire Detection Loop. |  | 0.041667 | REI |  | ×, × | ×
64 | 26-14-01-001-U | 100793435 | Operational Check of Lavatory Smoke Detector. |  | 0.041667 | CBN |  | ×, × | ×
65 | 26-21-00-001-LH | 100411442 | Functional Check of Engine Fire Extinguishing System. Perform a leak test to verify tubing leakage, proper operation of the Engine Drain valves and Tee valves. |  | 0.16667 | ACS |  | ACS, × | ×
66 | 26-21-00-001-RH | 100411777 | Functional Check of Engine Fire Extinguishing System. Perform a leak test to verify tubing leakage, proper operation of the Engine Drain valves and Tee valves. |  | 0.16667 | ACS |  | ACS, × | ×
67 | 26-21-01-001-U | 100793434 | Functional Check of Engine Fire Extinguishing Handle. Check if the handle is sending the correct signal to trigger the Engine Fire Extinguishing Bottle cartridge. |  | 0.064583 | ACS |  | ACS, × | ×
68 | 26-21-05-002-U | 100308897 | Operational Check of Engine Fire Extinguishing Bottle Temperature Compensated Pressure Switch (TCPS). Press the switches button and check if the related message is triggered on EICAS. |  | 0.052083 | ACS |  | ACS, × | ×
69 | 26-22-03-002-U | 100793430 | Operational Check of APU Fire Extinguishing Bottle Pressure Switch (TCPS). Press the switch button and check if the related message is triggered on EICAS. |  | 0.034028 | ACS |  | ACS, × | ×
70 | 26-22-07-001-U | 100411449 | Detailed Inspection the APU fire extinguishing piping for presence of cracks, misconnection and damage that may cause leakage of the fire extinguisher agent. |  | 0.041667 | ACS |  | ×, × | ×
71 | 26-22-09-001-U | 100793452 | Functional Check of APU Fire Extinguishing Bottle Electrical Hardware. Check if the switch is sending the correct signal to trigger the APU Fire Extinguishing Bottle cartridge. |  | 0.05625 | ACS |  | ACS, × | ×
72 | 26-23-01-002-U | 100618969 | Operational Check of Cargo Compartments Fire Extinguisher Bottles Pressure Switches. |  | 0.047917 | ACS |  | ×, × | ×
73 | 26-23-09-001-U | 100411454 | Functional Check of Cargo Fire Extinguishing Discharge Tubing, Discharge Head and Nozzles. |  | 0.23819 | ACS |  | ACS, × | ×
74 | 26-23-13-001-U | 800047128 | Operational Check of Cargo Compartments Fire Extinguishing Discharge Circuit. |  | 0.17083 | ACS |  | ×, × | ×
75 | 26-25-01-002-U | 100822199 | Weight inspection of Lavatory Auto-Discharge Fire Extinguisher bottle. |  | 0.0625 | CBN | FOR P/N:BA22649-1, S/N:73920
76 | 26-25-01-002-U | 100544670 | Weight inspection of Lavatory Auto-Discharge Fire Extinguisher bottle. |  | 0.0625 | CBN | FOR P/N:BA24320G-1, S/N:66223
77 | 27-00-00-001C-U | 100767404 | Operational Check of all Flight Control System Power Control Units (PCUs) - Integrity Test. |  | 0.10139 | ACS | A-CHECK ITEM | ×, × | ×
78 | 27-00-00-001-U | 100681251 | Operational Check of all Flight Control System Power Control Units (PCUs) - Integrity Test. |  | 0.054861 | ACS | A-CHECK ITEM | ×, × | ×
79 | 27-00-00-002-U | 100793448 | Operational Check of all Flight Control System Power Control Units (PCUs) Compensators - Freedom of Motion Test. |  | 0.12986 | ACS |  | ×, × | ×
80 | 27-00-00-003-U | 100793447 | Operational Check of all Flight Control System Power Control Units (PCUs) Compensators - Position Test. |  | 0.10278 | ACS |  | ×, × | ×
81 | 27-00-00-005-U | 100411460 | Functional Check of Rudder and Elevator Deflections in Direct Mode. |  | 0.31736 | ACS |  | ACS, × | ×
82 | 27-03-00-001-U | 800047202 | Operational Check of Fly-by-Wire Back-up Battery Hot Bus. |  | 0.054167 | ACS |  | ×, × | ×
83 | 27-03-01-001-U | 800047205 | Operational Check of Flight Control Panel. |  | 0.083333 | ACS |  | ×, × | ×
84 | 27-03-01-002-U | 100411466 | Operational Check of Stick Shaker Cutout Button. |  | 0.091667 | ACS | NHF TASK | REI, × | ×
85 | 27-03-04-001-U | 100793455 | Operational Check of Horizontal Stabilizer Cutout Switch. |  | 0.045833 | ACS |  | ×, × | ×
86 | 27-03-05-002-U | 100796548 | Functional Check of Fly-by-Wire Back-up Battery Charge. |  | 0.036111 | ACS |  | REI, × | ×
87 | 27-11-00-001-FWDLH | 100411474 | General Visual Inspection of Command Input Torque Tube and Control Yoke Chain. |  | 0.027778 | ACS |  | ×, × | control column lining
88 | 27-11-00-001-FWDRH | 100411741 | General Visual Inspection of Command Input Torque Tube and Control Yoke Chain. |  | 0.031944 | ACS |  | ×, × | control column lining
89 | 27-11-00-002C-U | 100411479 | Operational Check of Control-Yoke Disconnect System. |  | 0.090278 | ACS |  | ×, × | ×
90 | 27-11-00-002-U | 800047226 | Operational Check of Control-Yoke Disconnect System. |  | 0.05 | ACS |  | ×, × | ×
91 | 27-11-00-003-LH | 100871671 | Detailed Inspection of Aileron Control Cables, Pulleys and Quadrant at wing area for signs of damage and wear. |  | 0.018056 | ACS |  | ×, × | ×
92 | 27-11-00-003-RH | 100871672 | Detailed Inspection of Aileron Control Cables, Pulleys and Quadrant at wing area for signs of damage and wear. |  | 0.018056 | ACS |  | ×, × | ×
93 | 27-11-00-005-U | 100730832 | Operational Check of Aileron System Interconnect System. |  | 0.041667 | ACS |  | ×, I | ×
94 | 27-11-01-001-FWDLH | 100411484 | Lubrication of Control Yokes Chains. Lubricate the sprocket and the Control Yoke chain. |  | 0.083333 | ACS |  | ×, × | control column lining
95 | 27-11-01-001-FWDRH | 100411745 | Lubrication of Control Yokes Chains. Lubricate the sprocket and the Control Yoke chain. |  | 0.083333 | ACS |  | ×, × | control column lining
96 | 27-11-03-001-LH | 100308912 | Functional Check of Aileron Control Cables Tension at Wing Area. |  | 0.16319 | ACS |  | ACS, × | ×
97 | 27-11-03-001-RH | 100308973 | Functional Check of Aileron Control Cables Tension at Wing Area. |  | 0.12014 | ACS |  | ACS, × | ×
98 | 27-11-03-004C-LH | 100411489 | Detailed Inspection of Fuselage Aileron Control Cables. |  | 0.060417 | ACS |  | ×, I | control column lining
99 | 27-11-03-004C-RH | 100411754 | Detailed Inspection of Fuselage Aileron Control Cables. |  | 0.067361 | ACS |  | ×, I | control column lining
100 | 27-11-03-004-LH | 100411494 | Detailed Inspection of Aileron Control Cables and Interconnect Cables, Pulleys and Quadrant at fuselage area for signs of damage and wear. |  | 0.12083 | ACS |  | ×, I | control column lining
101 | 27-11-03-004-RH | 100411751 | Detailed Inspection of Aileron Control Cables and Interconnect Cables, Pulleys and Quadrant at fuselage area for signs of damage and wear. |  | 0.12083 | ACS |  | ×, I | control column lining
102 | 27-11-03-005C-LH | 100411499 | Operational Check of Fuselage Aileron Control Cables for Rupture. |  | 0.063889 | ACS |  | ×, I | ×
103 | 27-11-03-005C-RH | 100411760 | Operational Check of Fuselage Aileron Control Cables for Rupture. |  | 0.0625 | ACS |  | ×, I | ×
104 | 27-11-03-006-U | 100308918 | Functional Check of Aileron Control Cables Tension at Fuselage Area. |  | 0.15069 | ACS |  | ACS, × | control column lining
105 | 27-11-03-007-U | 100706908 | Lubrication of Carbon Steel Aileron Cables - Wing Area |  | 0.10417 | ACS |  | ×, × | ×
106 | 27-11-11-001-U | 800047260 | Operational Check of Aileron Override Unit. |  | 0.041667 | ACS |  | ×, × | ×
107 | 27-11-11-002C-U | 800047263 | Operational Check of Aileron Override Unit for Jamming / Disconnection. |  | 0.016667 | ACS |  | ×, × | ×
108 | 27-11-12-001-U | 100411503 | Restoration of Control-Yoke Disconnect Device for lubrication. |  | 0.35625 | ACS |  | ×, I | ×
109 | 27-12-01-001-LH | 100308921 | Lubrication of Aileron PCUs Toggle Links. |  | 0.083333 | ACS |  | ×, × | ×
110 | 27-12-01-001-RH | 100308925 | Lubrication of Aileron PCUs Toggle Links. |  | 0.050694 | ACS |  | ×, × | ×
111 | 27-12-01-002-LH | 100411509 | Detailed Inspection of Aileron PCUs for signs of leakage or other damage. Make sure that all electrical connections are tight and the electrical cables are not twisted and can move freely. |  | 0.020833 | ACS |  | ×, × | ×
112 | 27-12-01-002-RH | 100411513 | Detailed Inspection of Aileron PCUs for signs of leakage or other damage. Make sure that all electrical connections are tight and the electrical cables are not twisted and can move freely. |  | 0.016667 | ACS |  | ×, × | ×
113 | 27-12-01-006-LH | 800047292 | Functional Check of Aileron Backlash. |  | 0.2125 | ACS |  | ACS, × | ×
114 | 27-12-01-006-RH | 800047300 | Functional Check of Aileron Backlash. |  | 0.2125 | ACS |  | ACS, × | ×
115 | 27-12-500-H001-U | 100411518 | Detailed Inspection of LH and RH Flap PSU connectors and bonding jumper. |  | 0.035417 | ACS |  | ×, × | ×
116 | 27-13-500-H001-U | 100411522 | Detailed Inspection of LH and RH Slat PSU connectors and bonding jumper. |  | 0.047917 | ACS |  | ×, × | ×
117 | 27-14-01-001-U | 800047324 | Functional Check of Aileron Trim Actuator. Make sure the single command does not exceed 3.3 seconds. |  | 0.058333 | ACS |  | ACS, × | ×
118 | 27-21-00-001-U | 100598831 | General Visual Inspection of Rudder Mechanical Components. |  | 0.041667 | ACS |  | ×, × | ×
119 | 27-21-03-001-U | 100425817 | Visually check Rudder Pedals Damper. Check oil level on the Rudder Pedals level indicator. |  | 0.0625 | ACS |  | ×, × | ×
120 | 27-22-01-001-U | 100308929 | Lubrication of Rudder PCUs Toggle Links. |  | 0.12361 | ACS |  | ×, × | ×
121 | 27-22-01-002-U | 100411537 | Detailed Inspection of Rudder PCUs for signs of leakage or other damage. Make sure that all electrical connections are tight and the electrical cables are not twisted and can move freely. |  | 0.036806 | ACS |  | ×, × | ×
122 | 27-22-01-005-U | 100411540 | Functional Check of Rudder PCUs (Re-rigging). |  | 0.0625 | ACS |  | ACS, × | ×
123 | 27-22-01-006-U | 100411545 | Functional Check of Rudder Backlash. |  | 0.43056 | ACS |  | ACS, × | ×
124 | 27-22-01-007C-U | 100411548 | Functional Check of Rudder PCU Hinge Moment Limiter. |  | 0.18403 | ACS |  | ACS, × | ×
125 | 27-22-01-007-U | 100871651 | Functional Check of Rudder PCU Hinge Moment Limiter. |  | 0.125 | ACS |  | ACS, × | ×
126 | 27-24-01-001-U | 800047371 | Functional Check of Rudder Trim Actuator. Verify the 3.3 seconds limit for a continuous Rudder command. |  | 0.05 | ACS |  | ACS, × | ×
127 | 27-31-00-001-LH | 100411552 | General Visual Inspection of Elevator Mechanical Components. |  | 0.041667 | ACS |  | ×, × | ×
128 | 27-31-00-001-RH | 100411556 | General Visual Inspection of Elevator Mechanical Components. |  | 0.041667 | ACS |  | ×, × | ×
129 | 27-31-00-002C-U | 100411560 | Operational Check of Control-Column Disconnect System. |  | 0.086111 | ACS |  | ×, × | ×
130 | 27-31-00-002-U | 100308935 | Operational Check of Control-Column Disconnect System. |  | 0.10833 | ACS |  | ×, × | ×
131 | 27-31-02-001-FWDLH | 100308936 | Visually check Control-Column Dampers. Check the Level Indicator of Control-Column Dampers (Left and Right Columns). |  | 0.082639 | ACS |  | ×, × | ×
132 | 27-31-02-001-FWDRH | 100308978 | Visually check Control-Column Dampers. Check the Level Indicator of Control-Column Dampers (Left and Right Columns). |  | 0.082639 | ACS |  | ×, × | ×
133 | 27-31-06-001-U | 100411566 | Restoration of Control-Column Disconnect Device for lubrication. |  | 0.41667 | ACS |  | ×, I | ×
134 | 27-32-01-002-LH | 100411570 | Detailed Inspection of Elevator PCUs for signs of leakage or other damage. Make sure that all electrical connections are tight and the electrical cables are not twisted and can move freely. |  | 0.041667 | ACS |  | ×, × | ×
135 | 27-32-01-002-RH | 100411574 | Detailed Inspection of Elevator PCUs for signs of leakage or other damage. Make sure that all electrical connections are tight and the electrical cables are not twisted and can move freely. |  | 0.034722 | ACS |  | ×, × | ×
136 | 27-32-01-005-LH | 800047434 | Functional Check of Elevator PCUs (Re-rigging). |  | 0.11111 | ACS |  | ACS, × | ×
137 | 27-32-01-005-RH | 100411578 | Functional Check of Elevator PCUs (Re-rigging). |  | 0.072917 | ACS |  | ACS, × | ×
138 | 27-32-01-006-LH | 800047448 | Functional Check of Elevator Backlash. |  | 0.24167 | ACS |  | ACS, × | ×
139 | 27-32-01-006-RH | 800047451 | Functional Check of Elevator Backlash. |  | 0.24167 | ACS |  | ACS, × | ×
140 | 27-36-01-001-U | 100767408 | Operational Check of Stick Shaker Motors. |  | 0.064583 | REI | NHF TASK A-CHECK ITEM | REI, × | ×
141 | 27-40-00-001-U | 100757826 | Functional Check of Horizontal Stabilizer Backlash. |  | 0.44583 | ACS |  | ACS, × | ×
142 | 27-41-01-001-U | 100767409 | Lubrication of Horizontal Stabilizer Actuator. With a Grease Gun, refill Ballnut with grease. |  | 0.0625 | ACS | A-CHECK ITEM | ×, × | ×
143 | 27-41-01-002-U | 100871663 | Detailed Inspection of Horizontal Stabilizer Actuator including Actuator Mechanical Stops and Actuator Upper and Lower Gimbals for any signs of damage. |  | 0.090972 | ACS |  | ×, × | ×
144 | 27-41-01-003-U | 800047470 | Functional Check of Horizontal Stabilizer Actuator. Check of Actuator Locking Mechanism, Torque Limiting Clutch, Electric Travel Limits, Timer Function, Resolver and HS-ACE logic. |  | 0.24167 | ACS |  | ACS, × | ×
145 | 27-41-01-005-U | 100767410 | General Visual Inspection of HSTA Ballnut External Ball Return Circuit. |  | 0.050694 | ACS | A-CHECK ITEM | ×, × | ×
146 | 27-41-01-006C-U | 800047491 | Detailed Inspection of Horizontal Stabilizer Actuator Lower secondary Gimbal. |  | 0.025 | ACS |  | ACS, × | ×
147 | 27-41-01-008-U | 800047501 | Detailed Inspection of Horizontal Stabilizer Actuator No-Back Mechanism for broken or damaged components. |  | 0.15 | ACS |  | ×, × | ×
148 | 27-41-01-009-U | 100308941 | Servicing of Horizontal Stabilizer No-back mechanism oil. |  | 0.083333 | ACS |  | ×, × | ×
149 | 27-43-01-001-U | 100793427 | Functional Check of Horizontal Stabilizer Zero Velocity function. Check Horizontal Stabilizer Zero Velocity Hold functionality. |  | 0.083333 | ACS |  | ACS, × | ×
150 | 27-51-00-004-LH | 100308949 | General Visual Inspection of Flap Aerodynamic Seals. |  | 0.066667 | ACS | NOTE: Flaps have to be fully extended. | ×, × | ×
151 | 27-51-00-004-RH | 100308950 | General Visual Inspection of Flap Aerodynamic Seals. |  | 0.041667 | ACS | NOTE: Flaps have to be fully extended. | ×, × | ×
152 | 27-51-01-002-LH | 100871646 | Lubrication of Flap Actuators Ballscrews. |  | 0.077083 | ACS |  | ×, × | ×
153 | 27-51-01-002-RH | 100871649 | Lubrication of Flap Actuators Ballscrews. |  | 0.0875 | ACS |  | ×, × | ×
154 | 27-51-01-003-LH | 800047539 | Functional Check of Inboard Flap Actuators integrity. |  | 0.17083 | ACS |  | ACS, × | ×
155 | 27-51-01-003-RH | 800047542 | Functional Check of Inboard Flap Actuators integrity. |  | 0.16667 | ACS |  | ACS, × | ×
156 | 27-51-03-001-LH | 800047586 | Lubrication of Flap Torque Tube Splines. |  | 0.19167 | ACS |  | ACS, × | ×
157 | 27-51-03-001-RH | 800047595 | Lubrication of Flap Torque Tube Splines. |  | 0.16667 | ACS |  | ACS, × | ×
158 | 27-51-03-002-LH | 100411619 | Detailed Inspection of Flap Torque Tubes including universal joint boots for cracks or scratches. |  | 0.042361 | ACS |  | ×, × | ×
159 | 27-51-03-002-RH | 100411623 | Detailed Inspection of Flap Torque Tubes including universal joint boots for cracks or scratches. |  | 0.043056 | ACS |  | ×, × | ×
160 | 27-51-10-001-LH | 100736453 | Lubrication of Flap Track Mechanism Needle Rollers. |  | 0.1 | ACS |  | ×, × | ×
161 | 27-51-10-001-RH | 100736456 | Lubrication of Flap Track Mechanism Needle Rollers. |  | 0.12083 | ACS |  | ×, × | ×
162 | 27-51-11-001-LH | 100411785 | Detailed Inspection of Flap Track Mechanism Needle Rollers for condition. |  | 0.083333 | ACS |  | ×, × | ×
163 | 27-51-11-001-RH | 100411789 | Detailed Inspection of Flap Track Mechanism Needle Rollers for condition. |  | 0.027778 | ACS |  | ×, × | ×
164 | 27-62-02-001-LH | 100411626 | Operational Check of Ground Spoilers Control Module Hold-Down Lock Valves. |  | 0.026389 | ACS |  | ×, × | ×
165 | 27-62-02-001-RH | 100411630 | Operational Check of Ground Spoilers Control Module Hold-Down Lock Valves. |  | 0.028472 | ACS |  | ×, × | ×
166 | 27-65-01-001-LH | 100411634 | Operational Check of Multifunction Spoilers PCUs Hold-Down Lock Valves. |  | 0.028472 | ACS |  | ×, × | ×
167 | 27-65-01-001-RH | 100411638 | Operational Check of Multifunction Spoilers PCUs Hold-Down Lock Valves. |  | 0.035417 | ACS |  | ×, × | ×
168 | 27-81-01-002-U | 100411644 | Operational Check to verify Slat Actuator/Track Rack and Pinion disconnection. |  | 0.085417 | ACS |  | ×, × | ×
169 | 27-81-01-003C-LH | 100411646 | Operational Check to verify Slat Actuator or Track Rack and Pinion disconnection. |  | 0.073611 | ACS |  | ×, × | ×
170 | 27-81-01-003C-RH | 100411733 | Operational Check to verify Slat Actuator or Track Rack and Pinion disconnection. |  | 0.16667 | ACS |  | ×, × | ×
171 | 27-81-03-001-LH | 800047652 | Lubrication of Slat Torque Tube Splines. |  | 0.1875 | ACS |  | ACS, × | ×
172 | 27-81-03-001-RH | 100411652 | Lubrication of Slat Torque Tube Splines. |  | 0.39306 | ACS |  | ACS, × | ×
173 | 27-81-03-002-LH | 100411656 | Detailed Inspection of Slat Torque Tubes including universal joint boots for cracks or scratches. |  | 0.054167 | ACS |  | ×, × | ×
174 | 27-81-03-002-RH | 100411660 | Detailed Inspection of Slat Torque Tubes including universal joint boots for cracks or scratches. |  | 0.094444 | ACS |  | ×, × | ×
175 | 27-81-11-001-LH | 100308966 | Lubrication of Slat Track Rack and Pinion Mechanism. |  | 0.34028 | ACS |  | ×, × | ×
176 | 27-81-11-001-RH | 100308982 | Lubrication of Slat Track Rack and Pinion Mechanism. |  | 0.26667 | ACS |  | ×, × | ×
177 | 27-83-01-002C-LH | 100411665 | General Visual Inspection of Outboard Slat Skew Sensor. |  | 0.085417 | ACS |  | ×, × | ×
178 | 27-83-01-002C-RH | 100411669 | General Visual Inspection of Outboard Slat Skew Sensor. |  | 0.10833 | ACS |  | ×, × | ×
179 | 28-11-01-001-LH | 100723057 | Operational Check of Fuel Tank Baffle and Flapper Valves. Check if the valves are free to move. |  | 0.022222 | ACS |  | ×, I | ×
180 | 28-11-01-001-RH | 100723056 | Operational Check of Fuel Tank Baffle and Flapper Valves. Check if the valves are free to move. |  | 0.022222 | ACS |  | ×, I | ×
181 | 28-11-07-001-LH | 100411681 | Functional Check of Fuel Tanks Grounding Points. Resistance check. |  | 0.064583 | ACS |  | ×, × | ×
182 | 28-11-07-001-RH | 100411773 | Functional Check of Fuel Tanks Grounding Points. Resistance check. |  | 0.072917 | ACS |  | ×, × | ×
183 | 28-12-01-001-LH | 100200035 | Functional Check of the Pressure Relief Valve to verify the pressure set point which it opens. |  | 0.01875 | ACS |  | ×, × | ×
184 | 28-12-01-001-RH | 100200039 | Functional Check of the Pressure Relief Valve to verify the pressure set point which it opens. |  | 0.01875 | ACS |  | ×, × | ×
185 | 28-12-05-001C-LH | 100723062 | Operational Check of Float Vent Valve. Check if the valves are free to move. |  | 0.017361 | ACS |  | ×, × | ×
186 | 28-12-05-001C-RH | 100723061 | Operational Check of Float Vent Valve. Check if the valves are free to move. |  | 0.017361 | ACS |  | ×, × | ×
187 | 28-12-05-001-LH | 100723054 | Operational Check of Float Vent Valve. Check if the valves are free to move. |  | 0.017361 | ACS |  | ×, × | ×
188 | 28-12-05-001-RH | 100723055 | Operational Check of Float Vent Valve. Check if the valves are free to move. |  | 0.017361 | ACS |  | ×, × | ×
189 | 28-12-11-001C-LH | 100411695 | Detailed Inspection of Fuel Tank Flame Arrestor Honeycomb for clogging. |  | 0.0375 | ACS |  | ×, × | ×
190 | 28-12-11-001C-RH | 100411699 | Detailed Inspection of Fuel Tank Flame Arrestor Honeycomb for clogging. |  | 0.041667 | ACS |  | ×, × | ×
191 | 28-12-11-001-LH | 100411703 | Detailed Inspection of Fuel Tank Flame Arrestor Honeycomb for clogging. |  | 0.046528 | ACS |  | ×, × | ×
192 | 28-12-11-001-RH | 100411707 | Detailed Inspection of Fuel Tank Flame Arrestor Honeycomb for clogging. |  | 0.027778 | ACS |  | ×, × | ×
193 | 28-12-11-002C-LH | 100411711 | Operational Check of Fuel Tank Flame Arrestor In and Out Flow Valves. Check if the valves are free to move. |  | 0.031944 | ACS |  | ×, × | ×
194 | 28-12-11-002C-RH | 100411715 | Operational Check of Fuel Tank Flame Arrestor In and Out Flow Valves. Check if the valves are free to move. |  | 0.031944 | ACS |  | ×, × | ×
195 | 28-12-11-002-LH | 100411719 | Operational Check of Fuel Tank Flame Arrestor In and Out Flow Valves. Check if the valves are free to move. |  | 0.034722 | ACS |  | ×, × | ×
196 | 28-12-11-002-RH | 100411723 | Operational Check of Fuel Tank Flame Arrestor In and Out Flow Valves. Check if the valves are free to move. |  | 0.031944 | ACS |  | ×, × | ×
197 | 28-21-00-001-U | 800047739 | Operational Check of Crossfeed System. Operate the Crossfeed Switch, checking the system status on Fuel Synoptic Page. |  | 0.041667 | ACS |  | ×, × | ×
198 | 28-21-17-002-LH | 100793415 | Operational Check of the Engine Fuel Shutoff Valve. Check if the valve is closing by pulling the fire handle. |  | 0.010417 | ACS |  | ACS, × | ×
199 | 28-21-17-002-RH | 100793414 | Operational Check of the Engine Fuel Shutoff Valve. Check if the valve is closing by pulling the fire handle. |  | 0.010417 | ACS |  | ACS, × | ×
200 | 28-22-00-001-U | 100411729 | Functional Check of APU Fuel Feed Lines Shroud and Drains. Leak test. |  | 0.52083 | ACS |  | ACS, × | ×
201 | 28-40-00-001-LH | 100411794 | Functional Check of Fuel Low Level Sensor. Transfer Fuel from one wing to the other until the low level message appears on EICAS. |  | 0.059722 | REI |  | ACS, × | ×
202 | 28-40-00-001-RH | 100411798 | Functional Check of Fuel Low Level Sensor. Transfer Fuel from one wing to the other until the low level message appears on EICAS. |  | 0.059722 | REI |  | ACS, × | ×
203 | 28-40-04-001-U | 100411803 | Functional Check of Fuel Temperature Sensor. Check sensor indication accuracy. |  | 0.033333 | REI |  | ×, × | ×
204 | 28-50-00-002F-LH | 100493344 | Inspect (General Visual) the Wing Leading Edge Harness. Examine for adequate installation, lost clamps, chafing, connectors and damages. |  | 0.11458 | REI |  | ×, × | ×
205 | 28-50-00-002F-RH | 100493345 | Inspect (General Visual) the Wing Leading Edge Harness. Examine for adequate installation, lost clamps, chafing, connectors and damages. |  | 0.14583 | REI |  | ×, × | ×
206 | 28-50-00-003F-LH | 100411814 | Inspect (General Visual) the Wing Trailing Edge Harness. Examine for adequate installation, lost clamps, chafing, connectors and damages. |  | 0.072917 | REI |  | ×, × | ×
207 | 28-50-00-003F-RH | 100411818 | Inspect (General Visual) the Wing Trailing Edge Harness. Examine for adequate installation, lost clamps, chafing, connectors and damages. |  | 0.083333 | REI |  | ×, × | ×
208 | 28-50-00-004F-LH | 100411822 | Inspect (General Visual) the Wing Stub Harness. Examine for adequate installation, lost clamps, chafing, connectors and damages. |  | 0.072917 | REI |  | ×, × | ×
209 | 28-50-00-004F-RH | 100411826 | Inspect (General Visual) the Wing Stub Harness. Examine for adequate installation, lost clamps, chafing, connectors and damages. |  | 0.045139 | REI |  | ×, × | ×
210 | 28-50-00-007F-LH | 100291009 | Inspect (General Visual) the Flexible Connections, Jumpers, Clamps and Flanges at Wing Stub. Examine for excessive wearing, and adequate installation. |  | 0.048611 | REI |  | ×, I | ×
211 | 28-50-00-007F-RH | 100291010 | Inspect (General Visual) the Flexible Connections, Jumpers, Clamps and Flanges at Wing Stub. Examine for excessive wearing, and adequate installation. |  | 0.044444 | REI |  | ×, I | ×
212 | 28-50-00-010F-U | 100411830 | Inspect (General Visual) the Fuel Conditioning Unit (FCU) for adequate installation. |  | 0.03125 | REI |  | ×, × | ×
213 | 28-50-00-014F-LH | 100291011 | Inspect (General Visual) the Flexible Connections, Jumpers, Clamps and Flanges at Wing Main Box. Examine for excessive wearing, and adequate installation. |  | 0.027778 | REI |  | ×, × | ×
214 | 28-50-00-014F-RH | 100291012 | Inspect (General Visual) the Flexible Connections, Jumpers, Clamps and Flanges at Wing Main Box. Examine for excessive wearing, and adequate installation. |  | 0.03125 | REI |  | ×, × | ×
215 | 29-11-00-001-LH | 100411839 | Functional Check of No.1 & 2 Hydraulic System Bootstrap Systems. Check proper operation of bootstrap main components (Priority Valve and other main components) through ACMPs operation and pressure monitoring. |  | 0.0125 | ACS |  | ACS, × | ×
216 | 29-11-00-001-RH | 100411843 | Functional Check of No.1 & 2 Hydraulic System Bootstrap Systems. Check proper operation of bootstrap main components (Priority Valve and other main components) through ACMPs operation and pressure monitoring. |  | 0.0125 | ACS |  | ACS, × | ×
217 | 29-11-00-003-AFTLH | 100751067 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.013889 | ACS | A-CHECK ITEM | ACS, × | ×
218 | 29-11-00-003-AFTRH | 100751068 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.072917 | ACS | A-CHECK ITEM | ACS, × | ×
219 | 29-11-00-003-FWDLH | 100751069 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.013889 | ACS | A-CHECK ITEM | ×, × | ×
220 | 29-11-00-003-FWDRH | 100751070 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.013889 | ACS | A-CHECK ITEM | ×, × | ×
221 | 29-11-00-004-U | 100411845 | Functional Check of Power Transfer Unit (PTU) System. |  | 0.15833 | ACS |  | ×, × | ×
222 | 29-11-11-001C-LH | 800128854 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.041667 | ACS |  | ACS, × | ×
223 | 29-11-11-001C-RH | 800128821 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.041667 | ACS |  | ACS, × | ×
224 | 29-11-11-001F-LH | 100308988 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.033333 | ACS |  | ACS, × | ×
225 | 29-11-11-001F-RH | 100308989 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.036806 | ACS |  | ACS, × | ×
226 | 29-11-11-001-LH | 100308993 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.092361 | ACS |  | ACS, × | ×
227 | 29-11-11-001-RH | 100308994 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.036806 | ACS |  | ACS, × | ×
228 | 29-11-20-001-U | 100411855 | Functional Check of Hydraulic System 2 Priority Valve. |  | 0.16042 | ACS |  | ACS, × | ×
229 | 29-11-30-001-LH | 100533429 | Functional Check of No.1 & 2 Hydraulic Systems Accumulators Pre-Charge. |  | 0.041667 | ACS |  | ACS, × | ×
230 | 29-11-30-001-RH | 100533433 | Functional Check of No.1 & 2 Hydraulic Systems Accumulators Pre-Charge. |  | 0.041667 | ACS |  | ACS, × | ×
231 | 29-12-00-003-AFTLH | 100702272 | Visual Check of No.3 Hydraulic System Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.058333 | ACS | A-CHECK ITEM | ACS, × | ×
232 | 29-12-00-003-AFTRH | 100702273 | Visual Check of No.3 Hydraulic System Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.058333 | ACS | A-CHECK ITEM | ACS, × | ×
233 | 29-12-00-004C-U | 100730831 | Functional Check of No.3 Hydraulic System Unloader Components. Check Hydraulic System 3 Pump Unloader Valve and Flow Limiter Valve. |  | 0.0625 | ACS |  | ACS, × | ×
234 | 29-12-00-004-U | 100730835 | Functional Check of No.3 Hydraulic System Unloader Components. Check Hydraulic System 3 Pump Unloader Valve and Flow Limiter Valve. |  | 0.074306 | ACS |  | ACS, × | ×
235 | 29-12-00-005C-U | 100524177 | Functional Check of No.3 Hydraulic System Internal Leakage. |  | 0.25069 | ACS |  | ACS, × | ×
236 | 29-12-00-005-U | 800047895 | Functional Check of No.3 Hydraulic System Internal Leakage. |  | 0.25 | ACS |  | ACS, × | ×
237 | 29-12-30-001C-U | 100411868 | Functional Check of No.3 Hydraulic System Accumulator Pre-Charge. |  | 0.041667 | ACS | A-CHECK ITEM | ×, × | ×
238 | 29-32-00-001-U | 100702275 | Operational Check of Hydraulic Systems Reservoir. |  | 0.022917 | ACS | A-CHECK ITEM | ×, × | ×
239 | 29-33-01-001F-U | 100662834 | Operational Check of Hydraulic Systems Temperature Transducers. |  | 0.033333 | ACS | A-CHECK ITEM | ×, × | ×
240 | 29-33-02-001C-U | 800047935 | Operational Check of No.3 Hydraulic System ACMPs Automatic Shutdown. |  | 0.066667 | ACS |  | ×, × | ×
241 | 29-33-02-001-U | 800047934 | Operational Check of No.3 Hydraulic System ACMPs Automatic Shutdown. |  | 0.070833 | ACS |  | ×, × | ×
242 | 29-33-02-002F-LH | 800047950 | Functional Check of No.1 & 2 Hydraulic Systems Temperature Switches. |  | 0.028472 | ACS |  | ×, × | ×
243 | 29-33-02-002F-RH | 800047953 | Functional Check of No.1 & 2 Hydraulic Systems Temperature Switches. |  | 0.028472 | ACS |  | ×, × | ×
244 | 29-33-02-002-LH | 800047938 | Functional Check of No.1 & 2 Hydraulic Systems Temperature Switches. |  | 0.025694 | ACS |  | ×, × | ×
245 | 29-33-02-002-RH | 100411878 | Functional Check of No.1 & 2 Hydraulic Systems Temperature Switches. |  | 0.0625 | ACS |  | ×, × | ×
246 | 29-33-02-003C-U | 100411882 | Functional Check of No.3 Hydraulic System Temperature Switch. |  | 0.053472 | ACS |  | ×, × | ×
247 | 29-33-02-003-U | 800047958 | Functional Check of No.3 Hydraulic System Temperature Switch. |  | 0.083333 | ACS |  | ×, × | ×
248 | 30-11-00-001F-LH | 100309003 | General Visual Inspection of Wing Anti-Ice Supply Ducts and Components for insulation integrity. |  | 0.061806 | ACS |  | ×, × | ×
249 | 30-11-00-001F-RH | 100309326 | General Visual Inspection of Wing Anti-Ice Supply Ducts and Components for insulation integrity. |  | 0.069444 | ACS |  | ×, × | ×
250 | 30-11-01-001-LH | 100736412 | Cleaning of Wing Anti-Ice Valve Filter. |  | 0.041667 | ACS | FOR P/N:1001249-2/, S/N:2009060001
251 | 30-11-01-001-RH | 100736410 | Cleaning of Wing Anti-Ice Valve Filter. |  | 0.041667 | ACS | FOR P/N:1001249-2, S/N:2009051782
252 | 30-11-06-001-LH | 100619087 | Detailed Inspection of Wing Anti-Ice Slat Hoses for signs of excessive wear, tearing, or visual signs of leakage such as localized discoloring. |  | 0.041667 | ACS |  | ×, × | ×
253 | 30-11-06-001-RH | 100619091 | Detailed Inspection of Wing Anti-Ice Slat Hoses for signs of excessive wear, tearing, or visual signs of leakage such as localized discoloring. |  | 0.041667 | ACS |  | ×, × | ×
254 | 30-21-00-001-LH | 100411891 | General Visual Inspection for distortion, rupture, security and general condition of the installation. Inspect exhaust duct for obstruction. |  | 0.025 | ACS |  | ×, × | ×
255 | 30-21-00-001-RH | 100411895 | General Visual Inspection for distortion, rupture, security and general condition of the installation. Inspect exhaust duct for obstruction. |  | 0.030556 | ACS |  | ×, × | ×
256 | 30-21-00-002-LH | 100619097 | Detailed Inspection of the engine anti-icing interbulkhead duct for cracks, condition and security. |  | 0.027778 | ACS |  | ×, × | ×
257 | 30-21-00-002-RH | 100619101 | Detailed Inspection of the engine anti-icing interbulkhead duct for cracks, condition and security. |  | 0.030556 | ACS |  | ×, × | ×
258 | 30-21-01-001-LH | 100411907 | Special Detailed Inspection (Boroscope) of the Piccolo Tube for condition and security. |  | 0.15486 | ACS | Borescope | ACS, × | ×
259 | 30-21-01-001-RH | 100411911 | Special Detailed Inspection (Boroscope) of the Piccolo Tube for condition and security. |  | 0.16875 | ACS | Borescope | ACS, × | ×
260 | 30-21-11-001-LH | 100686972 | Functional Check of the engine anti-icing system Shroud leak Detector Switch set point. |  | 0.071528 | ACS |  | ACS, × | ×
261 | 30-21-11-001-RH | 100686973 | Functional Check of the engine anti-icing system Shroud leak Detector Switch set point. |  | 0.076389 | ACS |  | ACS, × | ×
262 | 30-32-00-001-U | 100411928 | Operational Check of Static Port Heater. |  | 0.065972 | REI |  | ×, × | ×
263 | 31-03-140-H001-U | 100686980 | Detailed Inspection of MAU 3 connectors, 360° metallic backshells, metallic chassis bonded points and electrical bonding by interface between unit and aircraft structure. |  | 0.024306 | REI |  | ×, × | ×
264 | 31-31-00-001-U | 100411943 | Functional Check of Digital Voice and Data Recorder System parameters. |  | 0.34583 | REI |  | ×, × | ×
265 | 31-41-00-001-U | 100412073 | Cleaning the air inlet screen of the MAU cabinet. |  | 0.15417 | REI | NHF TASK | ×, × | ×
266 | 32-01-710-H001-U | 100411947 | Detailed Inspection of NLG WOW Sensors 1 and 2 Connectors, Overbraids and Electrical Bonding by interface between unit and aircraft structure. |  | 0.014583 | REI |  | ×, × | ×
267 | 32-02-730-H001-U | 100411951 | Detailed Inspection of RH and LH MLG WOW Sensors 1 and 2 Connectors, Overbraids and Electrical Bonding by interface between unit and aircraft structure. |  | 0.019444 | REI |  | ×, × | ×
268 | 32-03-710-H001-U | 100411955 | Detailed Inspection of NLG Steering Feedback Sensors 1 and 2 Connectors, Overbraids and Electrical Bonding by interface between unit and aircraft structure. |  | 0.014583 | REI |  | ×, × | ×
269 | 32-04-710-H001-U | 100411959 | Detailed Inspection of NLG Down Lock Sensors 1 and 2 Connectors, Overbraids and Electrical Bonding by interface between unit and aircraft structure. |  | 0.014583 | REI | NHF TASK | ×, × | ×
270 | 32-05-730-H001-U | 100411963 | Detailed Inspection of RH and LH MLG Down Lock Sensors 1 and 2 Connectors, Overbraids and Electrical Bonding by interface between unit and aircraft structure. |  | 0.019444 | REI | NHF TASK | ×, × | ×
271 | 32-11-00-002-LH | 100736474 | Servicing of MLG Shock Absorber Nitrogen Chamber. |  | 0.125 | ACS |  | ×, × | ×
272 | 32-11-00-002-RH | 100736475 | Servicing of MLG Shock Absorber Nitrogen Chamber. |  | 0.13194 | ACS |  | ×, × | ×
273 | 32-11-00-006-LH | 100619120 | Complete servicing of Main Landing Gear Shock Strut. |  | 0.19583 | ACS |  | ×, × | ×
274 | 32-11-00-006-RH | 100619121 | Complete servicing of Main Landing Gear Shock Strut. |  | 0.16806 | ACS |  | ×, × | ×
275 | 32-11-002-0205-U | 100687025 | Detailed Inspection of MLG Sliding Tube - Area covered by MLG Shock Strut. |  | 0.18194 | ACS | NOTE: Aircraft jacking is required. | ACS, × | ×
276 | 32-11-11-001-LH | 100411976 | Functional check MLG Torque Link Clearance and Shimmy Damper Torque. |  | 0.25972 | ACS |  | ACS, × | ×
277 | 32-11-11-001-RH | 100411980 | Functional check MLG Torque Link Clearance and Shimmy Damper Torque. |  | 0.25972 | ACS |  | ACS, × | ×
278 | 32-11-11-002-LH | 100687002 | Functional check MLG Torque Link Backlash. |  | 0.375 | ACS |  | ACS, ×
279 | 32-11-11-002-RH | 100687009 | Functional check MLG Torque Link Backlash. |  | 0.375 | ACS |  | ACS, ×
280 | 32-21-00-002-U | 100736489 | Servicing of NLG Shock Absorber Nitrogen Chamber. |  | 0.09375 | ACS |  | ×, × | ×
281 | 32-21-00-006-U | 100619132 | Complete servicing of Nose Landing Gear Shock Strut. |  | 0.17639 | ACS |  | ×, × | ×
282 | 32-21-006-1048-U | 100619133 | General Visual Inspection of NLG Sliding Tube - Area covered by NLG Shock Strut. |  | 0.13611 | STR | NOTE: Aircraft jacking is required. | ACS, × | ×
283 | 32-21-09-001-U | 800048111 | Functional check of NLG Torque Link Clearance. |  | 0.045833 | ACS |  | ×, × | ×
284 | 32-33-01-001-U | 800048114 | Operational Check of Landing Gear Control Lever Locking Solenoid. |  | 0.11667 | ACS |  | ACS, × | ×
285 | 32-34-00-001C-U | 800048118 | Functional Check of Mechanical Emergency Extension System. Operate Landing Gears using the Free-fall Lever, measuring the extension time, and the load to actuate the Emergency Handle. |  | 0.0875 | ACS |  | ACS, × | ×
286 | 32-34-00-001-U | 100411989 | Functional Check of Mechanical Emergency Extension System. Operate Landing Gears using the Free-fall Lever, measuring the extension time, and the load to actuate the Emergency Handle. |  | 0.12917 | ACS | NHF TASK | ACS, × | ×
287 | 32-34-00-002-LH | 100493724 | Detailed Inspection of Mechanical Emergency Extension System Components for integrity, general conditions and cracks. |  | 0.067361 | ACS | NHF TASK | ACS, × | ×
288 | 32-34-00-002-RH | 100493706 | Detailed Inspection of Mechanical Emergency Extension System Components for integrity, general conditions and cracks. |  | 0.063889 | ACS | NHF TASK | ACS, × | ×
289 | 32-34-00-003-LH | 100411997 | Functional Check of Mechanical Emergency Extension System by measuring the cables tension. |  | 0.12222 | ACS | NHF TASK | ×, × | ×
290 | 32-34-00-003-RH | 100412091 | Functional Check of Mechanical Emergency Extension System by measuring the cables tension. |  | 0.12222 | ACS | NHF TASK | ×, × | ×
291 | 32-35-00-001-U | 800048129 | Operational Check of Electrical Emergency Release System. Operate Landing Gears using the Extension Override Switch. |  | 0.125 | ACS |  | ACS, × | ×
292 | 32-40-00-001-LH | 800048132 | Operational Check of Main Brake and Emergency/Parking Brake Hydraulic Fuses. |  | 0.095833 | ACS |  | ×, × | ×
293 | 32-40-00-001-RH | 800048135 | Operational Check of Main Brake and Emergency/Parking Brake Hydraulic Fuses. |  | 0.1 | ACS |  | ×, × | ×
294 | 32-41-17-001-U | 100494133 | Operational Check of Return Line Check Valve of Main Brake Control System. |  | 0.11667 | ACS |  | ×, ×
295 | 32-44-00-002-U | 100686954 | General Visual Inspection of Mechanical Linkage from Emergency/Parking Brake Handle/Cable to Emergency/Parking Brake Valve. Inspect for integrity and general conditions. |  | 0.13333 | ACS |  | ACS/CBN, × | ×
296 | 32-44-11-001-U | 100871653 | Operational Check of Return Line Check Valve of Emergency/Parking Brake System. |  | 0.05 | ACS |  | ×, × | ×
297 | 32-44-13-001-U | 100793410 | Functional Check of Emergency/Parking Brake Accumulator for Nitrogen Pre-Charge. |  | 0.027083 | ACS |  | ACS, × | ×
298 | 33-50-21-002-LH | 100309045 | General Visual Inspection of Photoluminescent Strip for missing pieces or polycarbonate covered track damage. |  | 0.041667 | CBN |  | ×, × | ×
299 | 33-50-21-002-RH | 100309328 | General Visual Inspection of Photoluminescent Strip for missing pieces or polycarbonate covered track damage. |  | 0.041667 | CBN |  | ×, × | ×
300 | 33-51-01-002-AFT | 100571096 | Inspect (General Visual) Flashlight and Recharging Bracket. |  | 0.019444 | CBN |  | ×, × | ×
301 | 33-51-01-002-FWD | 100571100 | Inspect (General Visual) Flashlight and Recharging Bracket. |  | 0.01875 | CBN |  | ×, × | ×
302 | 33-51-01-002-FWDLH | 100571104 | Inspect (General Visual) Flashlight and Recharging Bracket. |  | 0.020139 | CBN |  | ×, × | ×
303 | 33-51-01-002-FWDRH | 100571108 | Inspect (General Visual) Flashlight and Recharging Bracket. |  | 0.020139 | CBN |  | ×, × | ×
304 | 34-01-120-H001-U | 100412008 | General Visual Inspection of ADSPs 1, 2, 3 and 4 Connectors, 360° Metallic backshell and Electrical Bonding by interface between unit and aircraft structure. |  | 0.016667 | REI |  | ×, × | ×
305 | 34-15-00-001-U | 100309049 | Functional check of the Pitot Static System ADS 1, ADS 2 and ADS 3 (altitude and airspeed). |  | 0.42708 | REI | NHF TASK | REI, × | ×
306 | 34-15-00-002-U | 100687026 | Special Detailed Inspection of ADSPs Coverplate step and Radome step/gap in the RVSM Critical Region. |  | 0.075 | REI |  | ×, × | ×
307 | 35-10-00-001-LH | 100309070 | Operational Check of Crew Oxygen Masks and Stowage Box. |  | 0.059028 | CBN |  | ×, × | ×
308 | 35-10-00-001-M | 100309074 | Operational Check of Crew Oxygen Masks and Stowage Box. |  | 0.049306 | CBN |  | ×, × | ×
309 | 35-10-00-001-RH | 100309078 | Operational Check of Crew Oxygen Masks and Stowage Box. |  | 0.048611 | CBN |  | ×, × | ×
310 | 35-10-00-002-LH | 100793464 | Detailed Inspection of Crew Oxygen Masks for deterioration, discoloration, cracks, wear and damage. |  | 0.038194 | CBN |  | ×, × | ×
311 | 35-10-00-002-M | 100793406 | Detailed Inspection of Crew Oxygen Masks for deterioration, discoloration, cracks, wear and damage. |  | 0.035417 | CBN |  | ×, × | ×
312 | 35-10-00-002-RH | 100793405 | Detailed Inspection of Crew Oxygen Masks for deterioration, discoloration, cracks, wear and damage. |  | 0.041667 | CBN |  | ×, × | ×
313 | 35-11-00-001-U | 800048273 | Visual Check of Pressure Transducer Indication on Synoptic Page versus External Gauge Indication. |  | 0.058333 | CBN |  | ×, × | ×
314 | 35-11-02-001-U | 800048274 | Functional Check of Crew Oxygen Cylinder Pressure Transducer. |  | 0.14444 | CBN |  | CBN, × | ×
315 | 35-20-01-001-U | 100409720 | Discard of Passenger Chemical Oxygen Generators. |  | 0.041667 | CBN | POS:FWD RH ATT REPLACE P/N:803000-22, S/N:A08042137
316 | 35-20-01-001-U | 100409721 | Discard of Passenger Chemical Oxygen Generators. |  | 0.041667 | CBN | POS:FWD LH ATT REPLACE P/N:803000-22, S/N:A08042144
317 | 35-20-01-001-U | 800057224 | Discard of Passenger Chemical Oxygen Generators. |  | 0.041667 | CBN | POS:AFT LH LAV REPLACE P/N:803000-22, S/N:A08111923
318 | 35-20-01-001-U | 800057229 | Discard of Passenger Chemical Oxygen Generators. |  | 0.041667 | CBN | POS:AFT LH ATT REPLACE P/N:803000-22, S/N:A08111988
319 | 35-20-04-001-LH | 100412041 | Detailed Inspection of Passenger Oxygen Masks for integrity, tears, wear and general conditions. |  | 0.58333 | CBN |  | ×, × | ×
320 | 35-20-04-001-RH | 100412100 | Detailed Inspection of Passenger Oxygen Masks for integrity, tears, wear and general conditions. |  | 0.58333 | CBN |  | ×, × | ×
321 | 35-20-06-001-U | 100412045 | General Visual Inspection of Lavatory Gaseous Oxygen Cylinder. |  | 0.072222 | CBN |  | ×, × | ×
322 | 35-21-00-001-U | 800048285 | Functional Check of Passenger Oxygen System in Auto Mode, including Altitude Pressure Switch. |  | 0.20833 | CBN | NHF TASK | CBN, × | ×
323 | 35-21-00-002-U | 800048288 | Operational Check of Passenger Oxygen System in Manual Mode. |  | 0.25417 | CBN | NHF TASK | CBN, × | ×
324 | 35-30-01-002-U | 100309086 | Visual Check of Portable Oxygen Cylinders Pressure Gauge Indication. |  | 0.023611 | ACS |  | ×, × | ×
325 | 35-30-02-001-U | 100793426 | Inspect (General Visual) Portable Oxygen Continuous Flow Masks for kinks, contamination, wear, tears and cracks. |  | 0.030556 | ACS |  | ×, × | ×
326 | 36-11-00-001C-U | 100412052 | Operational Check of Bleed Pushbutton. |  | 0.067361 | ACS |  | ×, × | ×
327 | 36-11-01-001-LH | 100736415 | Cleaning of High Stage Bleed Valve Wire Mesh Filter by Ultrasonic Method. |  | 0.041667 | ACS | FOR P/N:1001246-3, S/N:2014060038
328 | 36-11-02-002-LH | 100309094 | Functional Check of Low Stage Bleed Check Valve. |  | 0.29792 | ACS |  | ACS, × | ×
329 | 36-11-02-002-RH | 100309098 | Functional Check of Low Stage Bleed Check Valve. |  | 0.34028 | ACS |  | ACS, × | ×
330 | 36-11-03-001-LH | 100575390 | Cleaning of Nacelle Pressure-Regulating Shutoff-Valve Filter by ultrasonic method. |  | 0.041667 | ACS | FOR P/N:1001246-3, S/N:2008020224
331 | 36-11-03-001-RH | 100654137 | Cleaning of Nacelle Pressure-Regulating Shutoff-Valve Filter by ultrasonic method. |  | 0.041667 | ACS | FOR P/N:1001246-3, S/N:2017010070
332 | 36-11-06-001-LH | 800229183 | Cleaning of Torque Motor Controller Wire Mesh Filter by Ultrasonic Method. |  | 0.041667 | ACS | FOR P/N:1001253-1, S/N:08121240
333 | 36-11-09-001-LH | 800578604 | Cleaning of Fan Air Valve Wire Mesh Filter by Ultrasonic Method. |  | 0.041667 | ACS | FOR P/N:1002166-6, S/N:2011080155
334 | 36-11-09-001-RH | 800581242 | Cleaning of Fan Air Valve Wire Mesh Filter by Ultrasonic Method. |  | 0.041667 | ACS | FOR P/N:1002166-6, S/N:2011080383
335 | 38-11-00-001-U | 100607603 | Disinfection of Potable Water System Components. |  | 0.2625 | CBN |  | ×, × | ×
336 | 38-32-06-001-U | 100412064 | General Visual Inspection of Waste Tank Water Separator. Inspect the Water Separator filter for evidence of waste accumulation, corrosion or damage. |  | 0.10208 | CBN |  | ×, × | ×
337 | 38-41-00-001-U | 100309105 | Discard of Air Manifold Air Filter. |  | 0.10764 | CBN |  | ×, × | ×
338 | 44-10-00-001-U | 100793433 | Operational check of the Cabin Loudspeakers. |  | 0.08125 | CBN |  | ×, × | ×
339 | 49-12-00-001-U | 100619176 | Functional Check of APU Mount Elastomer. Check the gap between each mount housing and mounting bracket. |  | 0.048611 | ACS |  | ACS, × | ×
340 | 49-16-01-001-U | 100412105 | Detailed Inspection of APU Air Inlet Silencer for evidence of cracks or feltmetal contamination. |  | 0.083333 | ACS |  | ×, × | APU Air Inlet Silencer
341 | 49-62-01-001-U | 800048352 | Operational Check of APU Emergency Shutdown and APU Shutoff Valve. |  | 0.045833 | ACS |  | ×, × | ×
342 | 49-80-01-001-U | 100412110 | Detailed Inspection of APU Exhaust Liner for evidence of cracking, damage or feltmetal contamination. |  | 0.14306 | ACS |  | ×, × | APU exhaust silencer liner
343 | 50-22-01-001-AFT | 100309110 | General Visual Inspection of Cargo Door Nets. |  | 0.035417 | ACS |  | ×, × | aft cargo door net
344 | 50-22-01-001-FWD | 100309114 | General Visual Inspection of Cargo Door Nets. |  | 0.033333 | ACS |  | ×, × | FWD cargo door net
345 | 50-32-00-001-AFT | 100309118 | Inspect (General Visual) FWD and AFT Cargo Compartments Partitions. |  | 0 | ACS |  | ×, × | aft cargo door net
346 | 50-32-00-001-FWD | 100309119 | Inspect (General Visual) FWD and AFT Cargo Compartments Partitions. |  | 0.020139 | ACS |  | ×, × | FWD cargo door net
347 | 52-10-003-0001-U | 100514692 | General Visual Inspection of Fwd Passenger Door Stops at Fuselage Cutout Area - External Side at Fuselage Cutout Area. |  | 0.019444 | STR |  | ×, × | ×
348 | 52-10-003-0002-AFTLH | 100513460 | General Visual Inspection of Aft Passenger Door Stops at Fuselage Cutout Area - External Side at Fuselage Cutout Area. |  | 0.028472 | STR |  | ×, × | ×
349 | 52-10-003-0112-U | 100412120 | Detailed Inspection of Fwd Passenger Door Stops at Door and Fuselage - External Side of Door and Fuselage. |  | 0.014583 | STR |  | ×, × | ×
350 | 52-10-003-0126-U | 100412124 | Detailed Inspection of Aft Passenger Door Stops at Door and Fuselage - External Side of Door and Fuselage. |  | 0.023611 | STR |  | ×, × | ×
351 | 52-11-00-001-FWDLH | 100412128 | Lubrication of Fwd Passenger Door. |  | 0.041667 | CBN |  | ×, × | ×
352 | 52-11-20-003-FWDLH | 100412133 | Detailed Inspection of Fwd Passenger Door Main Shaft and Hoisting Mechanism Assembly - Internal side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
353 | 52-11-22-001-FWDLH | 100412137 | Detailed Inspection of Fwd Passenger Door Box Mechanism - Internal and External Side of Door for condition, disconnection and rupture. |  | 0.011111 | CBN |  | ×, × | ×
354 | 52-11-23-002-FWDLH | 800048495 | Functional check to verify the Forward Passenger Door Stop assemblies adjustment. |  | 0.041667 | CBN |  | CBN, × | ×
355 | 52-11-23-003-FWDLH | 100412142 | Detailed Inspection of Fwd Passenger Door Stops at Door and Fuselage Assemblies - External side of the door for condition, disconnection and rupture. |  | 0.041667 | CBN |  | ×, × | ×
356 | 52-11-25-001-FWDLH | 100687018 | Detailed Inspection of Fwd Passenger Door Vent Flap tube and Vent Flap Assembly - Internal and External Side of Door for condition, disconnection and rupture. |  | 0.015972 | CBN |  | ×, × | ×
357 | 52-11-27-001-U | 100619197 | Operational Check of Fwd Passenger Door Damper for loss of damping. |  | 0.025 | CBN |  | ×, × | ×
358 | 52-11-30-003-FWDLH | 800048509 | Detailed Inspection of Fwd Passenger Door Hook , Arm Assembly and actuator Assembly - Internal side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
359 | 52-11-40-001-FWDLH | 100412151 | Detailed Inspection of Fwd Passenger Door Slide Bellcrank, Girt Bar and Slide Mechanism (Fixtures, Bearings and Flexball) - Internal Side of Door for condition, disconnection and rupture. |  | 0.058333 | CBN |  | CBN, × | ×
360 | 52-11-40-003-U | 100412155 | Operational Check of Fwd Passenger Door full opening from inside (without Slide release) in emergency configuration (with EOS percussion). |  | 0.17222 | CBN |  | CBN, × | ×
361 | 52-11-40-004-U | 800048538 | Operational check of slide disarming during outside opening of the Fwd Passenger Door. |  | 0.079167 | CBN |  | CBN, × | emergency evacuation slide
362 | 52-11-51-001-U | 800048541 | Detailed Inspection of Fwd Passenger Door Pneumatic Assembly - Internal Side of Door for condition and rupture. |  | 0.033333 | CBN |  | ×, × | ×
363 | 52-11-51-003-FWDLH | 100412160 | Functional Check of Fwd Passenger Door Pneumatic Assembly Gauge. |  | 0.048611 | CBN |  | CBN, × | ×
364 | 52-11-52-001-U | 100598841 | Detailed Inspection of forward Passenger Door Control Mechanism - Internal Side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
365 | 52-12-00-001-AFTLH | 100412166 | Lubrication of Aft Passenger Door. |  | 0.024306 | CBN |  | ×, × | ×
366 | 52-12-20-003-AFTLH | 800048559 | Detailed Inspection of Aft Passenger Door Main Shaft and Hoisting Mechanism Assembly - Internal Side of Door for condition, disconnection and rupture. |  | 0.0125 | CBN |  | ×, × | ×
367 | 52-12-22-001-AFTLH | 800048562 | Detailed Inspection of Aft Passenger Door Box Mechanism - Internal and External Side of Door for condition, disconnection and rupture. |  | 0.0125 | CBN |  | ×, × | ×
368 | 52-12-23-002-AFTLH | 800048565 | Functional check to verify the Stop assemblies adjustment. |  | 0.0625 | CBN |  | CBN, × | ×
369 | 52-12-23-003-AFTLH | 100412177 | Detailed Inspection of Aft Passenger Door Stops at Door and Fuselage Assemblies - External side of the door for condition, disconnection and rupture. |  | 0.020833 | CBN |  | ×, × | ×
370 | 52-12-25-001-AFTLH | 100686988 | Detailed Inspection of the Aft Passenger Door Vent Flap tube and Vent Flap Assembly - Internal and external side of the door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
371 | 52-12-27-001-AFTLH | 100619212 | Operational Check of Aft Passenger Door Damper for loss of damping. |  | 0.022222 | CBN |  | ×, × | ×
372 | 52-12-30-003-AFTLH | 100412182 | Detailed Inspection of Aft Passenger Door Hook, Arm Assembly and Actuator Assembly - Internal side of Door for condition, disconnection and rupture. |  | 0.0125 | CBN |  | ×, × | ×
373 | 52-12-40-001-AFTLH | 100412186 | Detailed Inspection of Aft Passenger Door Slide Bellcrank, Girt Bar and Slide Mechanism (Fixtures, Bearings and Flexball) - Internal Side of Door for condition,disconnection and rupture. |  | 0.058333 | CBN |  | CBN, × | ×
374 | 52-12-40-003-AFTLH | 100412190 | Operational Check of Aft Passenger Door full opening from inside (without Slide release) in emergency configuration (with EOS percussion). |  | 0.22222 | CBN |  | CBN, × | emergency-evacuation slide
375 | 52-12-40-004-AFTLH | 100412194 | Operational check of slide disarming during outside opening of the Aft Passenger Door. |  | 0.11111 | CBN |  | CBN, × | emergency evacuation slide
376 | 52-12-51-001-AFTLH | 100412198 | Detailed Inspection of Aft Passenger Door Pneumatic Assembly - Internal Side of Door for condition and rupture. |  | 0.052778 | CBN |  | ×, × | ×
377 | 52-12-51-003-AFTLH | 100412201 | Functional Check of Aft Passenger Door Pneumatic Assembly Gauge. |  | 0.053472 | CBN |  | CBN, × | ×
378 | 52-12-52-001-U | 100598820 | Detailed Inspection of Aft Passenger Door Control Mechanism - Internal Side of Door for condition, disconnection and rupture. |  | 0.017361 | CBN |  | ×, × | ×
379 | 52-30-003-0001-U | 100309146 | General Visual Inspection of Forward Cargo Door Piano Hinge - External Side of Door at Piano Hinge Area. |  | 0.041667 | STR |  | ×, × | ×
380 | 52-30-003-0003-AFTLH | 100309147 | General Visual Inspection of Aft Cargo Door Piano Hinge - External Side of Door. |  | 0.041667 | STR |  | ×, × | ×
381 | 52-30-003-0304-U | 100412212 | Detailed Inspection of Fwd Cargo Door Piano Hinge area at Cargo Door and Fuselage - External Side of Door. |  | 0.038194 | STR |  | ×, × | ×
382 | 52-30-003-0306-U | 100412216 | Detailed Inspection of Aft Cargo Door Piano Hinge area at Cargo Door and Fuselage - External Side of Door. |  | 0.020139 | STR |  | ×, × | AFT cargo-compartment lining AFT cargo-door lining AFT-cargo-door surround lining
383 | 52-30-005-0001-U | 100309159 | General Visual Inspection of Fwd Cargo Door C-Latch (Door) and Latch Fittings and Pins (Fuselage Cutout Area) - External Side of Door and at Fuselage Cutout Area. |  | 0.022917 | STR |  | ×, × | ×
384 | 52-30-005-0002-U | 100513511 | Detailed Inspection of Fwd Cargo Door Latch Shafts, Latch Outer Flange, Latch-Frame Junction, Latch Lug, Latch Fitting and Attachments Bolts, With Door Lining Removed - Inside of Door. |  | 0.027778 | STR |  | ×, × | ×
385 | 52-30-005-0003-U | 100309167 | General Visual Inspection of Fwd Cargo Door Outer Skin Under Latch With Door Lining Removed - Internal Side of Door. |  | 0.024306 | STR |  | STR, × | ×
386 | 52-30-005-0005-AFTRH | 100309171 | General Visual Inspection of Aft Cargo Door C-Latch (Door) and Latch Fittings and Pins (Fuselage Cutout Area) - External Side of Door and at Fuselage Cutout Area. |  | 0.027083 | STR |  | ×, × | ×
387 | 52-30-005-0006-AFTRH | 100513724 | Detailed Inspection of Aft Cargo Door Latch Shafts, Latch Outer Flange, Latch-Frame Junction, Latch Lug, Latch Fitting and Attachments Bolts, With Door Lining Removed - Inside of Door. |  | 0.027778 | STR |  | STR, × | ×
388 | 52-30-005-0007-AFTRH | 100309179 | General Visual Inspection of Aft Cargo Door Outer Skin Under Latch With Door Lining Removed - Internal Side of Door. |  | 0.033333 | STR |  | STR, × | ×
389 | 52-30-005-0052-FWDRH | 100757825 | Detailed Inspection of Fwd Cargo Door Latch Shafts (at Door), Latch Pins and Fittings (at Fuselage) - External Side of Door and at Fuselage Cutout Area. |  | 0.025694 | STR |  | STR, × | ×
390 | 52-30-005-0062-U | 100309183 | Detailed Inspection of Aft Cargo Door Latch Shafts (at Door), Latch Pins and Fittings (at Fuselage) - External Side of Door and at Fuselage Cutout Area. |  | 0.028472 | STR |  | STR, × | ×
391 | 52-31-00-001-U | 100723491 | Detailed Inspection of Fwd Cargo Door Vent Flap Bearings Assembly (Internal Side), Latch Mechanism, Terminal Shaft and Lock Mechanism Assembly (Internal Side), Vent Flap (Internal and External Side) for condition, disconnection and rupture. | TCD/AD | 0.055556 | STR |  | ×, × | ×
392 | 52-31-20-005-U | 100723507 | Functional Check of gap between Lock Handle Fitting and Fitting Roller. | TCD/AD | 0.020833 | ACS
393 | 52-31-23-001-U | 100412231 | Detailed Inspection of Fwd Cargo Door Fittings - Internal Side of Door for condition, disconnection and rupture. |  | 0.029861 | ACS |  | ×, × | ×
394 | 52-31-24-001-FWDRH | 100412235 | Detailed Inspection of Fwd Cargo Door Bellcrank and Hook Assembly - Internal Side of the Door for conditions, disconection and rupture. |  | 0.019444 | ACS |  | ×, × | ×
395 | 52-31-27-001-FWDRH | 100412239 | Detailed Inspection of Fwd Cargo Door Actuators - Internal Side of Door for condition, disconnection and rupture. |  | 0.019444 | ACS |  | ×, × | ×
396 | 52-31-27-003-U | 100412458 | Functional Check of Fwd Cargo Door Actuators nitrogen charge. |  | 0.083333 | ACS |  | ×, × | ×
397 | 52-31-28-001-FWDRH | 100412243 | Detailed Inspection of Fwd Cargo Door Drive Rods - Internal Side of Door for condition, disconnection and rupture. |  | 0.01875 | ACS |  | ×, × | ×
398 | 52-32-00-001-U | 100723599 | Detailed Inspection of Aft Cargo Door Vent Flap Bearings Assembly (Internal Side), Latch Mechanism, Terminal Shaft and Lock Mechanism Assembly (Internal Side), Vent Flap (Internal and External Side) for condition, disconnection and rupture. | TCD/AD | 0.11111 | STR |  | ×, × | ×
399 | 52-32-20-005-U | 100723699 | Functional Check of gap between Lock Handle Fitting and Fitting Roller. | TCD/AD | 0.020833 | ACS
400 | 52-32-23-001-U | 100412251 | Detailed Inspection of Aft Cargo Door Fittings - Internal Side of Door for condition, disconnection and rupture. |  | 0.033333 | ACS |  | ×, × | ×
401 | 52-32-24-001-AFTRH | 100412255 | Detailed Inspection of Aft Cargo Door Bellcrank and Hook Assembly - Internal Side of the Door for conditions, disconection and rupture. |  | 0.033333 | ACS |  | ×, × | ×
402 | 52-32-27-001-AFTRH | 100412259 | Detailed Inspection of Aft Cargo Door Actuators - Internal Side of Door for condition, disconnection and rupture. |  | 0.030556 | ACS |  | ×, × | ×
403 | 52-32-27-003-U | 100412446 | Functional Check of Aft Cargo Door Actuators nitrogen charge. |  | 0.083333 | ACS |  | ×, × | ×
404 | 52-32-28-001-AFTRH | 100412263 | Detailed Inspection of Aft Cargo Door Drive Rods - Internal Side of Door for condition, disconnection and rupture. |  | 0.022222 | ACS |  | ×, × | ×
405 | 52-40-003-0001-U | 100514041 | General Visual Inspection of Fwd Service Door Stops at Fuselage - External Side ot Fuselage Cutout Area. |  | 0.019444 | STR |  | ×, × | ×
406 | 52-40-003-0002-AFTRH | 100513562 | General Visual Inspection of Aft Service Door Stops at Fuselage - External Side at Fuselage Cutout Area. |  | 0.028472 | STR |  | ×, × | ×
407 | 52-40-003-0127-U | 800048781 | Detailed Inspection of Fwd Service Door Stops at Door and Fuselage - External Side of Door and Fuselage. |  | 0.0125 | STR |  | ×, × | ×
408 | 52-40-003-0128-U | 800048784 | Detailed Inspection of Aft Service Door Stops at Door and Fuselage - External Side of Door and Fuselage. |  | 0.016667 | STR |  | ×, × | ×
409 | 52-41-00-001-FWDRH | 100412271 | Lubrication of Fwd Service Door. |  | 0.022917 | CBN |  | ×, × | ×
410 | 52-41-20-003-FWDRH | 800048793 | Detailed Inspection of Fwd Service Door Main Shaft and Hoisting Mechanism Assembly - Internal side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
411 | 52-41-22-001-FWDRH | 800048796 | Detailed Inspection of Fwd Service Door Box Mechanism - Internal and External Side of Door for condition, disconnection and rupture. |  | 0.016667 | CBN |  | ×, × | ×
412 | 52-41-23-002-FWDRH | 800048799 | Functional check to verify the Stop assemblies adjustment. |  | 0.041667 | CBN |  | CBN, × | ×
413 | 52-41-23-003-FWDRH | 100412282 | Detailed Inspection of Fwd Service Door Stops at Door and Fuselage Assemblies - External side of the door for condition, disconnection and rupture. |  | 0.020833 | CBN |  | ×, × | ×
414 | 52-41-25-001-FWDRH | 100686959 | Detailed Inspection of the forward Service Door Vent Flap tube and Vent Flap Assembly - Internal and external side of the door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
415 | 52-41-27-001-FWDRH | 100619255 | Operational Check of Fwd Service Door Damper for loss of damping. |  | 0.025 | CBN |  | ×, × | ×
416 | 52-41-30-003-FWDRH | 800048811 | Detailed Inspection of Fwd Service Door Hook, Arm Assembly and actuator Assembly - Internal side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
417 | 52-41-40-001-FWDRH | 100686958 | Detailed Inspection of Fwd Service Door Slide Bellcrank, Girt Bar and Slide Mechanism (Fixtures, Bearings and Flexball) - Internal Side of Door for condition, disconnection and rupture. |  | 0.083333 | CBN |  | CBN, × | ×
418 | 52-41-40-003-FWDRH | 100412289 | Operational Check of Fwd Service Door full opening from inside (without Slide release) in emergency configuration (with EOS percussion). |  | 0.20347 | CBN |  | CBN, × | emergency-evacuation slide
419 | 52-41-40-004-FWDRH | 800048820 | Operational check of slide disarming during outside opening of Fwd Service Door. |  | 0.079167 | CBN |  | CBN, × | emergency evacuation slide
420 | 52-41-51-001-U | 800048823 | Detailed Inspection of Fwd Service Door Pneumatic Assembly - Internal Side of Door for condition and rupture. |  | 0.033333 | CBN |  | ×, × | ×
421 | 52-41-51-003-FWDRH | 100412294 | Functional Check of Fwd Service Door Pneumatic Assembly Gauge. |  | 0.046528 | CBN |  | CBN, × | ×
422 | 52-41-52-001-U | 100598813 | Detailed Inspection of Fwd Service Door Control Mechanism - Internal Side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
423 | 52-42-00-001-AFTRH | 100412300 | Lubrication of Aft Service Door. |  | 0.022222 | CBN |  | ×, × | ×
424 | 52-42-20-003-AFTRH | 100412305 | Detailed Inspection of Aft Service Door Main Shaft and Hoisting Mechanism Assembly - Internal side of Door for condition, disconnection and rupture. |  | 0.020833 | CBN |  | ×, × | ×
425 | 52-42-22-001-AFTRH | 800048865 | Detailed Inspection of Aft Service Door Box Mechanism - Internal and External Side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
426 | 52-42-23-002-AFTRH | 800048868 | Functional check to verify the Aft Service Door Stop assemblies adjustment. |  | 0.05 | CBN |  | CBN, × | ×
427 | 52-42-23-003-AFTRH | 100412311 | Detailed Inspection of Aft Service Door Stops at Door and Fuselage Assemblies - External side of the door for condition, disconnection and rupture. |  | 0.020833 | CBN |  | ×, × | ×
428 | 52-42-25-001-AFTRH | 100687022 | Detailed Inspection of the Aft Service Door Vent Flap tube and Vent Flap Assembly - Internal and external side of the door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
429 | 52-42-27-001-AFTRH | 100619270 | Operational Check of Aft Service Door Damper for loss of damping. |  | 0.020833 | CBN |  | ×, × | ×
430 | 52-42-30-003-AFTRH | 800048900 | Detailed Inspection of Aft Service Door Hook , Arm Assembly and actuator Assembly - Internal side of Door for condition, disconnection and rupture. |  | 0.0125 | CBN |  | ×, × | ×
431 | 52-42-40-001-AFTRH | 800048903 | Detailed Inspection of Aft Service Door Slide Bellcrank, Girt Bar and Slide Mechanism (Fixtures, Bearings and Flexball) - Internal Side of Door for condition, disconnection and rupture. |  | 0.0625 | CBN |  | CBN, × | ×
432 | 52-42-40-003-AFTRH | 100412318 | Operational Check of Aft Service Door full opening from inside (without Slide release) in emergency configuration (with EOS percussion). |  | 0.25208 | CBN |  | CBN, × | emergency-evacuation slide
433 | 52-42-40-004-AFTRH | 100412322 | Operational check of slide disarming during outside opening of the Aft Service Door. |  | 0.10625 | CBN |  | CBN, × | emergency-evacuation slide
434 | 52-42-51-001-U | 100412326 | Detailed Inspection of Aft Service Door Pneumatic Assembly - Internal Side of Door for condition and rupture. |  | 0.032639 | CBN |  | ×, × | ×
435 | 52-42-51-003-AFTRH | 100412329 | Functional Check of Aft Service Door Pneumatic Assembly Gauge. |  | 0.051389 | CBN |  | CBN, × | ×
436 | 52-42-52-001-U | 100598814 | Detailed Inspection of Aft Service Door Control Mechanism - Internal Side of Door for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
437 | 52-43-00-001-FWD | 100412335 | General Visual Inspection of Fwd Avionics Compartment Access Hatch Actuating and Locking Mechanism (including the seals). |  | 0.044444 | ACS |  | ×, × | forward avionics-compartment access hatch
438 | 52-43-001-0441-U | 100412339 | General Visual Inspection of Fwd Avionics Compartment Access Hatch Structure, Handle Box and Vent Valve - External Side of Door. |  | 0.05 | STR |  | ×, × | forward avionics-compartment access hatch
439 | 52-43-20-002-FWD | 100412454 | Lubrication of Fwd Avionics Compartment Access Hatch Actuating and Locking Mechanism Components. |  | 0.026389 | ACS |  | ×, × | ×
440 | 52-46-00-001-M | 800048948 | General Visual Inspection of Middle Avionic Compartment Access Door Actuating and Locking Mechanism (including the seals). |  | 0.041667 | ACS |  | ×, × | middle avionics-compartment access door
441 | 52-46-20-002-U | 100412450 | Lubrication of Middle Avionics Compartment Access Door Actuating and Locking Mechanism Components. |  | 0.026389 | ACS |  | ×, × | ×
442 | 52-51-02-001-U | 100040294 | Operational Check of Reinforced Cockpit Door Control Panels and Electro-Mechanical Latch. |  | 0.10556 | ACS |  | ×, × | ×
443 | 52-51-02-002-U | 100871666 | Detailed Inspection of Reinforced Cockpit Door Assembly including Electromechanical Latch, Upper and Lower Hinges, Quick Release Pin, and header assembly for condition, disconnection and rupture. |  | 0.052083 | CBN |  | ×, ×
444 | 52-51-02-003-U | 100871644 | Functional Check of Reinforced Cockpit Door Upper and Lower Hinges for proper alignment. |  | 0.041667 | REI
445 | 52-73-00-001-AFT | 100412345 | Operational Check of Forward/Aft Cargo Door Warning Sensor (Locked). |  | 0.075694 | ACS |  | ×, × | ×
446 | 52-73-00-001-FWD | 100412349 | Operational Check of Forward/Aft Cargo Door Warning Sensor (Locked). |  | 0.083333 | ACS |  | ×, × | ×
447 | 53-05-00-001-AFT | 100412354 | Detail Inspection of Fuselage Drain Valves for obstruction or Damage. Clean as necessary. |  | 0.16667 | ACS |  | ×, × | rear-fuselage drain-tube fairing
448 | 53-05-00-001-FWD | 100412438 | Detail Inspection of Fuselage Drain Valves for obstruction or Damage. Clean as necessary. |  | 0.16667 | ACS |  | ×, × | rear-fuselage drain-tube fairing
449 | 53-10-001-0001-U | 800048974 | General Visual Inspection of Fwd Pressure Bulkhead Fwd Face - Inside of Radome. |  | 0.041667 | STR |  | ×, I | radome
450 | 53-10-002-0139-U | 100412358 | General Visual Inspection of Fwd Avionics Compartment Access Hatch Cutout Structure, from FR 4 to FR 6 and from STGR 25 LH to STGR 25 RH - External Side of Fuselage. |  | 0.0375 | STR |  | STR, × | ×
451 | 53-10-004-0001-FWDLH | 100143906 | General Visual Inspection of Windshield Cutout Structure - Inside of Fuselage. |  | 0.041667 | ACS |  | ×, × | ×
452 | 53-10-004-0001-FWDRH | 100143954 | General Visual Inspection of Windshield Cutout Structure - Inside of Fuselage. |  | 0.041667 | ACS |  | ×, × | ×
453 | 53-10-005-0001-FWDLH | 100143907 | General Visual Inspection of Direct-Vision Window Cutout Structure - Inside of Fuselage. |  | 0.041667 | ACS |  | ×, × | ×
454 | 53-10-005-0001-FWDRH | 100143941 | General Visual Inspection of Direct-Vision Window Cutout Structure - Inside of Fuselage. |  | 0.041667 | ACS |  | ×, × | ×
455 | 53-10-008-0001-U | 100509344 | General Visual Inspection of Fwd Passenger Door Cutout Structure, from Fr 15 to Fr 19A and from Str 03 LH to Str 18 LH - Inside of Fuselage. |  | 0.041667 | STR |  | ×, × | PAX cabin insulation
456 | 53-10-008-0002-U | 91048881 | Detailed Inspection of Fwd Passenger Door Cutout Structure, from Fr 15 to Fr 19A and from Str 03 LH to Str 18 LH - External Side of Fuselage. |  | 0.041667 | STR | NOTE: Scuff Plate has to be removed. | ×, × | FWD PAX door protective plate
457 | 53-10-012-0001-U | 800049074 | Detailed Inspection of Ram Air Turbine (RAT) Compartment, Supporting and Cutout Structure - Inside of RAT Compartment. |  | 0.041667 | STR |  | STR, × | ×
458 | 53-10-012-0349-U | 100412366 | General Visual Inspection of Ram Air Turbine (RAT) Compartment Cutout Structure - External Side of Fuselage. |  | 0.027778 | STR |  | STR, × | ×
459 | 53-10-014-0002-U | 100412374 | Detailed Inspection of Upper Skin Panel from STGR 7 LH to STGR 7 RH and from FR 1 to Forward Fuselage and Center Fuselage I Junction, including Longitudinal Skin Splices Attachment area, Passenger and Service Door Cutouts, Direct Vision Window and Windshield Cutouts - External Side of Fuselage. |  | 0.026389 | STR |  | ×, × | ×
460 | 53-10-014-0003-U | 100706884 | Detailed Inspection of Upper Skin Panel around of Central Post and Upper Beam Attachment Holes - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
461 | 53-10-014-0004-U | 100706883 | Detailed Inspection of Upper Skin Panel around of Central Post and Lower Beam Attachment Holes - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
462 | 53-10-014-0005-U | 100706886 | Special Detailed Inspection (Eddy Current) of Upper Skin Panel around of Central Post and Lower Beam Attachment Holes to verify the Doubler located under the Skin Panel - External Side of Fuselage. |  | 0.041667 | STR | NDI(ET/LFEC) | ×, × | ×
463 | 53-10-015-0001-FWDLH | 100412381 | General Visual Inspection of Side Skin Panels from Str 7 RH to Str 17 RH, Str 07 LH to Str 17 LH and from Fr 01 to Forward and Center Fuselage I Junction, including Stringers, Frames and Shear clips - Inside of Fuselage. |  | 0.11319 | STR |  | ×, I | sound dampeners cockpit and passenger cabin insulation If necessary, monuments(partition, closet, galley, overhead bin or lavatory)
464 | 53-10-015-0001-FWDRH | 100412441 | General Visual Inspection of Side Skin Panels from Str 7 RH to Str 17 RH, Str 07 LH to Str 17 LH and from Fr 01 to Forward and Center Fuselage I Junction, including Stringers, Frames and Shear clips - Inside of Fuselage. |  | 0.097222 | STR |  | ×, I | sound dampeners cockpit and passenger cabin insulation If necessary, monuments(partition, closet, galley, overhead bin or lavatory)
465 | 53-10-015-0002-U | 100412386 | Detailed Inspection of Side Skin Panels from Str 7 RH to Str 17 RH, Str 7 LH to Str 17 LH and from Fr 1 to Forward and Center Fuselage I Junction, including Longitudinal Skin Splices to Skin Attachment area, Service Door Cutout, Direct Vision Window and Windshield Cutouts - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
466 | 53-10-016-0002-U | 800049136 | Detailed Inspection of Lower Skin Panel from Str 17 LH to Str 17 RH and from Fr 1 to Forward Fuselage to Center Fuselage I Junction, including Fwd Avionics Compartment and Fwd Service Door Cutouts, Nose Landing Gear Wheel Well Cutout Structure, Longitudinal Skin Splices Attachment area - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
467 | 53-10-016-0423-U | 100619292 | General Visual Inspection of Lower Skin Panel, from FR 1 to FR 23 and from STGR 17 LH to STGR 17 RH, area between Fwd Pressure Bulkhead and Fwd Fuselage to Center Fuselage I Junction - External Side of Fuselage. |  | 0.034722 | STR |  | ×, × | ×
468 | 53-10-017-0001-U | 100412393 | Detailed Inspection of Fwd Fuselage Circumferential Skin Splices and Stringer Splices - Inside of Fuselage. |  | 0.10069 | STR |  | ×, I | cargo compartment insulation FWD cargo compartment FWD bulkhead cockpit insulation
469 | 53-10-017-0002-U | 800049148 | Detailed Inspection of Fwd Fuselage External Skin at Circumferential Splices and Stringer Splices Region - External Side of Fuselage. |  | 0.041667 | STR |  | STR, × | ×
470 | 53-10-020-0001-U | 100309262 | General Visual Inspection of Passenger Window Cutout Structure (Skin and Window Frame), from STR 08 RH to STR 11 RH, from FR 19 to Forward Fuselage and Center Fuselage I Junction - Inside of Fuselage. |  | 0.027778 | STR |  | ×, I | PAX cabin insulation
471 | 53-10-020-0002-U | 100309266 | General Visual Inspection of Passenger Window Cutout Structure (Skin and Window Frame), from STR 08 RH to STR 11 RH, from FR 19 to Forward Fuselage and Center Fuselage I Junction - External Side of Fuselage. |  | 0.022917 | STR |  | ×, × | ×
472 | 53-10-021-0001-U | 100412403 | General Visual Inspection of NLG Wheel Well Metallic Structure (Lateral Longeron, Bulkhead at Sta 2319 and 4520, and Upper Panel) - Inside of Fuselage. |  | 0.069444 | STR |  | ×, I | cargo compartment insulation
473 | 53-10-021-0005-U | 100087252 | General Visual Inspection of "I" Beam at Nose Landing Gear Wheel Well Metallic Structure (NLG Actuator Attachment Area - Sta 4270 - FR 14) - Inside of Fuselage. |  | 0.041667 | STR |  | ×, × | cargo compartment insulation
474 | 53-10-023-0383-U | 100394697 | Detailed Inspection of NLG Actuator Support Fitting and Backup Structure - External Side at NLG Compartment. |  | 0.010417 | STR |  | ×, × | ×
475 | 53-10-024-0378-U | 100309275 | Detailed Inspection of NLG Shock Strut and Upper Drag Brace Housing - External Side of Structure. |  | 0.059028 | STR |  | ×, I | ×
476 | 53-10-025-0390-U | 100412408 | General Visual Inspection of Nose Landing Gear Wheel Well Cutout Structure - External Side of Fuselage. |  | 0.034722 | STR |  | STR, × | ×
477 | 53-10-026-0391-U | 100394853 | General Visual Inspection of Cockpit Floor Structure and Cockpit Floor-to-Frame Attachments from Fr 5 to Fr 12 - Internal Side of Cockpit. |  | 0.024306 | STR |  | ×, I | ×
478 | 53-10-027-0392-U | 100706891 | General Visual Inspection of Passenger Floor Structure and Passenger Floor to Frame Attachment, from FR 12 to FR 20 (for E170) or from FR 12 to FR 22 (for E175) - Internal Side of Passenger Cabin at Wet areas. |  | 0.22778 | STR |  | ×, × | RH forward galleys FWD LH lavatory
479 | 53-10-21-001-FWDLH | 100412417 | Detailed Inspection of Fwd Passenger Door Keeper Assembly for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | forward-passenger-door surround lining
480 | 53-10-21-002-FWDLH | 100412421 | Detailed inspection of the forward passenger door command ramps. |  | 0.011111 | CBN |  | ×, × | forward-passenger-door surround lining
481 | 53-10-25-001-FWDRH | 800049291 | Detailed Inspection of Fwd Service Door Keeper Assembly for condition, disconnection and rupture. |  | 0.016667 | CBN |  | ×, × | forward-service-door surround lining
482 | 53-10-25-002-FWDRH | 100412430 | Detailed Inspection of the Fwd Service Door command ramps for condition and rupture. |  | 0.018056 | CBN |  | ×, × | ×
483 | 53-21-001-0001-U | 100309286 | Detailed Inspection of Upper Skin Panel from Str 7 LH to Str 7 RH and from Forward Fuselage and Center Fuselage I Junction to Center Fuselage I and Center Fuselage II Junction, Including Circumferential Skin Splice Attachment Area - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
484 | 53-21-002-0001-LH | 100309289 | Detailed Inspection of Side Skin Panels from Str 7 LH to Str 17 LH, from Str 7 RH to Str 17 RH, and from Forward Fuselage and Center Fuselage I Junction to Center Fuselage I and Center Fuselage II Junction, Including Circumferential Skin Splice Attachment Area - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
485 | 53-21-002-0001-RH | 100309342 | Detailed Inspection of Side Skin Panels from Str 7 LH to Str 17 LH, from Str 7 RH to Str 17 RH, and from Forward Fuselage and Center Fuselage I Junction to Center Fuselage I and Center Fuselage II Junction, Including Circumferential Skin Splice Attachment Area - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
486 | 53-21-003-0001-U | 800049317 | Detailed Inspection of Lower Skin Panel from Str 17 LH to Str 17 RH and from Forward Fuselage and Center Fuselage I Junction to Center Fuselage I and Center Fuselage II Junction, Including Circumferential Skin Splice Attachment Area, Fwd Cargo Door Cutout Structure and Latch Backup Fittings - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | forward wing-to-fuselage fairing
487 | 53-21-003-0320-U | 100619311 | General Visual Inspection of Lower Skin Panel, area not covered by Wing to Fuselage Fairing between Fwd Fuselage junction and Center Fuselage II junction, from FR 23 to FR 34 and from STGR 17 LH to STGR 17 RH - External Side of Fuselage. |  | 0.034722 | STR |  | ×, × | ×
488 | 53-21-009-0002-U | 800049383 | Detailed Inspection of Fwd Cargo Door Cutout Structure and Latch Backup Fittings, from Str 17 RH to Str 26 RH and from Fr 24 to Fr 27 - Inside of Fuselage. |  | 0.041667 | STR |  | ×, I | cargo compartment insulation
489 | 53-21-009-0093-U | 100656616 | General Visual Inspection of Fwd Cargo Door Cutout Structure and Latch Backup Fittings, from FR 24 to FR 27 and from STGR 17 RH to STGR 25 RH - Internal Side of Fuselage. |  | 0.069444 | STR |  | ×, × | cargo compartment insulation
490 | 53-21-009-0322-U | 100412474 | General Visual Inspection of Fwd Cargo Door Cutout Structure, from FR 24 to FR 27 and from STGR 17 RH to STGR 26 RH, except area covered by Scuff Plate - External Side of Fuselage. |  | 0.052778 | STR |  | ×, I | ×
491 | 53-21-29-001-FWDRH | 800049418 | Detailed Inspection of Fwd Cargo Door Uplock - for condition, disconnection and rupture. |  | 0.0125 | ACS |  | ×, × | ×
492 | 53-21-29-002-FWDRH | 100412479 | Detailed Inspection of the Fwd Cargo Door latch fittings. |  | 0.029861 | ACS |  | ×, × | ×
493 | 53-21-29-003-FWDRH | 800049424 | Functional check to verify Latch fittings adjustment. |  | 0.16736 | ACS |  | ACS, × | ×
494 | 53-21-29-004-U | 100412746 | Lubrication of Fwd Cargo Door Rotational Latch Fitting. |  | 0.031944 | ACS |  | ×, × | ×
495 | 53-22-001-0001-U | 800049426 | Detailed Inspection of Upper Skin Panel from Str 7 LH to Str 7 RH and from Center Fuselage I and Center Fuselage II Junction to Center Fuselage II and Center Fuselage III Junction, Including Longitudinal Splices to Skin Attachment Area - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
496 | 53-22-005-0001-LH | 100309366 | Detailed Inspection of Passenger Window Cutout Structure (Skin and Window Frame), from Str 08 LH to Str 11 LH, from Str 08 RH to Str 11 RH and from Center Fuselage I and Center Fuselage II Junction to Center Fuselage II and Center Fuselage III Junction - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
497 | 53-22-005-0001-RH | 100309636 | Detailed Inspection of Passenger Window Cutout Structure (Skin and Window Frame), from Str 08 LH to Str 11 LH, from Str 08 RH to Str 11 RH and from Center Fuselage I and Center Fuselage II Junction to Center Fuselage II and Center Fuselage III Junction - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
498 | 53-22-007-0001-U | 800049462 | Detailed Inspection of Fwd Pressure Bulkhead, Aft Face, at Fr 45 - Inside of Wing to Fuselage Fairing. |  | 0.041667 | STR | NOTE: Wing to Fuselage Fairing has to be removed. | ×, × | FWD wing-to-fuselage fairing
499 | 53-22-007-0002-U | 800049465 | Detailed Inspection of Fwd Pressure Bulkhead, Fwd Face, at Fr 45 - Inside of Fuselage. |  | 0.041667 | STR |  | ×, I | FWD wing-to-fuselage fairing
500 | 53-22-009-0001-U | 800049492 | Detailed Inspection of Keel Beam - Inside of MLG Compartment. |  | 0.070139 | STR | NOTE: Wing to Fuselage Fairing has to be removed. | ×, I | aft wing-to-fuselage fairing center wing-to-fuselage fairing forward wing-to-fuselage fairing
501 | 53-22-009-0157-U | 100309385 | Detailed Inspection of Keel Beam - External Side at MLG Compartment. |  | 0.041667 | STR |  | ×, I | ×
502 | 53-23-001-0001-U | 100309416 | Detailed Inspection of Upper Skin Panel from Stringer 7 RH to Str 7 LH and from Center Fuselage II and Center Fuselage III Junction to Center Fuselage III and Rear Fuselage Junction, Including Longitudinal Skin Splices to Skin Attachment Area - External Side of Fuselage. |  | 0.083333 | STR |  | ×, × | dorsal fin
503 | 53-23-002-0001-LH | 100309421 | Detailed Inspection of Side Skin Panels from Str 7 LH to Str 17 LH, from Str 7 RH to Str 17 RH and from Center Fuselage II and Center Fuselage III Junction to Center Fuselage III and Rear Fuselage Junction, Including Longitudinal Skin Splices to Skin Attachment Area - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
504 | 53-23-002-0001-RH | 100309646 | Detailed Inspection of Side Skin Panels from Str 7 LH to Str 17 LH, from Str 7 RH to Str 17 RH and from Center Fuselage II and Center Fuselage III Junction to Center Fuselage III and Rear Fuselage Junction, Including Longitudinal Skin Splices to Skin Attachment Area - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
505 | 53-23-003-0001-U | 100309422 | Detailed Inspection of Lower Skin Panel from Str 17 LH to Str 17 RH and from Center Fuselage II and Center Fuselage III Junction to Center Fuselage III and Rear Fuselage Junction, including Longitudinal Skin Splices to Skin Attachment area - External Side of Fuselage. |  | 0.041667 | STR | NOTE: Wing to Fuselage Fairing has to be removed. | ×, × | aft wing-to-fuselage fairing on the CF III
506 | 53-23-003-0321-U | 100315350 | General Visual Inspection of Lower Skin Panels from Str 17 LH to Str 17 RH and from Center Fuselage II to Center Fuselage III Junction to Center Fuselage III to Rear Fuselage Junction - External Side of Fuselage. |  | 0.0375 | STR | NOTE: Wing to Fuselage Fairing has to be removed. | ×, × | ×
507 | 53-23-005-0100-U | 100706878 | General Visual Inspection of Passenger Floor Structure and Passenger Floor to Frame Attachment, from FR 84 to FR 91 - Internal Side of Passenger Cabin at Wet areas. |  | 0.23056 | STR |  | ×, × | aft cargo-compartment aft bulkhead cargo nets If necessary, passenger cabin insulation If necessary, monuments(partition, closet, galley or lavatory)
508 | 53-23-006-0001-LH | 100309443 | Detailed Inspection of Passenger Window Cutout Structure (Skin and Window Frame), from Str 8 LH to Str 11 LH, from Str 8 RH to Str 11 RH and from Center Fuselage II and Center Fuselage III Junction to Center Fuselage III and Rear Fuselage Junction - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
509 | 53-23-006-0001-RH | 100309626 | Detailed Inspection of Passenger Window Cutout Structure (Skin and Window Frame), from Str 8 LH to Str 11 LH, from Str 8 RH to Str 11 RH and from Center Fuselage II and Center Fuselage III Junction to Center Fuselage III and Rear Fuselage Junction - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
510 | 53-23-008-0001-U | 800049603 | Detailed Inspection of External Skin in Circumferential Splices and Stringer Splices Region at Center Fuselage II and Center Fuselage III Junction - External Side of Fuselage. |  | 0.041667 | STR | NOTE: Wing to Fuselage Fairing has to be removed. | STR, × | aft wing-to-fuselage fairing
511 | 53-23-008-0002-U | 100309450 | Detailed Inspection of Circumferential Skin Splices and Stringer Splices at Center Fuselage II and Center Fuselage III Junction - Inside of Fuselage. |  | 0.067361 | STR |  | ×, I | overhead bins PSU supporting structure PAX cabin insulation sound dampeners aft cargo-compartment insulation
512 | 53-23-009-0001-U | 100309461 | Detailed Inspection of Aft Cargo Door Cutout Structure and Latch Backup Fittings, from Str 16 RH to Str 28 RH and from Fr 77 to Fr 80 - External Side of Fuselage with Scuff Plate Removed. |  | 0.59236 | STR |  | ×, I | scuff plate
513 | 53-23-009-0002-U | 100513988 | Detailed Inspection of Aft Cargo Door Cutout Structure and Latch Backup Fittings, from Str 16 RH to Str 28 RH and from Fr 77 to Fr 80 - Inside of Fuselage. |  | 0.041667 | STR |  | ×, I | cargo nets
514 | 53-23-009-0094-U | 100656606 | General Visual Inspection of Aft Cargo Door Cutout Structure and Latch Backup Fittings, from FR 77 to FR 80 and from STGR 17 RH to STGR 26 RH - Internal Side of Fuselage. |  | 0.041667 | STR
515 | 53-23-009-0323-U | 100412495 | General Visual Inspection of Aft Cargo Door Cutout Structure, from FR 77 to FR 80 and from STGR 17 RH to STGR 26 RH, except area covered by Scuff Plate - External Side of Fuselage. |  | 0.052778 | STR |  | ×, I | AFT cargo-door protective-plate
516 | 53-23-014-0001-U | 100309469 | Detailed Inspection of Aft Passenger Door Cutout Structure, from Fr 84 to Fr 88, except area covered by Scuff Plate - External Side of Fuselage. |  | 0.62083 | STR |  | ×, I | scuff plate
517 | 53-23-014-0002-U | 100515774 | Detailed Inspection of Aft Passenger Door Cutout Structure, from Fr 84 to Fr 88 and from Str 04 LH to Str 18 LH - Inside of Fuselage. |  | 0.041667 | STR |  | ×, I | PAX cabin insulation If necessary, monuments(partition, closet, galley, overhead bins or lavatory)
518 | 53-23-014-0005-U | 100517825 | Detailed Inspection of Aft Passenger Door Cutout Structure, at the area covered by Scuff Plate. |  | 0.0090278 | STR | NOTE: Scuff Plate has to be removed.
519 | 53-23-014-0760-U | 100412501 | General Visual Inspection of Aft Passenger Door Cutout Structure, from Fr 84 to Fr 88, Except Area Covered by Scuff Plate - External Side of Fuselage. |  | 0.069444 | STR |  | ×, I | ×
520 | 53-23-016-0001-U | 100309478 | Detailed Inspection of Aft Service Door Cutout Structure, from Fr 84 to Fr 88, except area covered by Scuff Plate - External Side of Fuselage. |  | 0.56875 | STR |  | ×, I | scuff plate
521 | 53-23-016-0002-U | 100515825 | Detailed Inspection of Aft Service Door Cutout Structure, from Fr 84 to Fr 88 and from Str 06 RH to Str 18 RH - Inside of Fuselage. |  | 0.041667 | STR |  | ×, I | If necessary, monuments(partition, closet, galley, overhead bin or lavatory) insulation blankets seal rest in the lower corners of the surrounding
522 | 53-23-016-0005-U | 100598208 | Detailed Inspection of Aft Service Door Cutout Structure, at the area covered by Scuff Plate. |  | 0.0090278 | STR | NOTE: Scuff Plate has to be removed. | ×, I
523 | 53-23-016-0764-U | 100087286 | General Visual Inspection of Aft Service Door Cutout Structure, area above Floor Level, from FR 84 to FR 88 and STGR 4 RH to STGR 17A RH - Internal Side of Fuselage. |  | 0.16875 | STR |  | ×, I | If necessary, monuments(partition, closet, galley, overhead bin or lavatory)
524 | 53-23-018-0162-U | 100656607 | General Visual Inspection of Waste and Water Access Door Cutout Structure - Internal Side of Fuselage. |  | 0.041667 | STR |  | STR, ×
525 | 53-23-21-001-AFTLH | 100412508 | Detailed Inspection of Aft Passenger Door Keeper Assembly for condition, disconnection and rupture. |  | 0.014583 | CBN |  | ×, × | ×
526 | 53-23-21-002-AFTLH | 800049700 | Detailed Inspection of the Aft Passenger Door command ramps for condition and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
527 | 53-23-25-001-AFTRH | 800049706 | Detailed Inspection of Aft Service Door Keeper Assembly for condition, disconnection and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
528 | 53-23-25-002-AFTRH | 800049709 | Detailed Inspection of the Aft Service Door command ramps for condition and rupture. |  | 0.0083333 | CBN |  | ×, × | ×
529 | 53-23-29-001-AFTRH | 100412520 | Detailed Inspection of Aft Cargo Door Uplock - for condition, disconnection and rupture. |  | 0.033333 | ACS |  | ×, × | ×
530 | 53-23-29-002-AFTRH | 100412524 | Detailed Inspection of the Aft Cargo Door latch fittings. |  | 0.039583 | ACS |  | ×, × | ×
531 | 53-23-29-003-AFTRH | 800049721 | Functional Check to verify Latch Fittings adjustment. |  | 0.18333 | ACS |  | ACS, × | inspection windows
532 | 53-23-29-004-AFTRH | 100412742 | Lubrication of Aft Cargo Door Rotational Latch Fitting. |  | 0.031944 | ACS |  | ×, × | ×
533 | 53-30-001-0001-U | 100515599 | Detailed Inspection of Rear Fuselage Upper Skin, Side Skin and Lower Skin Panels, including Circumferential Splices at Center Fuselage III to Rear Fuselage Junction Region and Longitudinal Splices from Center Fuselage III and Rear Fuselage Junction to Rear Fuselage and Tail Cone Junction - External Side of Rear Fuselage, including Area Covered by Fairings. |  | 0.09375 | STR |  | ×, × | dorsal fin elevator root fairing horizontal stabilizer sliding fairing horizontal stabilizer sliding plate
534 | 53-30-004-0147-U | 100181738 | Detailed Inspection of Circumferential Skin Splices and Stringer Splices, located between Center Fuselage III and Rear Fuselage junction, below Floor Level, from FR 90 to Aft Pressure Bulkhead, and from STGR 17A LH to STGR 17A RH - Internal Side of Fuselage. |  | 0.0375 | STR |  | ×, I | passenger-cabin insulation lining
535 | 53-30-005-0397-U | 100412529 | General Visual Inspection of Rear Fuselage Lower Skin Panel from FR 91 to FR 100 and from STGR 21 LH to STGR 21 RH - External Side of Fuselage. |  | 0.040278 | STR |  | ×, × | ×
536 | 53-30-008-0001-U | 800049765 | Detailed Inspection of Access Door Cutout Structure, from Fr 94 to Fr 96 and from Str 13 RH to Str 27 RH - External Side of Rear Fuselage. |  | 0.041667 | STR |  | STR, × | ×
537 | 53-30-008-0825-U | 100412532 | General Visual Inspection of Access Door Cutout Structure, from FR 94 to FR 96 and from STGR 14A RH to STGR 25 RH - External Side of Fuselage. |  | 0.0125 | STR |  | STR, × | ×
538 | 53-30-011-0001-U | 800049783 | Detailed Inspection of Rear Pressure Bulkhead Aft Face - Internal Side of Rear Fuselage. |  | 0.041667 | STR |  | ×, I | ×
539 | 53-30-014-0148-U | 100412536 | Detailed Inspection of Rear Fuselage Frames Lower Portion, from FR 92 to FR 96, FR 98 and FR 99 and Semi-Frame forward of Rear Pressure Bulkhead, from STGR 19 LH to STGR 19 RH - Internal Side of Fuselage. |  | 0.033333 | STR |  | STR, × | passenger-cabin insulation lining
540 | 53-30-017-0001-U | 100619363 | Detailed Inspection of Tail Cone Attachment Fittings, Backup Fittings and Intercostals and APU Struts Attachment Fittings, Backup Fittings and Intercostals at Frame 100 (Fwd and Aft Face) - Internal Side of Rear Fuselage. |  | 0.125 | STR |  | STR, × | APU strut seals on the firewall
541 | 53-30-027-0001-U | 800049937 | Detailed Inspection of Rod Attachment Fittings and Rod Assemblies from Fr 99 to Fr 100, Including Pins and Nuts - Internal side of Rear Fuselage. |  | 0.072917 | STR |  | STR, × | horizontal stabilizer lower sliding plate
542 | 55-10-002-0001-LH | 100509371 | Detailed Inspection of Upper Skin Upper Surface and Lower Skin Lower Surface (except Upper and Lower Splice Plates), from Rib 3 LH to Rib 3 RH - Internal Side of Rear Fuselage and External Side of Horizontal Stabilizer. |  | 0.041667 | STR |  | ×, I | ×
543 | 55-10-002-0001-RH | 100509426 | Detailed Inspection of Upper Skin Upper Surface and Lower Skin Lower Surface (except Upper and Lower Splice Plates), from Rib 3 LH to Rib 3 RH - Internal Side of Rear Fuselage and External Side of Horizontal Stabilizer. |  | 0.041667 | STR |  | ×, I | ×
544 | 55-10-002-0002-U | 100509341 | Detailed Inspection of Upper Skin Upper Surface and Lower Skin Lower Surface (except Upper and Lower Splice Plates), from Rib 3 LH to Rib 3 RH, at Spine Joint Region - Internal Side of Rear Fuselage and Horizontal Stabilizer Box. |  | 0.041667 | STR |  | ×, I | ×
545 | 55-10-005-0001-U | 100515446 | Detailed Inspection of Horizontal Stabilizer Upper Splice Plate Joint Upper Surface, Lower Splice Plate Joint Lower Surface, Fwd And Aft Splices Plates - Internal Side of Rear Fuselage. |  | 0.041667 | STR |  | ×, I | ×
546 | 55-10-023-0212-U | 100181698 | Detailed Inspection of Elevator Actuator Support Fittings, on Horizontal Stabilizer Rear Spar Aft Side, LH/RH - Internal Side at Trailing Edge. |  | 0.78611 | STR |  | ACS, I | elevator actuator
547 | 55-20-002-0189-U | 100412543 | Detailed Inspection of Elevator Hinges and Actuators Fittings, LH/RH - Internal Side at Horizontal Stabilizer Rear Spar and Elevator area. |  | 1899-12-31 21:53 | STR | NOTE: Elevators have to be removed. | GEN外/ACS, I | elevators
548 | 55-30-006-0143-U | 100301815 | Detailed Inspection of Front Spar Fwd Face - Internal Side of Vertical Stabilizer Leading Edge. |  | 0.125 | STR |  | ×, I | ×
549 | 56-10-004-0854-U | 100412547 | Detailed Inspection of the Direct Vision Window Frame and Fasteners - Internal Side of Fuselage. |  | 0.0625 | STR |  | STR, × | direct-vision window linings
550 | 56-12-00-001-FWDLH | 100412551 | Detailed Inspection of Cockpit Direct-Vision Window Actuation and Locking Mechanism for integrity, surface corrosion, cracks, or missing items. |  | 0.022222 | ACS |  | ×, × | direct-vision window linings
551 | 56-12-00-001-FWDRH | 100412555 | Detailed Inspection of Cockpit Direct-Vision Window Actuation and Locking Mechanism for integrity, surface corrosion, cracks, or missing items. |  | 0.022222 | ACS |  | ×, × | direct-vision window linings
552 | 56-12-00-002-LH | 100412559 | Lubrication of Cockpit Direct-Vision Window Actuation and Locking Mechanism. |  | 0.0625 | ACS |  | ×, × | direct-vision window linings
553 | 56-12-00-002-RH | 100412563 | Lubrication of Cockpit Direct-Vision Window Actuation and Locking Mechanism. |  | 0.045833 | ACS |  | ×, × | direct-vision window linings
554 | 56-30-00-001-FWDLH | 100412568 | Detailed inspection of the FWD passenger door window. |  | 0.011111 | CBN |  | ×, × | ×
555 | 56-30-00-002-AFTLH | 100412572 | Detailed inspection of the Aft passenger door window. |  | 0.014583 | CBN |  | ×, × | ×
556 | 56-30-00-003-FWDRH | 800050353 | Detailed inspection of the FWD service door window. |  | 0.0083333 | CBN |  | ×, × | ×
557 | 56-30-00-004-AFTRH | 800050356 | Detailed visual inspection of the aft service door window. |  | 0.0083333 | CBN |  | ×, × | ×
558 | 57-01-002-0003-U | 100412579 | Detailed Inspection of Wing Main Box Lower Skin Panel at Fuel Pump Satellite Holes Region - Internal Side of Wing to Fuselage Fairing. |  | 0.025 | STR |  | ×, I | ×
559 | 57-01-003-0001-U | 100514802 | Detailed Inspection of Wing Stub Rear Box Upper Skin Panel Upper Surface and Structures - Inside Fuselage. |  | 0.041667 | STR |  | STR/CBN, × | passenger-cabin floor finishing passenger seats
560 | 57-01-003-0319-U | 100412583 | General Visual Inspection of External Side of Wing Stub Rear Box Upper Skin Panel, Lower Surface, Including Area Covered by Tire Burst Shield, LH/RH - External Side at MLG Compartment. |  | 0.10417 | STR | NOTE: Tire Burst Shield has to be removed. | STR, × | ×
561 | 57-01-008-0757-U | 100412588 | General Visual Inspection of Wing Stub Spar 3, Area Exposed to MLG Compartment - External Side at MLG Compartment. |  | 0.020833 | STR |  | STR, × | ×
562 | 57-01-008-0762-U | 100230438 | Detailed Inspection of Wing Stub Spar 3 aft side including the side fittings, from Wing Stub Rear Box Rib 2 LH to Rib 2 RH - Internal Side of Fuselage. |  | 0.041667 | STR |  | STR, × | ×
563 | 57-01-010-0002-LH | 100412592 | Detailed Inspection of Wing Stub Spar 02 to Wing Stub Lower Skin Attachments and the Wing Stub Spar 02 and Wing Spar Upper and Lower Fittings, LH/RH - External Side at Wing Stub Rear Box and MLG Compartment. |  | 0.041667 | STR |  | ×, I | ×
564 | 57-01-010-0002-RH | 100412733 | Detailed Inspection of Wing Stub Spar 02 to Wing Stub Lower Skin Attachments and the Wing Stub Spar 02 and Wing Spar Upper and Lower Fittings, LH/RH - External Side at Wing Stub Rear Box and MLG Compartment. |  | 0.027778 | STR |  | ×, I | ×
565 | 57-10-001-0001-LH | 100514090 | Detailed Inspection of Wing Main Box Lower Skin (Lower Surface) along Spar 01 Attachments, from Rib 01 to Tip Rib, LH/RH - External Side Wing Main Box. |  | 0.01875 | STR |  | STR, × | ×
566 | 57-10-001-0001-RH | 100512818 | Detailed Inspection of Wing Main Box Lower Skin (Lower Surface) along Spar 01 Attachments, from Rib 01 to Tip Rib, LH/RH - External Side Wing Main Box. |  | 0.017361 | STR |  | STR, × | ×
567 | 57-10-001-0002-U | 100515502 | Detailed Inspection of Wing Main Box Lower Skin (Lower Surface) along Spar 01 Attachments, between Ribs 08 And 09, LH/RH - Area covered by Pylon Fairing. |  | 0.041667 | STR |  | ×, I | ×
568 | 57-10-002-0002-LH | 100686964 | General Visual Inspections of Wing Spar 1 from Rib 5 to Rib 8 - internal side of Dry Bay Area. |  | 0.011806 | STR |  | ×, I
569 | 57-10-002-0002-RH | 100686965 | General Visual Inspections of Wing Spar 1 from Rib 5 to Rib 8 - internal side of Dry Bay Area. |  | 0.011806 | STR |  | ×, I
570 | 57-10-004-0001-LH | 100514157 | Detailed Inspection of Wing Spar 02 Along of Main Box Lower Skin Attachments (Lower Surface), from Rib 01 to Tip Rib, LH/RH - External Side Wing Main Box. |  | 0.018056 | STR |  | STR, × | ×
571 | 57-10-004-0001-RH | 100512766 | Detailed Inspection of Wing Spar 02 Along of Main Box Lower Skin Attachments (Lower Surface), from Rib 01 to Tip Rib, LH/RH - External Side Wing Main Box. |  | 0.01875 | STR |  | STR, × | ×
572 | 57-10-007-0001-LH | 100515720 | Detailed Inspection of Wing Lower Skin Panel, Lower Surface, including area covered by Pylon Fairing and area around the Splice Attachments, LH/RH - External Side of Wing Main Box. |  | 0.12778 | STR | NOTE: Pylon Fairings have to be removed. | ×, × | pylon aft fairing
573 | 57-10-007-0001-RH | 100514368 | Detailed Inspection of Wing Lower Skin Panel, Lower Surface, including area covered by Pylon Fairing and area around the Splice Attachments, LH/RH - External Side of Wing Main Box. |  | 0.12778 | STR | NOTE: Pylon Fairings have to be removed. | ×, × | pylon aft fairing
574 | 57-10-012-0001-LH | 100509422 | Detailed Inspection of Wing Main Box Ribs (Rib 01 to Rib 26), Except Intercostals and Region Between Rib 05 and Rib 08 (Dry Bay Area), LH/RH - Inside of Wing Main Box. |  | 0.090972 | STR |  | ×, I | ×
575 | 57-10-012-0001-RH | 100509431 | Detailed Inspection of Wing Main Box Ribs (Rib 01 to Rib 26), Except Intercostals and Region Between Rib 05 and Rib 08 (Dry Bay Area), LH/RH - Inside of Wing Main Box. |  | 0.090972 | STR |  | ×, I | ×
576 | 57-40-001-0001-LH | 100509423 | General Visual Inspection of all Slat Track Attachment, including Track Rib Lugs, Track Lugs, Bolts, Links and Link Plates, LH/RH - External Side. |  | 0.024306 | STR | NOTE: Slats have to be fully extended. | ×, × | ×
577 | 57-40-001-0001-RH | 100509365 | General Visual Inspection of all Slat Track Attachment, including Track Rib Lugs, Track Lugs, Bolts, Links and Link Plates, LH/RH - External Side. |  | 0.041667 | STR | NOTE: Slats have to be fully extended. | ×, × | ×
578 | 57-40-005-0292-U | 100692833 | Detailed Inspection of all Slat Tracks Roller Paths Areas, LH/RH - External Side. |  | 0.041667 | STR | NOTE: Slats have to be fully extended. | ×, × | ×
579 | 57-40-011-0298-U | 100686981 | General Visual Inspection of Wing Fixed Leading Edge Skin, LH/RH - External Side of Wing Fixed Leading Edge. |  | 0.041667 | STR | NOTE: Slats have to be fully extended. | ×, × | ×
580 | 57-40-08-001-LH | 100309889 | General Visual Inspection of Slat Aerodynamic and Weather Seals. |  | 0.055556 | ACS | Note: Inspect the aerodynamic and weather seals as visible with slats retracted. | ×, × | ×
581 | 57-40-08-001-RH | 100309778 | General Visual Inspection of Slat Aerodynamic and Weather Seals. |  | 0.0375 | ACS | Note: Inspect the aerodynamic and weather seals as visible with slats retracted. | ×, × | ×
582 | 57-50-001-0001-LH | 100514426 | Detailed Inspection of Wing Fixed Trailing Edge Upper Skin Panel Upper Surface, from Spar 2 to Spar 3 and from Rib 1A to Rib 10, LH/RH - External Side of Fixed Trailing Edge Box. |  | 0.021528 | STR |  | ×, × | ×
583 | 57-50-001-0001-RH | 100514535 | Detailed Inspection of Wing Fixed Trailing Edge Upper Skin Panel Upper Surface, from Spar 2 to Spar 3 and from Rib 1A to Rib 10, LH/RH - External Side of Fixed Trailing Edge Box. |  | 0.018056 | STR |  | ×, × | ×
584 | 57-50-002-0001-LH | 100309787 | Detailed Inspection of Wing Fixed Trailing Edge Lower Skin Panel, Lower Surface, from Spar 02 to Spar 03 and from Rib 1A to Rib 10, including area covered by Pylon and Flap Fairing, LH/RH - External Side of Fixed Trailing Edge Box. |  | 0.023611 | STR |  | ×, × | inboard flap track fairing
585 | 57-50-002-0001-RH | 100309967 | Detailed Inspection of Wing Fixed Trailing Edge Lower Skin Panel, Lower Surface, from Spar 02 to Spar 03 and from Rib 1A to Rib 10, including area covered by Pylon and Flap Fairing, LH/RH - External Side of Fixed Trailing Edge Box. |  | 0.01875 | STR |  | ×, × | inboard flap track fairing
586 | 57-50-002-0002-U | 100309792 | Detailed Inspection of Wing Fixed Trailing Edge Lower Skin Panel at Splice between Rib 4A and Rib 06 Region - External Side of Wing Fixed Trailing Edge Lower Skin Panel. |  | 0.021528 | STR |  | ×, × | inboard flap track fairing
587 | 57-50-005-0001-LH | 100309796 | Detailed Inspection of Fixed Trailing Edge Ribs (Rib 1A to Rib 10), Including Its Attachments to Upper and Lower Fixed Leading Edge Skins, LH/RH - Inside of Fixed Trailing Edge Box and at MLG Compartment. |  | 0.027083 | STR |  | STR, × | inboard flap track fairing
588 | 57-50-005-0001-RH | 100309908 | Detailed Inspection of Fixed Trailing Edge Ribs (Rib 1A to Rib 10), Including Its Attachments to Upper and Lower Fixed Leading Edge Skins, LH/RH - Inside of Fixed Trailing Edge Box and at MLG Compartment. |  | 0.027083 | STR |  | STR, × | inboard flap track fairing
589 | 57-50-021-0001-LH | 100309807 | Detailed Inspection of Flap Track Support 01 Aft Attachment to Fuselage, Link, Pins (Special Attention to the Hollow Outer Pin) and Fitting at Fuselage, LH/RH with Flap Root Fairing removed - Inside of Wing to Fuselage and Flap Root Fairings. |  | 0.041667 | STR |  | ×, × | inboard-flap root-fairing
590 | 57-50-021-0001-RH | 100309899 | Detailed Inspection of Flap Track Support 01 Aft Attachment to Fuselage, Link, Pins (Special Attention to the Hollow Outer Pin) and Fitting at Fuselage, LH/RH with Flap Root Fairing removed - Inside of Wing to Fuselage and Flap Root Fairings. |  | 0.041667 | STR |  | ×, × | inboard-flap root-fairing
591 | 57-50-022-0001-LH | 100512494 | Detailed Inspection of Flap Track Supports 02, 03 and 04 Forward and Aft Attachments to Wing, including the Lower Flange of Forward Fitting and Outboard Side Track Supports, LH/RH, with Flap Fairings removed - Inside of Flap Fairings and at Trailing Edge area. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | STR, × | inboard and outboard flap-track fairings
592 | 57-50-022-0001-RH | 100513196 | Detailed Inspection of Flap Track Supports 02, 03 and 04 Forward and Aft Attachments to Wing, including the Lower Flange of Forward Fitting and Outboard Side Track Supports, LH/RH, with Flap Fairings removed - Inside of Flap Fairings and at Trailing Edge area. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | STR, × | inboard and outboard flap-track fairings
593 | 57-50-023-0795-U | 100412616 | General Visual Inspection of Flap Mechanism Track Supports 03 and 04 Aft Attachment to Wing, LH/RH - External Side of Wing Trailing Edge. |  | 0.048611 | STR | NOTE: Flaps have to be fully extended. | ×, I | ×
594 | 57-50-024-0001-LH | 100516528 | Detailed Inspection of Inboard Flap Track Support 2 and Outboard Flap Track Support 3 and 4, LH/RH - Internal side of Flap Fairings. |  | 0.063194 | STR | NOTE: Flaps have to be fully extended. | ×, I | flap track fairings
595 | 57-50-024-0001-RH | 100516634 | Detailed Inspection of Inboard Flap Track Support 2 and Outboard Flap Track Support 3 and 4, LH/RH - Internal side of Flap Fairings. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | ×, I | flap track fairings
596 | 57-50-025-0001-LH | 100513775 | Detailed Inspection of Inboard and Outboard Main and Aft Flap Tracks Roller path, with Flap track Fairing 1 removed, LH/RH - Inside of Flap Fairings. |  | 0.070139 | STR | NOTE: Flaps have to be fully extended. | STR, × | inboard and outboard flap-track fairings
597 | 57-50-025-0001-RH | 100513143 | Detailed Inspection of Inboard and Outboard Main and Aft Flap Tracks Roller path, with Flap track Fairing 1 removed, LH/RH - Inside of Flap Fairings. |  | 0.075 | STR | NOTE: Flaps have to be fully extended. | STR, × | inboard and outboard flap-track fairings
598 | 57-50-025-0335-U | 800050997 | Detailed Inspection of Main and Aft Flap Rails, at Flap Track Supports 2, 3 and 4, LH/RH. |  | 0.033333 | STR |  | STR, × | outboard flap track-fairing inboard flap track-fairing
599 | 57-50-025-0802-U | 100412622 | Detailed Inspection of Main and Aft Flap Rails 1, LH/RH - Internal Side of Flap Root Fairing and at Lateral Side of Aft Flap. |  | 0.042361 | STR |  | STR, × | flap track fairing No. 1
600 | 57-50-026-0001-U | 100514854 | Detailed Inspection of Inboard and Outboard Flap Main Carriage 1, 2, 3 and 4, LH/RH - Inside of Flap Fairings. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | ×, I | ×
601 | 57-50-027-0001-LH | 100516692 | Detail Inspection of Aft Flap Carriages 2, 3 and 4, LH/RH - Inside of Flap Fairings. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | ×, I | ×
602 | 57-50-027-0001-RH | 100516584 | Detail Inspection of Aft Flap Carriages 2, 3 and 4, LH/RH - Inside of Flap Fairings. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | ×, I | ×
603 | 57-50-029-0809-U | 100412632 | Detailed Inspection of Aft Flap Roller Fitting at Flap Track Support 01, LH/RH - External Side of Aft Flap Surface. |  | 0.046528 | STR | NOTE: Flaps have to be fully extended. | ×, × | ×
604 | 57-50-030-0001-LH | 100512551 | Detailed Inspection of Inboard Main Flap Torque Tubes at Track Support 01 and Attachment to Main Carriage, Including Bearings, Pins and Spline Fittings, LH/RH, with Flap Root Fairings removed - Inside of Wing to Fuselage Fairing and Main Inboard Flap. |  | 0.041667 | STR |  | ACS, × | inboard flap root fairing
605 | 57-50-030-0001-RH | 100513091 | Detailed Inspection of Inboard Main Flap Torque Tubes at Track Support 01 and Attachment to Main Carriage, Including Bearings, Pins and Spline Fittings, LH/RH, with Flap Root Fairings removed - Inside of Wing to Fuselage Fairing and Main Inboard Flap. |  | 0.041667 | STR |  | ACS, × | inboard flap root fairing
606 | 57-50-031-0001-LH | 100309845 | Special Detailed Inspection (Eddy Current) of Aft Flap Track Supports 02, 03 and 04, LH/RH - External area of Aft Flap Track Supports. |  | 0.063194 | STR | NDI(ET) NOTE: Flaps have to be fully extended. | ×, × | ×
607 | 57-50-031-0001-RH | 100309948 | Special Detailed Inspection (Eddy Current) of Aft Flap Track Supports 02, 03 and 04, LH/RH - External area of Aft Flap Track Supports. |  | 0.041667 | STR | NDI(ET) NOTE: Flaps have to be fully extended. | ×, × | ×
608 | 57-50-031-0002-LH | 100309851 | Detailed Inspection of Main Carriage to Main Panel Attachments, including Panel Fittings, Main Carriage Fittings, Pins and Links, LH/RH - External area. |  | 0.061111 | STR | NOTE: Flaps have to be fully extended. | STR, × | ×
609 | 57-50-031-0002-RH | 100309914 | Detailed Inspection of Main Carriage to Main Panel Attachments, including Panel Fittings, Main Carriage Fittings, Pins and Links, LH/RH - External area. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | STR, × | ×
610 | 57-70-001-0776-U | 100686984 | General Visual Inspection of Spoiler Hinges Fittings and Spoiler Actuator Fittings, including Attachments at Spoiler Panel and Wing Spars, LH/RH - External Side of Wing Fixed Trailing Edge. |  | 0.17708 | STR | NOTE: Flaps have to be fully extended and Spoilers have to be deployed. | STR, × | ×
611 | 71-00-00-001-LH | 100412641 | General Visual Inspection of the Thermal Blanket, Aft Core Cowl, Trust Reverser and Fireseals for general condition. |  | 0.025 | ACS |  | ×, × | ×
612 | 71-00-00-001-RH | 100412645 | General Visual Inspection of the Thermal Blanket, Aft Core Cowl, Trust Reverser and Fireseals for general condition. |  | 0.051389 | ACS |  | ×, × | ×
613 | 71-00-00-002-U | TBD | Visual Check of Engine Fault Messages on the MFD (Multi Function Display). |  | 0.022917 | REI | A CHECK ITEM NHF TASK
614 | 71-61-00-001-LH | 100424929 | General Visual Inspection of Engine Inlet Cowl lip, outer and inner barrel for general condition and distortion. |  | 0.020833 | ACS |  | ×, × | ×
615 | 71-61-00-001-RH | 100424941 | General Visual Inspection of Engine Inlet Cowl lip, outer and inner barrel for general condition and distortion. |  | 0.035417 | ACS |  | ×, × | ×
616 | 72-21-05-002-LH | 100412658 | Detailed Inspection of Engine Fan Blades to detect cracks. |  | 0.025 | ACS |  | ACS, × | ×
617 | 72-21-05-002-RH | 100412663 | Detailed Inspection of Engine Fan Blades to detect cracks. |  | 0.030556 | ACS |  | ACS, × | ×
618 | 72-23-01-001-LH | 100412666 | Inspect (General Visual) the Engine Fan Containment Case outside area for obvious damage. |  | 0.025 | ACS |  | ×, × | ×
619 | 72-23-01-001-RH | 100412671 | Inspect (General Visual) the Engine Fan Containment Case outside area for obvious damage. |  | 0.030556 | ACS |  | ×, × | ×
620 | 72-23-02-001-LH | 100412674 | Detailed Inspection of the visible areas of the outlet guide vanes frame mount lugs for cracks, condition and security. |  | 0.015278 | ACS |  | ACS, × | ×
621 | 72-23-02-001-RH | 100412679 | Detailed Inspection of the visible areas of the outlet guide vanes frame mount lugs for cracks, condition and security. |  | 0.030556 | ACS |  | ACS, × | ×
622 | 72-51-08-001-LH 72-44-00-001-LH | 100619882 | Special Detailed Inspection of Engine Stage 1 and 2 High Pressure Turbine Blades, and stage 2 nozzle segments for burns, cracks or damage using a borescope. Special Detailed Inspection of Engine Stage 1 Nozzle and Combustion Liner for evidence of burns, cracks or damage using a borescope. |  | 0.041667 | ACS | NHF TASK Borescope
623 | 72-51-08-001-RH 72-44-00-001-RH | 100614893 | Special Detailed Inspection of Engine Stage 1 and 2 High Pressure Turbine Blades, and stage 2 nozzle segments for burns, cracks or damage using a borescope. Special Detailed Inspection of Engine Stage 1 Nozzle and Combustion Liner for evidence of burns, cracks or damage using a borescope. |  | 0.041667 | ACS | NHF TASK Borescope
624 | 73-01-400-H001-U | 100412680 | Detailed Inspection of engine FADEC connectors, overbraids, tag-rings, strain relief backshell and electrical bonding between units and aircraft structure. |  | 0.015278 | ACS | NHF TASK | ×, × | ×
625 | 73-11-00-001-LH | 100412686 | General Visual Inspection of the Engine Fuel Distribution system components for leaks condition and security of installation. |  | 0.025 | ACS | NHF TASK | ×, × | ×
626 | 73-11-00-001-RH | 100412691 | General Visual Inspection of the Engine Fuel Distribution system components for leaks condition and security of installation. |  | 0.0375 | ACS | NHF TASK | ×, × | ×
627 | 73-11-09-001-LH | 100179804 | Remove and discard fuel filter element. |  | 0.1125 | ACS |  | ACS, × | ×
628 | 73-11-09-001-RH | 100309868 | Remove and discard fuel filter element. |  | 0.1125 | ACS |  | ACS, × | ×
629 | 74-11-02-001-LH | 800051230 | Operational check of Engine Ignition Switch. |  | 0.0625 | ACS | NHF TASK | ×, × | ×
630 | 74-11-02-001-RH | 800051233 | Operational check of Engine Ignition Switch. |  | 0.0625 | ACS | NHF TASK | ×, × | ×
631 | 75-31-00-001-LH | 100040539 | Detailed Inspection of Engine Variable Geometry Vanes System actuators, linkages and rings for condition and security. |  | 0.016667 | ACS |  | ACS, × | ×
632 | 75-31-00-001-RH | 100412699 | Detailed Inspection of Engine Variable Geometry Vanes System actuators, linkages and rings for condition and security. |  | 0.029167 | ACS |  | ACS, × | ×
633 | 78-31-001-0001-LH | 100143875 | Detailed Inspection of Thrust Reverser Hinges, LH/RH, with Thrust Reverser opened - Inside area covered by Thrust Reverser Assembly. |  | 0.041667 | STR |  | ACS, × | ×
634 | 78-31-001-0001-RH | 100144041 | Detailed Inspection of Thrust Reverser Hinges, LH/RH, with Thrust Reverser opened - Inside area covered by Thrust Reverser Assembly. |  | 0.041667 | STR |  | ×, × | ×
635 | 78-31-001-0002-U | 91049459 | Special Detailed Inspection (Eddy Current) of Thrust Reverser Upper Beam, LH/RH, with Thrust Reverser opened - Inside area covered by Thrust Reverser Assembly. |  | 0.041667 | STR | NDI(ET) | ACS, × | ×
636 | 78-31-002-0002-U | 100509377 | Special Detailed Inspection (Eddy Current) of Thrust Reverser Lower Beam, LH/RH, with Thrust Reverser opened - Inside area covered by Thrust Reverser Assembly. |  | 0.041667 | STR | NDI(ET) | ACS, × | ×
637 | 78-32-00-001-LH | 100412700 | Detailed Inspection of the Engine Thrust Reverser Cowl Lock, Actuators Locks and Gimbals. Inspect for general condition of the system and the integrity of each actuator internal lock, cowl lock and gimbals. |  | 0.095833 | ACS |  | ACS, × | ×
638 | 78-32-00-001-RH | 800051279 | Detailed Inspection of the Engine Thrust Reverser Cowl Lock, Actuators Locks and Gimbals. Inspect for general condition of the system and the integrity of each actuator internal lock, cowl lock and gimbals. |  | 0.0625 | ACS |  | ACS, × | ×
639 | 79-21-05-001-LH | 100412705 | Discard Engine Oil Filter Element. |  | 0.11944 | ACS |  | ACS, × | ×
640 | 79-21-05-001-RH | 100412706 | Discard Engine Oil Filter Element. |  | 0.0875 | ACS |  | ACS, × | ×
641 | 79-34-01-001-LH | 100619444 | Functional Check of Engine Oil Filter Impending Bypass Sensor pressure set point. |  | 0.1625 | ACS |  | ACS, × | ×
642 | 79-34-01-001-RH | 100619448 | Functional Check of Engine Oil Filter Impending Bypass Sensor pressure set point. |  | 0.12917 | ACS |  | ACS, × | ×
643 | 79-35-01-001-LH | 800051296 | Functional Check of Engine Master Chip Detector Indication System. |  | 0.125 | ACS |  | ACS, × | ×
644 | 79-35-01-001-RH | 100040544 | Functional Check of Engine Master Chip Detector Indication System. |  | 0.091667 | ACS |  | ACS, × | ×
645 | 80-11-01-002-LH | TBD | Detailed Inspection of Engine Air Turbine Starter drain plug chip detector. |  | 0.051389 | ACS | A CHECK ITEM NHF TASK
646 | 80-11-01-002-RH | TBD | Detailed Inspection of Engine Air Turbine Starter drain plug chip detector. |  | 0.0375 | ACS | A CHECK ITEM NHF TASK
647 | JAIR-E00-00-001 | 100823419 | GVI - TO PREVENT PDA DUE TO HUMAN ERROR (FUSELAGE) |  | 0.083333 | GEN
648 | JAIR-E00-00-002 | 100823418 | GVI - TO PREVENT PDA DUE TO HUMAN ERROR (WING) |  | 0.083333 | GEN
649 | JAIR-E00-00-003 | 100823417 | GVI - TO PREVENT PDA DUE TO HUMAN ERROR (TAIL) |  | 0.041667 | GEN
650 | JAIR-E05-98-001 | 100823416 | GVI - PDA RELATED AREA (FUSELAGE) |  | 0.41667 | GEN
651 | JAIR-E05-98-002 | 100823421 | GVI - PDA RELATED AREA (WING) |  | 0.25 | GEN
652 | JAIR-E05-98-003 | 100823420 | GVI - PDA RELATED AREA (TAIL) |  | 0.16667 | GEN
653 | JAIR-E12-13-001 | 100736565 | Check - Engine Oil Level (LH Engine) |  | 0.041667 | ACS | 最終日実施 | ×, ×
654 | JAIR-E12-13-002 | 100736566 | Check - Engine Oil Level (RH Engine) |  | 0.041667 | ACS | 最終日実施 | ×, ×
655 | JAIR-E12-22-103 | 100723063 | C C'K Cleaning |  | 1899-12-31 10:50 | CBN |  | ×, ×
656 | JAIR-E21-51-003 | 100619911 | Replace - Pack Flow Control Valve Filter (LH) |  | 0.041667 | ACS | REPLACE P/N:1001456-6, S/N:2017010025
657 | JAIR-E23-61-001 | 100730838 | Replace - Static Dischargers on the Trailing Edge of Rudder and Elavator |  | 1899-12-31 06:00 | REI
658 | JAIR-E23-98-003 | 100706877 | INSPECTION - GGV COMPONENTS FOR PROPER MOUNTING |  | 0.25 | REI |  | ×, ×
659 | JAIR-E24-03-001 | 100793417 | GVI - SPDA 1 Connectors, 360° Metallic backshell and Electrical Bonding |  | 0.024306 | REI
660 | JAIR-E25-00-101 | 100736567 | Check - Loading of Loose and Emergency Equipment |  | 0.14583 | CBN |  | ×, ×
661 | JAIR-E25-21-001 | 100412757 | Inspection - Lighter around Seat Bottom Cushion |  | 0.041667 | CBN |  | ×, ×
662 | JAIR-E25-62-002 | 100719474 | 180 DAYS CHECK |  | 0.083333 | CBN |  | ×, ×
663 | JAIR-E27-03-001 | 100827163 | FNC - P-ACE AOA LIMITING FUNCTION |  | 0.25 | ACS
664 | JAIR-E27-03-002 | 100518043 | FNC - P-ACE AOA LIMITING FUNCTION |  | 0.25 | ACS
665 | JAIR-E29-10-002 | 100412753 | Functional Check (acidity and contamination) of the Hydraulic Fluid (Analysis) |  | 0 | ACS |  | ACS, ×
666 | JAIR-E29-11-001 | 100722588 | RESTORE - No1 & No2 EDP CASE DRAIN FILTER |  | 0.083333 | ACS |  | ×
667 | JAIR-E29-11-002 | 100770005 | DET - ACMP UNION LOOSENESS |  | 0.125 | ACS | A-CHECK ITEM | ×, ×
668 | JAIR-E31-61-001 | 100871643 | Operational Check of the reversion operation of PFD, MFD & EICAS Displays. |  | 0.020833 | REI
669 | JAIR-E32-49-001 | 100736571 | SVC - NOSE LANDING GEAR (NLG) WHEEL TIRE |  | 0.027083 | ACS | 最終日実施 | ×, ×
670 | JAIR-E32-49-002 | 100736570 | SVC - MAIN LANDING GEAR (MLG) WHEEL TIRE |  | 0.029167 | ACS | 最終日実施 | ×, ×
671 | JAIR-E34-26-001 | 100793416 | Operation Check - Micro-IRU Switch on the pilot and co-pilot Reversionary Panel |  | 0.031944 | REI | NHF TASK | ×, ×
672 | JAIR-E36-10-001 | 100535087 | Replace - Cross Bleed Valve Supply Filter |  | 0.041667 | ACS | REPLACE P/N:1001248-2, S/N:2010061434
673 | JAIR-E53-05-001 | 100706905 | INSP – Rear Fuselage APU Compartment Drain Mast |  | 0.041667 | STR
674 | JAIR-E54-50-001 | 100723059 | INSP – Pylon Access Door |  | 0.0625 | STR |  | ×, ×
675 | JAIR-E56-11-001 | 100718011 | Inspection - L/H Cockpit Windshield |  | 0.041667 | ACS |  | ×, ×
676 | JAIR-E56-11-002 | 100718013 | Inspection - R/H Cockpit Windshield |  | 0.041667 | ACS |  | ×, ×
677 | JAIR-E71-00-002 | 100649281 | Replace - Engine |  | 1900-01-02 22:00 | ACS | POS:LH REPLACE P/N:CF34-8E5G01, S/N:193657 | ×, ×
678 |  | 100104497
679 | JAIR-E72-00-004 | TBD | Water Wash - LH ENG |  | 0.24375 | ACS |  | ACS, ×
680 | JAIR-E72-00-005 | 100836276 | Water Wash - RH ENG |  | 0.24375 | ACS |  | ACS, ×
681 | JAIR-E72-00-006 | 100856031 | Lubrication - FAN Blade Pins of LH ENG |  | 0.16667 | ACS |  | ×, ×
682 | JAIR-E72-00-007 | 100810329 | Lubrication - FAN Blade Pins of RH ENG |  | 0.16667 | ACS |  | ×, ×
683 | JAIR-E72-21-002 | 100878859 | Inspection - Fan Blades Pin Hole (RH Engine) | TCD/AD | 0.017361 | ACS | NDI(ET) POS:RH 17
684 |  | 100878860 |  |  | 0.017361 |  | NDI(ET) POS:RH 02
685 |  | 100878861 |  |  | 0.017361 |  | NDI(ET) POS:RH 23
686 |  | 100878862 |  |  | 0.017361 |  | NDI(ET) POS:RH 04
687 |  | 100878863 |  |  | 0.017361 |  | NDI(ET) POS:RH 25
688 |  | 100878864 |  |  | 0.017361 |  | NDI(ET) POS:RH 27
689 |  | 100878865 |  |  | 0.017361 |  | NDI(ET) POS:RH 10
690 |  | 100878866 |  |  | 0.017361 |  | NDI(ET) POS:RH 18
691 |  | 100878867 |  |  | 0.017361 |  | NDI(ET) POS:RH 15
692 |  | 100878868 |  |  | 0.017361 |  | NDI(ET) POS:RH 06
693 |  | 100878869 |  |  | 0.017361 |  | NDI(ET) POS:RH 03
694 |  | 100878870 |  |  | 0.017361 |  | NDI(ET) POS:RH 24
695 |  | 100878871 |  |  | 0.017361 |  | NDI(ET) POS:RH 13
696 |  | 100878872 |  |  | 0.017361 |  | NDI(ET) POS:RH 19
697 |  | 100878873 |  |  | 0.017361 |  | NDI(ET) POS:RH 28
698 |  | 100878874 |  |  | 0.017361 |  | NDI(ET) POS:RH 12
699 |  | 100878875 |  |  | 0.017361 |  | NDI(ET) POS:RH 08
700 |  | 100878876 |  |  | 0.017361 |  | NDI(ET) POS:RH 11
701 | JAIR-E72-21-002 | 100878877 | Inspection - Fan Blades Pin Hole (RH Engine) | TCD/AD | 0.017361 | ACS | NDI(ET) POS:RH 05
702 |  | 100878878 |  |  | 0.017361 |  | NDI(ET) POS:RH 22
703 |  | 100878879 |  |  | 0.017361 |  | NDI(ET) POS:RH 16
704 |  | 100878880 |  |  | 0.017361 |  | NDI(ET) POS:RH 26
705 |  | 100878881 |  |  | 0.017361 |  | NDI(ET) POS:RH 21
706 |  | 100878882 |  |  | 0.017361 |  | NDI(ET) POS:RH 07
707 |  | 100878883 |  |  | 0.017361 |  | NDI(ET) POS:RH 20
708 |  | 100878884 |  |  | 0.017361 |  | NDI(ET) POS:RH 09
709 |  | 100878885 |  |  | 0.017361 |  | NDI(ET) POS:RH 01
710 |  | 100878886 |  |  | 0.017361 |  | NDI(ET) POS:RH 14
711 | JAIR-E72-44-001 | 100619870 | BSI - Aft Inner Band of HPT Stage 1 Nozzle (LH Engine) |  | 0.083333 | ACS | Borescope
712 | JAIR-E72-44-002 | 100567221 | BSI - Aft Inner Band of HPT Stage 1 Nozzle (RH Engine) |  | 0.083333 | ACS | Borescope
713 | JAIR-E72-51-001 | 100619871 | BSI - HPT Stage 1 Damper (LH Engine) |  | 0.083333 | ACS | Borescope
714 | JAIR-E72-51-002 | 100567746 | BSI - HPT Stage 1 Damper (RH Engine) |  | 0.083333 | ACS | Borescope
715 | Z100-002-U | 100412761 | General Visual Inspection of Fuselage Lower Portion from Radome to Center Fuselage III, Including Radome, Antennas Areas, External Power, Oxygen Ground Connection, Water and Waste Compartments, Drain Valves, RAT and Cargo Compartment Doors (Except area covered by Wing to Fuselage Fairing) - External Side of Fuselage. |  | 0.1 | STR |  | ×, × | If necessary, rear-fuselage drain-tube fairing
716 | Z120-001-U | 100412765 | General Visual Inspection of Fwd Fuselage Fwd Pressure Bulkhead Aft Face, Fwd Fuselage Bottom Front Area and NLG Wheel Well Bay (Inside the Fuselage), including the Bottom Surface of Floor Structure areas - Internal Side. |  | 0.13958 | STR | NOTE: EWIS. Cockpit Floor Panels have to be removed. | ACS, I | ×
717 | Z140-001-U | 100412769 | General Visual Inspection of Wing Stub Rear Box and AFT Pressure Bulkhead (non pressurized side and covered by Tire Burst Shield Protector) at the Region of Main Landing Gear Wheel Well - Internal Side. |  | 0.041667 | STR | NOTE: Inspection through the Main Landing Gear Wheel Bay - Wing Stub Rear Box. | ACS, I | ×
718 | Z140-003-U | 100723064 | General Visual Inspection of Center E-Bay area and Aft Pressure Bulkhead Aft Face at Center Fuselage II, including the Bottom Surface of Floor Structures - Inside Center E-Bay. |  | 0.23611 | STR | NOTE: EWIS. | ×, I | ×
719 | Z190-001-U | 100412777 | General Visual Inspection of Wing to Fuselage Fairing - External Side. |  | 0.0625 | STR |  | ×, × | ×
720 | Z190-002-U | 100412781 | General Visual Inspection of Wing Stub and Center Fuselage II Lower Portion, Forward Pressure Bulkhead and Keel Beam at Areas Covered by Center and Lateral Wing to Fuselage Fairings, including Internal Surface of Fairings - Internal Side of Center and Lateral Wing to Fuselage Fairings. |  | 0.074306 | STR | NOTE: EWIS. | ACS, I | ×
721 | Z191-001-U | 100706902 | General Visual Inspection of Center Fuselage I and II Lower Portion, and Keel Beam at Areas Covered by FWD Wing to Fuselage Fairing, including Internal Surface of Fairing - Internal Side of FWD Wing to Fuselage Fairing. |  | 0.16667 | STR | NOTE: EWIS. FWD Wing to Fuselage Fairing has to be removed. | ×, × | FWD Wing-to-Fuselage Fairing
722 | Z195-001-U | 100412790 | General Visual Inspection of Center Fuselage II and III Lower Portion, and Keel Beam at Areas Covered by AFT Wing to Fuselage Fairing, including Internal Surface of Fairing - Internal Side of AFT Wing to Fuselage Fairing. |  | 0.09375 | STR | NOTE: EWIS. AFT Wing to Fuselage Fairing has to be removed. | ACS/STR, × | Aft Wing-to-Fuselage Fairing
723 | Z200-001-LH | 100412794 | General Visual Inspection of Fwd and Center Fuselage I, II and III Side and Top Areas - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
724 | Z200-001-RH | 100412962 | General Visual Inspection of Fwd and Center Fuselage I, II and III Side and Top Areas - External Side of Fuselage. |  | 0.041667 | STR |  | ×, × | ×
725 | Z220-003-U | 100730839 | General Visual Inspection of Cockpit Main Instrument Panel, Control Pedestal, Yoke and Pedals Areas - Internal Side of Cockpit. |  | 0.13611 | ACS | NOTE: EWIS. | ACS, × | ×
726 | Z310-001-U | 100412829 | General Visual Inspection of Rear Fuselage, Rear Pressure Bulkhead, Horizontal Stabilizer Root Area and Tail Cone to Rear Fuselage Attachments - Internal Side of Fuselage. |  | 0.15347 | STR | NOTE: EWIS. | STR, I | APU firewall panels
727 | Z320-001-U | 800051477 | General Visual Inspection of Vertical Stabilizer, Leading Edge, Dorsal Fin, Rudder, and Tip Fairings - External Side of Stabilizer. |  | 0.028472 | STR |  | ×, × | ×
728 | Z330-001-LH | 100412833 | General Visual Inspection of LH/RH Horizontal Stabilizer, Elevator, and Fairings - External Side. |  | 0.044444 | STR |  | ×, × | ×
729 | Z330-001-RH | 100412837 | General Visual Inspection of LH/RH Horizontal Stabilizer, Elevator, and Fairings - External Side. |  | 0.035417 | STR |  | ×, × | ×
730 | Z350-001-U | 100412842 | General Visual Inspection of Exhaust Silencer Pipe and Auxiliary Power Unit (APU) - Internal Side of Tail Cone and APU. |  | 0.075694 | STR | NOTE: EWIS. | STR/ACS, × | ×
731 | Z400-001-LH | 100412846 | General Visual Inspection of LH/RH Pylon, Engine, Fan, Thrust Reverser and Cowlings - External Side. |  | 0.031944 | STR |  | ACS, × | ×
732 | Z400-001-RH | 100412850 | General Visual Inspection of LH/RH Pylon, Engine, Fan, Thrust Reverser and Cowlings - External Side. |  | 0.0375 | STR |  | ACS, × | ×
733 | Z400-002-LH | 100412854 | General Visual Inspection of LH/RH Cowlings, Thrust Reverser - Internal side, and Engine from Fan Blades to Exhaust - Outer surface. |  | 0.15972 | STR | NOTE: EWIS. Engine Cowlings must be opened. | ACS, × | ×
734 | Z400-002-RH | 100412858 | General Visual Inspection of LH/RH Cowlings, Thrust Reverser - Internal side, and Engine from Fan Blades to Exhaust - Outer surface. |  | 0.17986 | STR | NOTE: EWIS. Engine Cowlings must be opened. | ACS, × | ×
735 | Z411-001-LH | 100598812 | General Visual Inspection of LH/RH Engine Air Inlet Module - Internal Side of Inlet Cowl. |  | 0.038194 | STR |  | ×, × | ×
736 | Z411-001-RH | 100598817 | General Visual Inspection of LH/RH Engine Air Inlet Module - Internal Side of Inlet Cowl. |  | 0.025694 | STR |  | ×, × | ×
737 | Z419-001-LH | 100412869 | General Visual Inspection of LH/RH Pylon and Pylon Fairings, including the area of Wing Lower Skin covered by Pylon Fairings - Internal Side of Pylon and Fairings. |  | 0.38403 | STR | NOTE: EWIS. | ACS/STR, × | ×
738 | Z419-001-RH | 100412873 | General Visual Inspection of LH/RH Pylon and Pylon Fairings, including the area of Wing Lower Skin covered by Pylon Fairings - Internal Side of Pylon and Fairings. |  | 0.43819 | STR | NOTE: EWIS. | ACS/STR, × | ×
739 | Z500-001-LH | 800051531 | General Visual Inspection of Wing Upper and Lower Surfaces, LH/RH - External Side of Wing. |  | 0.034028 | STR |  | ×, × | ×
740 | Z500-001-RH | 800051534 | General Visual Inspection of Wing Upper and Lower Surfaces, LH/RH - External Side of Wing. |  | 0.025 | STR |  | ×, × | ×
741 | Z500-002-LH | 800051539 | General Visual Inspection of Wing Flaps, Aileron, Spoilers, Flap Track Fairings, Shrouds and Wing Trailing Edge, Including Flap Actuation Torque Tube and Angle Gear Box, Multifunction Spoiler PCUs, Hydraulic Lines, FIREX Lines, Wiring Bundles, Aileron Control Cables, LH/RH - External Side. |  | 0.0625 | STR | NOTE: EWIS. Flaps and Spoilers have to be fully extended. | ACS, I | ×
742 | Z500-002-RH | 800051542 | General Visual Inspection of Wing Flaps, Aileron, Spoilers, Flap Track Fairings, Shrouds and Wing Trailing Edge, Including Flap Actuation Torque Tube and Angle Gear Box, Multifunction Spoiler PCUs, Hydraulic Lines, FIREX Lines, Wiring Bundles, Aileron Control Cables, LH/RH - External Side. |  | 0.0625 | STR | NOTE: EWIS. Flaps and Spoilers have to be fully extended. | ACS, I | ×
743 | Z500-004-LH | 100164595 | General Visual Inspection of Wing Main Box from Rib 21 to Wing Tip Rib and area covered by Aileron Shrouds - Internal Side of Wing Main Box Dry Area and Aileron Shrouds. |  | 0.029861 | STR | NOTE: EWIS. | ×, I | ×
744 | Z500-004-RH | 100164643 | General Visual Inspection of Wing Main Box from Rib 21 to Wing Tip Rib and area covered by Aileron Shrouds - Internal Side of Wing Main Box Dry Area and Aileron Shrouds. |  | 0.045833 | STR | NOTE: EWIS. | ×, I | ×
745 | Z500-005-LH | 100412883 | General Visual Inspection of Flap Mechanisms 2, 3, 4 and Flap Track Fairings, including the area of Wing Lower Skin covered by Flap Track Fairings - Internal Side of Flap Track Fairings. |  | 0.070833 | STR | NOTE: Flaps have to be fully extended and Flap Fairings have to be removed. | ACS, × | ×
746 | Z500-005-RH | 100412887 | General Visual Inspection of Flap Mechanisms 2, 3, 4 and Flap Track Fairings, including the area of Wing Lower Skin covered by Flap Track Fairings - Internal Side of Flap Track Fairings. |  | 0.050694 | STR | NOTE: Flaps have to be fully extended and Flap Fairings have to be removed. | ACS, × | ×
747 | Z510-001-LH | 100412892 | General Visual Inspection of Wing Leading Edge, Wing Slats, Wing Root Landing-Light Fairing, Wing Tip Leading Edge and Wing Tip Fairing - External Side of Wing Leading Edge. |  | 0.097222 | STR | NOTE: Slats have to be fully extended. | ×, × | ×
748 | Z510-001-RH | 100412896 | General Visual Inspection of Wing Leading Edge, Wing Slats, Wing Root Landing-Light Fairing, Wing Tip Leading Edge and Wing Tip Fairing - External Side of Wing Leading Edge. |  | 0.077083 | STR | NOTE: Slats have to be fully extended. | ×, × | ×
749 | Z510-002-LH | 100412899 | General Visual Inspection of Wing Leading Edge LH/RH, including the Winglet/Wingtip to Wing Spar Attachments - Internal Side of Wing Leading Edge. |  | 0.14653 | STR | NOTE: EWIS. | STR, × | wing root landing light lens fairing wing tip fairing
750 | Z510-002-RH | 100412903 | General Visual Inspection of Wing Leading Edge LH/RH, including the Winglet/Wingtip to Wing Spar Attachments - Internal Side of Wing Leading Edge. |  | 0.14653 | STR | NOTE: EWIS. | STR, × | wing root landing light lens fairing wing tip fairing
751 | Z522-001-LH | 100412907 | General Visual Inspection of Wing Rear Box at area between Spar II and Spar III, from Rib 4A to Rib 10 of Wing Fixed Trailing Edge - Internal Side. |  | 0.05 | STR | NOTE: EWIS. | STR, × | ×
752 | Z522-001-RH | 100412911 | General Visual Inspection of Wing Rear Box at area between Spar II and Spar III, from Rib 4A to Rib 10 of Wing Fixed Trailing Edge - Internal Side. |  | 0.05 | STR | NOTE: EWIS. | STR, × | ×
753 | Z700-001-U | 100412916 | General Visual Inspection of NLG, Wheelwell, and Doors - External Side at NLG Compartment. |  | 0.038889 | STR | NOTE: EWIS. | ACS/STR, × | ×
754 | Z700-002-LH | 100412920 | General Visual Inspection of LH/RH MLG Box, Tire Compartment, Center Fuselage II Aft Pressure Bulkhead Fwd Side at Non-Pressurized Side (Except Area Covered by Tire Burst Shield), MLG and MLG Doors, and part of Keel Beam at MLG compartment - External Side at MLG Compartment. |  | 0.059722 | STR | NOTE: EWIS. | ACS/STR, × | ×
755 | Z700-002-RH | 100412924 | General Visual Inspection of LH/RH MLG Box, Tire Compartment, Center Fuselage II Aft Pressure Bulkhead Fwd Side at Non-Pressurized Side (Except Area Covered by Tire Burst Shield), MLG and MLG Doors, and part of Keel Beam at MLG compartment - External Side at MLG Compartment. |  | 0.038889 | STR | NOTE: EWIS. | ACS/STR, × | ×
756 | Z811-001-U | 800051590 | General Visual Inspection of Fwd Passenger Door - External Side of Door. |  | 0.0125 | STR |  | ×, × | ×
757 | Z811-002-U | 800051593 | General Visual Inspection of Fwd Passenger Door - Internal Side of Door. |  | 0.045833 | STR | NOTE: Door has to be opened. | CBN, × | forward passenger-door lining emergency-evacuation slide
758 | Z812-001-U | 100412930 | General Visual Inspection of Aft Passenger Door - External Side of Door. |  | 0.033333 | STR |  | ×, × | ×
759 | Z812-002-U | 100412934 | General Visual Inspection of Aft Passenger Door - Internal Side of Door. |  | 0.077083 | STR | NOTE: Door has to be opened. | CBN, × | aft passenger-door lining emergency-evacuation slide
760 | Z821-001-U | 800051602 | General Visual Inspection of Fwd Service Door - External Side of Door. |  | 0.0125 | STR |  | ×, × | ×
761 | Z821-002-U | 100412939 | General Visual Inspection of Fwd Service Door - Internal Side of Door. |  | 0.046528 | STR | NOTE: Door has to be opened. | CBN, × | forward passenger-door lining emergency-evacuation slide
762 | Z822-001-U | 100412943 | General Visual Inspection of Fwd Cargo Door - External Side of Door. |  | 0.027083 | STR |  | ×, × | ×
763 | Z822-002-U | 100412947 | General Visual Inspection of Fwd Cargo Door - Internal Side of Door. |  | 0.036806 | STR | NOTE: Door has to be opened. | STR, × | forward cargo-door lining insulation blankets
764 | Z823-001-U | 100412951 | General Visual Inspection of Aft Cargo Door - External Side of Door. |  | 0.026389 | STR |  | ×, × | wing-to-fuselage aft section fairing
765 | Z823-002-U | 800051617 | General Visual Inspection of Aft Cargo Door - Internal Side of Door. |  | 0.025 | STR | NOTE: Door has to be opened. | STR, × | aft cargo-door lining insulation blankets
766 | Z824-001-U | 800051620 | General Visual Inspection of Aft Service Door - External Side of Door. |  | 0.0125 | STR |  | ×, × | ×
767 | Z824-002-U | 100412957 | General Visual Inspection of Aft Service Door - Internal Side of Door. |  | 0.069444 | STR | NOTE: Door has to be opened. | CBN, × | aft service-door lining emergency-evacuation slide
768 | REQUEST JOB CARD | 100901239 | PLZ RMV/INST - LH ENG |  | 1900-01-03 04:00 | GEN
769 | REQUEST JOB CARD | 100901240 | PERFORM - DOCK IN SAFETY |  | 1899-12-31 | GEN
770 | REQUEST JOB CARD | 100901241 | PERFORM - ENGINEERING SUPPORT |  | 1900-01-01 02:00 | GEN
771 | REQUEST JOB CARD | 100901242 | PERFORM - FLOOR INSPECTION (INSPECTOR) |  | 1900-01-01 02:00 | INSP
772 | REQUEST JOB CARD | 100901243 | PERFORM - CPT INVENTORY CK |  | 0.16667 | GEN
773 | REQUEST JOB CARD | 100901245 | PERFORM - SQ SCREEN (GEN) |  | 1900-01-03 04:00 | GEN
774 | REQUEST JOB CARD | 100901246 | PERFORM - SQ SCREEN (STR) |  | 1900-01-03 04:00 | STR
775 | REQUEST JOB CARD | 100901247 | COND CK - REMOVED PARTS (GEN) |  | 1900-01-01 | GEN
776 | REQUEST JOB CARD | 100901248 | COND CK - REMOVED PARTS (STR) |  | 0.66667 | STR
777 | REQUEST JOB CARD | 100901249 | PERFORM - SELF FINAL CK |  | 1899-12-31 08:00 | GEN
778 | REQUEST JOB CARD | 100901250 | DEACTIVE/ACTIVE - ALL PAX & SVC DOOR PNEU ASSY |  | 0.083333 | GEN
779 | REQUEST JOB CARD | 100901251 | PERFORM - CBN APPEARANCE C'K |  | 0.33333 | GEN
780 | REQUEST JOB CARD | 100901252 | COND CK - BOTH ENG PNEU T-DUCT (E170) |  | 0.083333 | GEN
781 | REQUEST JOB CARD | 100901253 | PERFORM - APU PRESERVATION |  | 0.33333 | GEN
782 | REQUEST JOB CARD | 100901254 | CONFIRM - GREEN MARK DATA BASE |  | 0.33333 | STR
783 | REQUEST JOB CARD | 100901255 | COND CK - EXTERIOR POLYURETHANE FILMS (PPT) |  | 0.083333 | GEN
784 | REQUEST JOB CARD | 100901256 | PLZ CLEAN UP - CBN RMVED PARTS |  | 1899-12-31 08:00 | GEN
785 | REQUEST JOB CARD | 100901257 | PLZ CLEAN UP - SHIP EXTERIOR |  | 1900-01-03 | GEN
786 | REQUEST JOB CARD | 100901258 | PLZ PNT TOUCH UP - COCKPIT & CBN INTERIOR |  | 0.33333 | GEN
787 | REQUEST JOB CARD | 100901259 | PLZ PNT TOUCH UP - EXTERNAL SURFACE |  | 1899-12-31 16:00 | GEN
788 | REQUEST JOB CARD | 100901260 | PLZ RMV/INST - LH ENG T/REV COWL FOR MAKE ACCESS |  | 1899-12-31 01:00 | GEN
789 | REQUEST JOB CARD | 100901261 | PLZ RMV/INST - RH ENG T/REV COWL FOR MAKE ACCESS |  | 1899-12-31 01:00 | GEN
790 | REQUEST JOB CARD | 100901262 | PLZ RMV/INST - COCKPIT MISCELLAEOUS PARTS |  | 0.33333 | GEN
791 | REQUEST JOB CARD | 100901263 | PLZ RMV/INST - CBN MISCELLAEOUS PARTS |  | 1900-01-02 08:00 | GEN
792 | REQUEST JOB CARD | 100901264 | PLZ RMV/INST - FWD CGO MISCELLAEOUS PARTS |  | 0.66667 | GEN
793 | REQUEST JOB CARD | 100901265 | PLZ RMV/INST - AFT CGO MISCELLAEOUS PARTS |  | 0.33333 | GEN
794 | REQUEST JOB CARD | 100901266 | PLZ RMV/INST - FUSELAGE MISCELLAEOUS PARTS |  | 0.66667 | GEN
795 | REQUEST JOB CARD | 100901267 | PLZ RMV/INST - LH WING MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
796 | REQUEST JOB CARD | 100901268 | PLZ RMV/INST - RH WING MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
797 | REQUEST JOB CARD | 100901269 | PLZ RMV/INST - TAIL MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
798 | REQUEST JOB CARD | 100901270 | PLZ RMV/INST - LH ENG/PYL MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
799 | REQUEST JOB CARD | 100901271 | PLZ RMV/INST - RH ENG/PYL MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
800 | REQUEST JOB CARD | 100901272 | LEAK CK - APU COMBUSTOR CASE BLEED AIR PORT & ANTI SURGE BLEED PORT |  | 0.083333 | GEN
801 | REQUEST JOB CARD | 100901273 | PLZ LEAK CK - BOTH ENG MANUAL CRANKING PAD AFT ENG RUN |  | 0.125 | GEN
802 | REQUEST JOB CARD | 100901274 | PERFORM - FUEL TANK WORK PREPERATION & RESTORATION |  | 0.83333 | GEN
803 | REQUEST JOB CARD | 100901275 | PLZ RMV/INST - INSULATION BLANKET FOR 1ST INSP |  | 1900-01-07 08:00 | GEN
804 | REQUEST JOB CARD | 100901276 | PERFORM - CBN PRESS CK |  | 0.16667 | GEN
805 | REQUEST JOB CARD | 100901277 | PLZ RMV/INST - PILOT & COPILOT SEAT FOR MAKE ACCESS |  | 0.25 | GEN
806 | REQUEST JOB CARD | 100901278 | PLZ RMV/INST - COCKPIT OVERHEAD PNL FOR MAKE ACCESS |  | 1899-12-31 06:00 | GEN
807 | REQUEST JOB CARD | 100901279 | PLZ RMV/INST - BOTH COCKPIT DV WINDOW FOR MAKE ACCESS |  | 0.25 | GEN
808 | REQUEST JOB CARD | 100901280 | PLZ RMV/INST - OXY MASK BOX FOR RMV CPT CONSOLES |  | 0.16667 | GEN
809 | REQUEST JOB CARD | 100901281 | PLZ RMV/INST - COCKPIT DOOR FOR MAKE ACCESS |  | 0.41667 | GEN
810 | REQUEST JOB CARD | 100901282 | PLZ OPE TEST - COCKPIT (AFT RESTORATION) |  | 0.083333 | GEN
811 | REQUEST JOB CARD | 100901283 | PLZ RMV/INST - FWD E-BAY ACCESS HATCH FOR MAKE ACCESS |  | 0.16667 | GEN
812 | REQUEST JOB CARD | 100901286 | PLZ RMV/INST - EICC FOR MAKE ACCESS |  | 0.33333 | GEN
813 | REQUEST JOB CARD | 100901287 | PLZ RMV/INST - CBN WINDSCREEN FOR MAKE ACCESS |  | 0.5 | GEN
814 | REQUEST JOB CARD | 100901288 | PLZ RMV/INST - PAX SEAT FOR MAKE ACCESS |  | 1900-01-02 08:00 | GEN
815 | REQUEST JOB CARD | 100901289 | PLZ RMV/INST - PAX/SVC DOOR EMER EVAC SLIDE ASSY FOR MAKE ACCESS |  | 0.66667 | GEN
816 | REQUEST JOB CARD | 100901290 | PLZ RMV/INST - CBN OVERHEAD BIN FOR MAKE ACCESS |  | 1900-01-01 | GEN
817 | REQUEST JOB CARD | 100901291 | PLZ RMV/INST - CBN PSU PNL & PSU STR FOR MAKE ACCESS |  | 0.66667 | GEN
818 | REQUEST JOB CARD | 100901292 | PLZ RMV/INST - CBN FLOOR CARPET FOR MAKE ACCESS |  | 1899-12-31 08:00 | GEN
819 | REQUEST JOB CARD | 100901293 | PLZ RMV/INST - CBN HARNESS PROT COVER FOR MAKE ACCESS |  | 0.33333 | GEN
820 | REQUEST JOB CARD | 100901295 | PLZ RMV/INST - FWD G1 GLY FOR MAKE ACCESS |  | 0.66667 | GEN
821 | REQUEST JOB CARD | 100901296 | PLZ RMV/INST - FWD G2 GLY FOR MAKE ACCESS |  | 0.66667 | GEN
822 | REQUEST JOB CARD | 100901297 | PLZ RMV/INST - AFT G3 GLY FOR MAKE ACCESS |  | 0.66667 | GEN
823 | REQUEST JOB CARD | 100901298 | PLZ RMV/INST - FWD LAV FOR MAKE ACCESS |  | 0.66667 | GEN
824 | REQUEST JOB CARD | 100901299 | PLZ RMV/INST - AFT LAV FOR MAKE ACCESS |  | 0.66667 | GEN
825 | REQUEST JOB CARD | 100901301 | PLZ RMV/INST - GLY INSERT FOR MAKE ACCESS |  | 0.083333 | GEN
826 | REQUEST JOB CARD | 100901302 | PLZ RMV/INST - FWD CGO LT & SMOKE DET FOR MAKE ACCESS |  | 0.41667 | GEN
827 | REQUEST JOB CARD | 100901303 | PLZ RMV/INST - AFT CGO LT & SMOKE DET FOR MAKE ACCESS |  | 0.41667 | GEN
828 | REQUEST JOB CARD | 100901304 | PLZ RMV/INST - FWD WING TO FUSE FRG FOR MAKE ACCESS |  | 0.625 | GEN
829 | REQUEST JOB CARD | 100901305 | PLZ RMV/INST - AFT DRAIN TUBE FRG FOR AFT BODY FRG TO RMV |  | 0.125 | GEN
830 | REQUEST JOB CARD | 100901306 | PLZ RMV/INST - AFT DRAIN TUBE FRG FOR FUSE DRAIN VLV INSP |  | 0.125 | GEN
831 | REQUEST JOB CARD | 100901307 | PLZ RPLC - LH WING & STUB FUEL TANK PNL SEAL |  | 1899-12-31 | GEN
832 | REQUEST JOB CARD | 100901308 | PLZ RPLC - RH WING & STUB FUEL TANK PNL SEAL |  | 1899-12-31 | GEN
833 | REQUEST JOB CARD | 100901309 | PLZ RMV/INST - BOTH AFT NAV/STROBE LT ASSY FOR MAKE ACCESS |  | 0.16667 | GEN
834 | REQUEST JOB CARD | 100901310 | PLZ RMV/INST - BOTH WING TIP FRG FOR MAKE ACCESS |  | 0.33333 | GEN
835 | REQUEST JOB CARD | 100901311 | PLZ RMV/INST - LH PYL AFT FRG FOR MAKE ACCESS |  | 0.625 | GEN
836 | REQUEST JOB CARD | 100901312 | PLZ RMV/INST - RH PYL AFT FRG FOR MAKE ACCESS |  | 0.625 | GEN
837 | REQUEST JOB CARD | 100901314 | PLZ RMV/INST - LH ELEV FOR MAKE ACCESS |  | 1899-12-31 01:00 | GEN
838 | REQUEST JOB CARD | 100901315 | PLZ RMV/INST - RH ELEV FOR MAKE ACCESS |  | 1899-12-31 01:00 | GEN
839 | REQUEST JOB CARD | 100901317 | PLZ RMV/INST - APU FOR MAKE ACCESS |  | 0.625 | GEN

## AP
JA216J _6C_AP List
No | Order | Event Description | Plan | Remarks
1 | 100901053 | OPEN THE PANEL(AFT CARGO COMPARTMENT CEILING - ACCESS DOORS AND PANELS) | 0.083333
2 | 100901054 | CLOSE THE PANEL(AFT CARGO COMPARTMENT CEILING - ACCESS DOORS AND PANELS) | 0.125
3 | 100901055 | OPEN THE PANEL(AFT CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.083333
4 | 100901056 | CLOSE THE PANEL(AFT CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.12083
5 | 100901057 | OPEN THE PANEL(AFT CARGO COMPARTMENT SIDEWALL - ACCESS DOORS AND PANELS) | 0.0625
6 | 100901058 | CLOSE THE PANEL(AFT CARGO COMPARTMENT SIDEWALL - ACCESS DOORS AND PANELS) | 0.20833
7 | 100901059 | OPEN THE PANEL(AFT CARGO DOOR - ACCESS DOORS AND PANELS) | 0.083333
8 | 100901060 | CLOSE THE PANEL(AFT CARGO DOOR - ACCESS DOORS AND PANELS) | 0.125
9 | 100901061 | OPEN THE PANEL(AFT PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.054167
10 | 100901062 | CLOSE THE PANEL(AFT PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.12083
11 | 100901063 | OPEN THE PANEL(AFT SERVICE DOOR - ACC DOORS AND PANELS) | 0.05
12 | 100901064 | CLOSE THE PANEL(AFT SERVICE DOOR - ACC DOORS AND PANELS) | 0.0875
13 | 100901065 | OPEN THE PANEL(CENTER FUSELAGE I (FWD CARGO COMPT) - ACCESS DOORS AND PANEL) | 0.10417
14 | 100901066 | CLOSE THE PANEL(CENTER FUSELAGE I (FWD CARGO COMPT) - ACCESS DOORS AND PANEL) | 0.20833
15 | 100901067 | OPEN THE PANEL(CENTER FUSELAGE I - ACCESS DOORS AND PANELS) | 0.0041667
16 | 100901068 | CLOSE THE PANEL(CENTER FUSELAGE I - ACCESS DOORS AND PANELS) | 0.0041667
17 | 100901069 | OPEN THE PANEL(CENTER FUSELAGE I CEILING - ACCESS DOORS AND PANELS) | 0.016667
18 | 100901070 | CLOSE THE PANEL(CENTER FUSELAGE I CEILING - ACCESS DOORS AND PANELS) | 0.041667
19 | 100901071 | OPEN THE PANEL(CENTER FUSELAGE I LH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.0375
20 | 100901072 | CLOSE THE PANEL(CENTER FUSELAGE I LH LATERAL LINING - ACCESS DOORS AND PAN... | 0.083333
21 | 100901073 | OPEN THE PANEL(CENTER FUSELAGE I RH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.025
22 | 100901074 | CLOSE THE PANEL(CENTER FUSELAGE I RH LATERAL LINING - ACCESS DOORS AND PAN... | 0.05
23 | 100901075 | OPEN THE PANEL(CENTER FUSELAGE II (PASSENGER CABIN) - ACCESS DOORS AND PANELS) | 0.10417
24 | 100901076 | CLOSE THE PANEL(CENTER FUSELAGE II (PASSENGER CABIN) - ACCESS DOORS AND PA... | 0.14583
25 | 100901077 | OPEN THE PANEL(CENTER FUSELAGE II - ACCESS DOORS AND PANELS) | 0.12917
26 | 100901078 | CLOSE THE PANEL(CENTER FUSELAGE II - ACCESS DOORS AND PANELS) | 0.25417
27 | 100901079 | OPEN THE PANEL(CENTER FUSELAGE II CEILING - ACCESS DOORS AND PANELS) | 0.066667
28 | 100901080 | CLOSE THE PANEL(CENTER FUSELAGE II CEILING - ACCESS DOORS AND PANELS) | 0.16667
29 | 100901081 | OPEN THE PANEL(CENTER FUSELAGE II LH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.045833
30 | 100901082 | CLOSE THE PANEL(CENTER FUSELAGE II LH LATERAL LINING - ACCESS DOORS AND PA... | 0.083333
31 | 100901083 | OPEN THE PANEL(CENTER FUSELAGE II RH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.045833
32 | 100901084 | CLOSE THE PANEL(CENTER FUSELAGE II RH LATERAL LINING - ACCESS DOORS AND PA... | 0.083333
33 | 100901085 | OPEN THE PANEL(CENTER FUSELAGE III (AFT CARGO COMPT) - ACCESS DOORS AND PANEL) | 0.10417
34 | 100901086 | CLOSE THE PANEL(CENTER FUSELAGE III (AFT CARGO COMPT) - ACCESS DOORS AND P... | 0.20833
35 | 100901087 | OPEN THE PANEL(CENTER FUSELAGE III (PASSENGER CABIN) - ACCESS DOORS AND PAN... | 0.21667
36 | 100901088 | CLOSE THE PANEL(CENTER FUSELAGE III (PASSENGER CABIN) - ACCESS DOORS AND P... | 0.30417
37 | 100901089 | OPEN THE PANEL(CENTER FUSELAGE III - ACCESS DOORS AND PANELS) | 0.0013889
38 | 100901090 | CLOSE THE PANEL(CENTER FUSELAGE III - ACCESS DOORS AND PANELS) | 0.0013889
39 | 100901091 | OPEN THE PANEL(CENTER FUSELAGE III CEILING - ACCESS DOORS AND PANELS) | 0.16667
40 | 100901092 | CLOSE THE PANEL(CENTER FUSELAGE III CEILING - ACCESS DOORS AND PANELS) | 0.41667
41 | 100901093 | OPEN THE PANEL(CENTER FUSELAGE III LH LATERAL LINING - ACCESS DOORS AND PAN... | 0.083333
42 | 100901094 | CLOSE THE PANEL(CENTER FUSELAGE III LH LATERAL LINING - ACCESS DOORS AND P... | 0.15833
43 | 100901095 | OPEN THE PANEL(CENTER FUSELAGE III RH LATERAL LINING - ACCESS DOORS AND PAN... | 0.075
44 | 100901096 | CLOSE THE PANEL(CENTER FUSELAGE III RH LATERAL LINING - ACCESS DOORS AND P... | 0.11667
45 | 100901097 | OPEN THE PANEL(COCKPIT - ACCESS DOORS AND PANELS) | 0.6
46 | 100901098 | CLOSE THE PANEL(COCKPIT - ACCESS DOORS AND PANELS) | 0.9125
47 | 100901099 | OPEN THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - LH WING - ACCESS DOORS AND PA... | 0.26667
48 | 100901100 | CLOSE THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - LH WING - ACCESS DOORS AND ... | 0.35
49 | 100901101 | OPEN THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - RH WING - ACCESS DOORS AND PA... | 0.26667
50 | 100901102 | CLOSE THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - RH WING - ACCESS DOORS AND ... | 0.35
51 | 100901103 | OPEN THE PANEL(FLAPS - LH WING - ACCESS DOORS AND PANELS) | 0.025
52 | 100901104 | CLOSE THE PANEL(FLAPS - LH WING - ACCESS DOORS AND PANELS) | 0.033333
53 | 100901105 | OPEN THE PANEL(FLAPS - RH WING - ACCESS DOORS AND PANELS) | 0.025
54 | 100901106 | CLOSE THE PANEL(FLAPS - RH WING - ACCESS DOORS AND PANELS) | 0.033333
55 | 100901107 | OPEN THE PANEL(FORWARD CARGO COMPARTMENT CEILING - ACCESS DOORS AND PANELS) | 0.14583
56 | 100901108 | CLOSE THE PANEL(FORWARD CARGO COMPARTMENT CEILING - ACCESS DOORS AND PANELS) | 0.33333
57 | 100901109 | OPEN THE PANEL(FORWARD CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.054167
58 | 100901110 | CLOSE THE PANEL(FORWARD CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.14167
59 | 100901111 | OPEN THE PANEL(FORWARD CARGO COMPARTMENT SIDEWALL - ACCESS DOORS AND PANELS) | 0.066667
60 | 100901112 | CLOSE THE PANEL(FORWARD CARGO COMPARTMENT SIDEWALL - ACCESS DOORS AND PANELS) | 0.2
61 | 100901113 | OPEN THE PANEL(FORWARD CARGO DOOR - ACCESS DOORS AND PANELS) | 0.066667
62 | 100901114 | CLOSE THE PANEL(FORWARD CARGO DOOR - ACCESS DOORS AND PANELS) | 0.11667
63 | 100901115 | OPEN THE PANEL(FORWARD FUSELAGE (COCKPIT) - ACCESS DOORS AND PANELS) | 0.17917
64 | 100901116 | CLOSE THE PANEL(FORWARD FUSELAGE (COCKPIT) - ACCESS DOORS AND PANELS) | 0.2625
65 | 100901117 | OPEN THE PANEL(FORWARD FUSELAGE (FWD CARGO COMPARTMENT) - ACCESS DOORS AND ... | 0.0625
66 | 100901118 | CLOSE THE PANEL(FORWARD FUSELAGE (FWD CARGO COMPARTMENT) - ACCESS DOORS AN... | 0.10417
67 | 100901119 | OPEN THE PANEL(FORWARD FUSELAGE (PASSENGER CABIN) - ACCESS DOORS AND PANELS) | 0.075
68 | 100901120 | CLOSE THE PANEL(FORWARD FUSELAGE (PASSENGER CABIN) - ACCESS DOORS AND PANELS) | 0.11667
69 | 100901121 | OPEN THE PANEL(FORWARD FUSELAGE - ACCESS DOORS AND PANELS) | 0.020833
70 | 100901122 | CLOSE THE PANEL(FORWARD FUSELAGE - ACCESS DOORS AND PANELS) | 0.05
71 | 100901123 | OPEN THE PANEL(FORWARD PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.054167
72 | 100901124 | CLOSE THE PANEL(FORWARD PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.091667
73 | 100901125 | OPEN THE PANEL(FORWARD SERVICE DOOR - ACCESS DOORS AND PANELS) | 0.05
74 | 100901126 | CLOSE THE PANEL(FORWARD SERVICE DOOR - ACCESS DOORS AND PANELS) | 0.0875
75 | 100901127 | OPEN THE PANEL(FWD FUSELAGE LH LATERAL LINING(PAX CABIN) - ACCESS DOORS & P... | 0.10417
76 | 100901128 | CLOSE THE PANEL(FWD FUSELAGE LH LATERAL LINING(PAX CABIN) - ACCESS DOORS &... | 0.13333
77 | 100901129 | OPEN THE PANEL(FWD FUSELAGE RH LATERAL LINING(PAX CABIN) - ACCESS DOORS & P... | 0.079167
78 | 100901130 | CLOSE THE PANEL(FWD FUSELAGE RH LATERAL LINING(PAX CABIN) - ACCESS DOORS &... | 0.11667
79 | 100901131 | OPEN THE PANEL(LEADING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.2
80 | 100901132 | CLOSE THE PANEL(LEADING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.375
81 | 100901133 | OPEN THE PANEL(LEADING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.21667
82 | 100901134 | CLOSE THE PANEL(LEADING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.40833
83 | 100901135 | OPEN THE PANEL(LH HORIZONTAL TAIL - ACCESS DOORS AND PANELS) | 0.17569
84 | 100901136 | CLOSE THE PANEL(LH HORIZONTAL TAIL - ACCESS DOORS AND PANELS) | 0.33403
85 | 100901137 | OPEN THE PANEL(LH POWERPLANT - ACCESS DOORS AND PANELS) | 0.10694
86 | 100901138 | CLOSE THE PANEL(LH POWERPLANT - ACCESS DOORS AND PANELS) | 0.15278
87 | 100901139 | OPEN THE PANEL(LH PYLON - ACCESS DOORS AND PANELS) | 0.59167
88 | 100901140 | CLOSE THE PANEL(LH PYLON - ACCESS DOORS AND PANELS) | 1899-12-31 01:00
89 | 100901141 | OPEN THE PANEL(MAIN LANDING GEAR WHEELWELL - ACCESS DOORS AND PANELS) | 0.13333
90 | 100901142 | CLOSE THE PANEL(MAIN LANDING GEAR WHEELWELL - ACCESS DOORS AND PANELS) | 0.13333
91 | 100901143 | OPEN THE PANEL(MAJOR SUB-ZONE 810 - DOORS - LEFT FUSELAGE SIDE) | 0.0013889
92 | 100901144 | CLOSE THE PANEL(MAJOR SUB-ZONE 810 - DOORS - LEFT FUSELAGE SIDE) | 0.0013889
93 | 100901145 | OPEN THE PANEL(MAJOR SUB-ZONE 820 - DOORS - RH FUSELAGE SIDE) | 0.0027778
94 | 100901146 | CLOSE THE PANEL(MAJOR SUB-ZONE 820 - DOORS - RH FUSELAGE SIDE) | 0.0027778
95 | 100901147 | OPEN THE PANEL(PASSENGER CABIN INTERNAL - ACCESS DOORS AND PANELS) | 0.016667
96 | 100901148 | CLOSE THE PANEL(PASSENGER CABIN INTERNAL - ACCESS DOORS AND PANELS) | 0.025
97 | 100901149 | OPEN THE PANEL(REAR FUSELAGE - ACCESS DOORS AND PANELS) | 0.0125
98 | 100901150 | CLOSE THE PANEL(REAR FUSELAGE - ACCESS DOORS AND PANELS) | 0.0125
99 | 100901151 | OPEN THE PANEL(RH HORIZONTAL TAIL - ACCESS DOORS AND PANELS) | 0.17569
100 | 100901152 | CLOSE THE PANEL(RH HORIZONTAL TAIL - ACCESS DOORS AND PANELS) | 0.33403
101 | 100901153 | OPEN THE PANEL(RH POWERPLANT - ACCESS DOORS AND PANELS) | 0.10694
102 | 100901154 | CLOSE THE PANEL(RH POWERPLANT - ACCESS DOORS AND PANELS) | 0.15278
103 | 100901155 | OPEN THE PANEL(RH PYLON - ACCESS DOORS AND PANELS) | 0.58333
104 | 100901156 | CLOSE THE PANEL(RH PYLON - ACCESS DOORS AND PANELS) | 0.95833
105 | 100901157 | OPEN THE PANEL(TAIL CONE - ACCESS DOORS AND PANELS) | 0.11667
106 | 100901158 | CLOSE THE PANEL(TAIL CONE - ACCESS DOORS AND PANELS) | 0.15417
107 | 100901159 | OPEN THE PANEL(TRAILING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.066667
108 | 100901160 | CLOSE THE PANEL(TRAILING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.11667
109 | 100901161 | OPEN THE PANEL(TRAILING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.066667
110 | 100901162 | CLOSE THE PANEL(TRAILING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.11667
111 | 100901163 | OPEN THE PANEL(VERTICAL TAIL - ACCESS DOORS AND PANELS) | 0.56667
112 | 100901164 | CLOSE THE PANEL(VERTICAL TAIL - ACCESS DOORS AND PANELS) | 0.92083
113 | 100901165 | OPEN THE PANEL(WING CENTER AREA - LH WING - ACCESS DOORS AND PANELS) | 0.0875
114 | 100901166 | CLOSE THE PANEL(WING CENTER AREA - LH WING - ACCESS DOORS AND PANELS) | 0.27083
115 | 100901167 | OPEN THE PANEL(WING CENTER AREA - RH WING - ACCESS DOORS AND PANELS) | 0.0875
116 | 100901168 | CLOSE THE PANEL(WING CENTER AREA - RH WING - ACCESS DOORS AND PANELS) | 0.27083
117 | 100901169 | OPEN THE PANEL(WING INBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.15
118 | 100901170 | CLOSE THE PANEL(WING INBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.35417
119 | 100901171 | OPEN THE PANEL(WING INBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.15417
120 | 100901172 | CLOSE THE PANEL(WING INBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.3625
121 | 100901173 | OPEN THE PANEL(WING OUTBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.079167
122 | 100901174 | CLOSE THE PANEL(WING OUTBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.13333
123 | 100901175 | OPEN THE PANEL(WING OUTBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.079167
124 | 100901176 | CLOSE THE PANEL(WING OUTBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.13333
125 | 100901177 | OPEN THE PANEL(WING-TO-FUSELAGE FAIRING - ACCESS DOORS AND PANELS) | 0.91667
126 | 100901178 | CLOSE THE PANEL(WING-TO-FUSELAGE FAIRING - ACCESS DOORS AND PANELS) | 1899-12-31 08:00
127 | 100901179 | OPEN THE PANEL(WINGLET - LH WING - ACCESS DOORS AND PANELS) | 0.029167
128 | 100901180 | CLOSE THE PANEL(WINGLET - LH WING - ACCESS DOORS AND PANELS) | 0.05
129 | 100901181 | OPEN THE PANEL(WINGLET - RH WING - ACCESS DOORS AND PANELS) | 0.029167
130 | 100901182 | CLOSE THE PANEL(WINGLET - RH WING - ACCESS DOORS AND PANELS) | 0.05

## COA
JA216J _6C_COA List
No | COA/ER | Order | Event Description | AD TCD | Work CAT | COA Rev. | ER Rev. | Plan | Remarks
1 | COA23-00013-ER02 | 100880059 | Replace - VHF-3 Antenna (E170) |  | MI | 0 | A | 0.16667
2 | COA25-00040-ER01 | 100816549 | RPLC - Spacer of Toilet Shroud at FWD LAV (E170) |  | MI | 0 | A | 0.083333
3 | COA25-00040-ER03 | 100816608 | RPLC - Spacer of Toilet Shroud at AFT LAV (E170) |  | MI | 0 | A | 0.083333
4 | COA27-00011-ER01 | 100889110 | INSP - Control Yoke Harness (ERJ170) |  | MI | A | A | 0.33333
5 | COA27-00013-ER01 | 100848122 | Modification - Control Column Wires (E170) |  | MI | 0 | 0 | 0.20833
6 | COA31-00011-ER02 | 100894484 | Install - EPIC Load 25.9 (E170) |  | MI | 0 | 0 | 0.3375
7 | COA36-00011-ER01 | 100759507 | Install - Resistor to ODS (E170) |  | MI | 0 | A | 1899-12-31 12:00
8 | COA36-00015-ER01 | 100860787 | INSP/RPLC - Sensing Elements (Part I) |  | MI | A | B | 1900-01-02 04:00
9 | COA36-00015-ER02 | 100860836 | INSP/RPLC - Sensing Elements (Part II) |  | MI | A | B | 1899-12-31 14:00
10 | COA36-00015-ER03 | 100860885 | INSP/RPLC - Sensing Elements (Part III) |  | MI | A | B | 1900-01-02
11 | COA36-00015-ER04 | 100860932 | INSP/RPLC - Sensing Elements (Part IV) |  | MI | A | C | 1899-12-31 02:00
12 | COA36-00015-ER05 | 100861044 | INSP/RPLC - Sensing Elements (Part V) |  | MI | A | B | 1899-12-31 22:00
13 | COA36-00015-ER06 | 100861099 | INSP/RPLC - Sensing Elements (Part VI) |  | MI | A | B | 1900-01-01
14 | COA36-00015-ER07 | 100861155 | INSP/RPLC - Sensing Elements (Part VII) |  | MI | A | B | 1899-12-31 02:00
15 | COA36-00017-ER01-LH | 100881198 | MOD - Pylon Sense Line and ELEC Cables |  | MI | 0 | 0 | 0.25
16 | COA36-00017-ER01-RH | 100881216 | MOD - Pylon Sense Line and ELEC Cables |  | MI | 0 | 0 | 0.25
17 | COA38-00005-ER01 | 100791184 | MOD - WWSC Electrical Harness (E170) |  | MI | 0 | A | 0.5
18 | COA52-00011-ER01 | 100770369 | Re-TQ - PAX and SVC Door Hinge Arm Chain |  | MK | 0 | 0 | 0.41667
19 | COA52-00013-ER01 | 100748436 | CK/LUB-FWD PAX Door Handle and Ramp |  | MI | 0 | 0 | 0.16667
20 | COA52-00015-ER01 | 100812681 | INSP-Non-plug Type MAINT SVC DR/PNL |  | MI | 0 | 0 | 0.083333
21 | COA53-00030-ER01 | 100734508 | Rework - Protection Cover Support (E170) |  | MI | 0 | A | 0.16667
22 | COA54-00002-ER01 | 100753552 | MOD-L/H Pylon LWR Link FTG Attach Parts |  | MI | 0 | D | 1900-01-13 04:00
23 | COA54-00002-ER02 | 100753719 | MOD-R/H Pylon LWR Link FTG Attach Parts |  | MI | 0 | D | 1900-01-13 04:00
24 | COA54-00008-ER01 | 100882724 | RPLC - LH Pylon Drain Tube Parts |  | MI | 0 | 0 | 0.79167
25 | COA54-00008-ER02 | 100882742 | RPLC - RH Pylon Drain Tube Parts |  | MI | 0 | 0 | 0.79167

## EV
JA216J _6C_EV List
No | EV | Order | Event Description | AD TCD | Work CAT | EV Rev. | Plan | Remarks
1 | EV-OSASE-01369 | 100768397 | EV-OSASE-01369 "SWAP - ACMP 3A FOR 3B (JA216J) |  | GEN | 0 | 0.16667
0:00
[9 empty] | 249J/H-18-2 | 0:00

## 経観CO
JA216J _6C_C/O SQ & Monitoring Inspection
Monitoring Inspection |  | C/O SQ |  | C'K
INSP Date | CLOSE Date | C/O Date | CLOSE Date | JALEC | No |  | Order | Extern.ID | Task Description | M/H | Remarks
[5 empty] | 1 | CO | 100616593 | DOCK SQ:100616593 | C/O DELAMI - CBN FLOOR PNL 241BLF UPR SURFACE | 0.66667 | REPLACE実施
[5 empty] | 2 | CO | 100616556 | DOCK SQ:100616556 | C/O DELAMI - PAX CBN FLOOR PNL 232ARF | 0.66667 | REPLACE実施
[5 empty] | 3 | CO | 100833894 | 2058280821ITM001 | BOTH OB MAIN WHEEL FAIRING SCREW HOLE WAS ENLARGE. | 0.66667 | PERMANENT REPAIR実施
[5 empty] | 4 | CO | 100819115 | 2190280621ITM001 | FOUND DAMAGE FWD CGO FLOOR FINISHING (LEXAN) AT 131CLF. | 0.16667 | REPAIR実施
[5 empty] | 5 | CO | 100833899 | 2058280821ITM003 | LH #1 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 6 | CO | 100833902 | 2058280821ITM004 | LH #2 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 7 | CO | 100833905 | 2058280821ITM005 | LH #3 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 8 | CO | 100833907 | 2058280821ITM006 | LH #4 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 9 | CO | 100833910 | 2058280821ITM007 | LH #5 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 10 | CO | 100833908 | 2058280821ITM008 | RH #1 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 11 | CO | 100833903 | 2058280821ITM009 | RH #2 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 12 | CO | 100833906 | 2058280821ITM010 | RH #3 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 13 | CO | 100833909 | 2058280821ITM011 | RH #4 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 14 | CO | 100833911 | 2058280821ITM012 | RH #5 SPOILER NAME PLATE MISSING |  | NOT PLANNED
[5 empty] | 15 | MI | EWE7415 | EWE7415-MI | TAPPING CK AND VISUAL INSP - FAN CASE ABRADABLE AREA (RH ENG) | 0.125 | INSP実施
[5 empty] | 16 | MI | EWS7144 | EWS7144-MI | INSP - APU FIRE WALL PNL No.351BZ LWR AREA | 0.041667 | INSP実施
[5 empty] | 17 | MI | EWS7415 | EWS7145-MI | INSP - APU FIRE WALL PNL No.351BZ UPR AREA | 0.041667 | INSP実施
[5 empty] | 18 | MI | EWS7097 | EWS7097-MI | INSP - LH H/STAB L/E ACC PNL No.331AL L/E SKIN | 0.041667 | INSP実施
[5 empty] | 19 | MI | EWS7098 | EWS7098-MI | INSP - RH H/STAB L/E ACC PNL No.341AR L/E SKIN | 0.041667 | INSP実施
[5 empty] | 20 | MI | EWS7033 | EWS7033-MI | INSP - APU FIRE WALL LH PNL (PNL No,351AZ) | 0.16667 | INSP実施
[5 empty] | 21 | MI | EWS7035 | EWS7035-MI | INSP - TOOL MARK WINDSHIELD CUTOUT STRUCTURE | 0.041667 | INSP実施

## IO
JA216J _6C_Inspection Order
No | Date | Order | Event Description | Receipt | Completion
/
/
/
/
/
/
/
| / | [5 empty] | 0:00
/
| / |  |  |  |  | 249J/H-18-2 | 0:00
/
/
/
/
/
/
/