## 計画書
OMZ Hangar Maintenance Plan & Report | [9 empty] | Plan No. OMZ/P-320 |  |  |  |  | Plan |  |  |  | Receipt | Completion |  |  |  |  | Planner Complete
| In-Charge | ( | OMA |  | ) | [9 empty] | Approval |  | In-Charge |  |  | DIC |  |  | OMA
JA227J _08S_長期要目
Work Place: ITM HGR
■ 航空機整備改造認定 |  |  |  | □ 航空機整備検査認定
In-Out Plan |  | 2022-01-03 |  | (Mon) | S | ～ | 2022-01-06 |  | (Thu) | S | 4 |  | Days
① Schedule | [11 empty] | ② Aircraft Detail Data
|  | Arrival |  | Start |  | HGR |  | ALL | Departure |  |  |  | A/C Reg No. |  |  | Ship Type |  |  | Model |  | Serial No.
[6 empty] | Completion |  | Completion |  |  |  |  | JA227J |  |  | E170 |  |  | ERJ 170-100 STD |  | 17000524
| Plan | 2021-01-03 |  | 2021-01-03 |  | 2021-01-06 |  | 2021-01-06 | 2021-01-07
|  | TBD |  | 22:00 |  | 9:00 |  | 22:00 | TBD
|  | TBD | [6 empty] | TBD
| Actual | / |  | / |  | / |  | / | /
|  | ： |  | ： |  | ： |  | ： | ：
③ Topics | [8 empty] | ④ Elapse (Start～All Completion) | [8 empty] | ⑦ Planning Job & Manhour Info
| A CHECK (G4A04) | [8 empty] | Plan |  | 72:00 |  | Hours |  |  |  |  | RTN | 160 |  | Item | 1900-02-04 17:23 | Manhour
[10 empty] | Actual |  |  |  | Hours |  |  |  |  | AP | 82 |  | Item | 1900-01-04 17:22 | Manhour
[19 empty] | COA | 19 |  | Item | 1900-01-14 01:00 | Manhour
[9 empty] | ⑤ Work Place | [9 empty] | EV | 0 |  | Item | 0:00 | Manhour
[10 empty] | ITM #1 Bay | [8 empty] | C/O&MI | 0 |  | Item | 0 | Manhour
[19 empty] | Planning Total | 261 |  | Item | 1900-02-25 11:45 | Manhour
[9 empty] | ⑥ AMOS Info | [9 empty] | Estimated SQ |  |  |  | 1900-01-01 02:00 | Manhour
[10 empty] | Work Package |  |  | 227J/H-22 | [5 empty] | Estimated Total |  |  |  | 1900-02-27 13:45 | Manhour
Note: Planning section will fill in blanks above after maintenance completion.
Formulas:
OMA = AF26+[OMA, row above]

## RTN
JA227J _08S_RTN List
No | Task Card | Order | Event Description | AD TCD | Plan | Trade | Remarks | TRADE表記 | MAKE ACC(AP CARD以外)
1 | 21-24-02-001-LH | 100794230 | Discard of Recirculation Fan Filters. |  | 0.0625 | CBN |  | ×, × | ×
2 | 21-24-02-001-RH | 100794206 | Discard of Recirculation Fan Filters. |  | 0.0625 | CBN |  | ×, × | ×
3 | 21-51-10-001-RH | 800461557 | Restoration (cleaning) of Pack Bypass Valve Filter. |  | 0.041667 | CBN | FOR P/N:820914-7, S/N:2007080667 | ×, × | ×
4 | 25-11-01-004-U | 100356014 | Detailed Inspection of Pilot/Co-pilot Seats belts looking for possible damage and wear. |  | 0.0375 | REI |  | ×, × | ×
5 | 25-21-20-001-U | 100186024 | Detailed Inspection of Flight Attendant Seats (Cushions and Structures, including Seat Belts, Buckles and Shoulder Harness) for tears, loose stiches, wear, corrosion, defective parts and damage. |  | 0.027778 | CBN |  | ×, × | ×
6 | 26-21-05-002-U | 100355879 | Operational Check of Engine Fire Extinguishing Bottle Temperature Compensated Pressure Switch (TCPS). Press the switches button and check if the related message is triggered on EICAS. |  | 0.052083 | ACS |  | ACS, × | ×
7 | 26-22-03-002-U | 100794199 | Operational Check of APU Fire Extinguishing Bottle Pressure Switch (TCPS). Press the switch button and check if the related message is triggered on EICAS. |  | 0.034028 | ACS |  | ACS, × | ×
8 | 26-22-09-002-U | 100798851 | Operational Check of APU Fire Extinguishing Switch to Fuel Shutoff Valve Electrical Hardware. Check through the message on the EICAS if the APU fire extinguishing switch is commanding the APU fuel shutoff valve closure. |  | 0.10069 | ACS | A-CHECK ITEM | ACS, × | ×
9 | 27-00-00-001C-U | 100720969 | Operational Check of all Flight Control System Power Control Units (PCUs) - Integrity Test. |  | 0.10139 | ACS | A-CHECK ITEM | ×, × | ×
10 | 27-00-00-001-U | 100670162 | Operational Check of all Flight Control System Power Control Units (PCUs) - Integrity Test. |  | 0.054861 | ACS | A-CHECK ITEM | ×, × | ×
11 | 27-11-03-001-LH | 100186040 | Functional Check of Aileron Control Cables Tension at Wing Area. |  | 0.16319 | ACS |  | ACS, × | ×
12 | 27-11-03-001-RH | 100186044 | Functional Check of Aileron Control Cables Tension at Wing Area. |  | 0.12014 | ACS |  | ACS, × | ×
13 | 27-11-03-005C-LH | 100359962 | Operational Check of Fuselage Aileron Control Cables for Rupture. |  | 0.063889 | ACS |  | ×, I | ×
14 | 27-11-03-005C-RH | 100360739 | Operational Check of Fuselage Aileron Control Cables for Rupture. |  | 0.0625 | ACS |  | ×, I | ×
15 | 27-12-01-001-LH | 100186053 | Lubrication of Aileron PCUs Toggle Links. |  | 0.083333 | ACS |  | ×, × | ×
16 | 27-12-01-001-RH | 100355936 | Lubrication of Aileron PCUs Toggle Links. |  | 0.050694 | ACS |  | ×, × | ×
17 | 27-22-01-001-U | 100355959 | Lubrication of Rudder PCUs Toggle Links. |  | 0.12361 | ACS |  | ×, × | ×
18 | 27-22-01-007C-U | 100186057 | Functional Check of Rudder PCU Hinge Moment Limiter. |  | 0.18403 | ACS |  | ACS, × | ×
19 | 27-22-01-007-U | 100186056 | Functional Check of Rudder PCU Hinge Moment Limiter. |  | 0.125 | ACS |  | ACS, × | ×
20 | 27-31-00-002-U | 100355986 | Operational Check of Control-Column Disconnect System. |  | 0.10833 | ACS |  | ×, × | ×
21 | 27-31-02-001-FWDLH | 100186062 | Visually check Control-Column Dampers. Check the Level Indicator of Control-Column Dampers (Left and Right Columns). |  | 0.082639 | ACS |  | ×, × | ×
22 | 27-31-02-001-FWDRH | 100186066 | Visually check Control-Column Dampers. Check the Level Indicator of Control-Column Dampers (Left and Right Columns). |  | 0.082639 | ACS |  | ×, × | ×
23 | 27-41-01-001-U | 100737680 | Lubrication of Horizontal Stabilizer Actuator. With a Grease Gun, refill Ballnut with grease. |  | 0.0625 | ACS | A-CHECK ITEM | ×, × | ×
24 | 27-41-01-002-U | 100356102 | Detailed Inspection of Horizontal Stabilizer Actuator including Actuator Mechanical Stops and Actuator Upper and Lower Gimbals for any signs of damage. |  | 0.090972 | ACS |  | ×, × | ×
25 | 27-41-01-005-U | 100720974 | General Visual Inspection of HSTA Ballnut External Ball Return Circuit. |  | 0.050694 | ACS | A-CHECK ITEM | ×, × | ×
26 | 27-41-01-009-U | 100186068 | Servicing of Horizontal Stabilizer No-back mechanism oil. |  | 0.083333 | ACS |  | ×, × | ×
27 | 27-51-00-004-LH | 100356113 | General Visual Inspection of Flap Aerodynamic Seals. |  | 0.066667 | ACS | NOTE: Flaps have to be fully extended. | ×, × | ×
28 | 27-51-00-004-RH | 100186078 | General Visual Inspection of Flap Aerodynamic Seals. |  | 0.041667 | ACS | NOTE: Flaps have to be fully extended. | ×, × | ×
29 | 27-51-10-001-LH | 100730989 | Lubrication of Flap Track Mechanism Needle Rollers. |  | 0.1 | ACS |  | ×, × | ×
30 | 27-51-10-001-RH | 100730983 | Lubrication of Flap Track Mechanism Needle Rollers. |  | 0.12083 | ACS |  | ×, × | ×
31 | 27-81-01-002-U | 100360805 | Operational Check to verify Slat Actuator/Track Rack and Pinion disconnection. |  | 0.085417 | ACS |  | ×, × | ×
32 | 27-81-11-001-LH | 100356149 | Lubrication of Slat Track Rack and Pinion Mechanism. |  | 0.34028 | ACS |  | ×, × | ×
33 | 27-81-11-001-RH | 100356328 | Lubrication of Slat Track Rack and Pinion Mechanism. |  | 0.26667 | ACS |  | ×, × | ×
34 | 28-12-01-001-LH | 100211407 | Functional Check of the Pressure Relief Valve to verify the pressure set point which it opens. |  | 0.01875 | ACS |  | ×, × | ×
35 | 28-12-01-001-RH | 100211411 | Functional Check of the Pressure Relief Valve to verify the pressure set point which it opens. |  | 0.01875 | ACS |  | ×, × | ×
36 | 29-11-00-001-LH | 100360526 | Functional Check of No.1 & 2 Hydraulic System Bootstrap Systems. Check proper operation of bootstrap main components (Priority Valve and other main components) through ACMPs operation and pressure monitoring. |  | 0.0125 | ACS |  | ACS, × | ×
37 | 29-11-00-001-RH | 100360530 | Functional Check of No.1 & 2 Hydraulic System Bootstrap Systems. Check proper operation of bootstrap main components (Priority Valve and other main components) through ACMPs operation and pressure monitoring. |  | 0.0125 | ACS |  | ACS, × | ×
38 | 29-11-00-003-AFTLH | 100692544 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.013889 | ACS | A-CHECK ITEM | ACS, × | ×
39 | 29-11-00-003-AFTRH | 100693192 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.072917 | ACS | A-CHECK ITEM | ACS, × | ×
40 | 29-11-00-003-FWDLH | 100692598 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.013889 | ACS | A-CHECK ITEM | ×, × | ×
41 | 29-11-00-003-FWDRH | 100693624 | Visual Check of No.1 & 2 Hydraulic Systems Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.013889 | ACS | A-CHECK ITEM | ×, × | ×
42 | 29-11-11-001C-LH | 100186092 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.041667 | ACS |  | ACS, × | ×
43 | 29-11-11-001C-RH | 100186093 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.041667 | ACS |  | ACS, × | ×
44 | 29-11-11-001F-LH | 100356236 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.033333 | ACS |  | ACS, × | ×
45 | 29-11-11-001F-RH | 100186095 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.036806 | ACS |  | ACS, × | ×
46 | 29-11-11-001-LH | 100356241 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.092361 | ACS |  | ACS, × | ×
47 | 29-11-11-001-RH | 100186091 | Operational check of No. 1 & 2 Hydraulic Systems Firewall Shutoff Valves (FWSOV) and Auto Shutoff Circuits in the Hydraulic Synoptic Page. |  | 0.036806 | ACS |  | ACS, × | ×
48 | 29-11-16-001-LH | 100827248 | Visual Check of No.1 & 2 Hydraulic Systems Ecology Bottles. Check if the Ecology Bottles are full or cracked. |  | 0.058333 | ACS | A-CHECK ITEM | ×, × | ×
49 | 29-11-16-001-RH | 100827249 | Visual Check of No.1 & 2 Hydraulic Systems Ecology Bottles. Check if the Ecology Bottles are full or cracked. |  | 0.058333 | ACS | A-CHECK ITEM | ×, × | ×
50 | 29-11-30-001-LH | 100360826 | Functional Check of No.1 & 2 Hydraulic Systems Accumulators Pre-Charge. |  | 0.041667 | ACS |  | ACS, × | ×
51 | 29-11-30-001-RH | 100360832 | Functional Check of No.1 & 2 Hydraulic Systems Accumulators Pre-Charge. |  | 0.041667 | ACS |  | ACS, × | ×
52 | 29-12-00-001-U | 100794198 | Functional Check of No.3 Hydraulic System Bootstrap System. Check proper operation of bootstrap main components (Priority Valve and other main components) through ACMP 3B operation and pressure monitoring. |  | 0.013889 | ACS | A-CHECK ITEM | ACS, × | ×
53 | 29-12-00-003-AFTLH | 100827250 | Visual Check of No.3 Hydraulic System Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.058333 | ACS | A-CHECK ITEM | ACS, × | ×
54 | 29-12-00-003-AFTRH | 100827251 | Visual Check of No.3 Hydraulic System Filters DPIs. Make sure that the Filters DPIs are not extended. |  | 0.058333 | ACS | A-CHECK ITEM | ACS, × | ×
55 | 29-12-10-001-U | 100827252 | Visual Check of No.3 Hydraulic System Ecology Bottles. Check if the Ecology Bottles are full or cracked. |  | 0.058333 | ACS | A-CHECK ITEM | ×, × | ×
56 | 29-12-30-001C-U | 100336279 | Functional Check of No.3 Hydraulic System Accumulator Pre-Charge. |  | 0.041667 | ACS | A-CHECK ITEM | ×, × | ×
57 | 29-12-30-001-U | 100794201 | Functional Check of No.3 Hydraulic System Accumulator Pre-Charge. |  | 0.013889 | ACS | A-CHECK ITEM | ACS, × | ×
58 | 29-32-00-001-U | 100827253 | Operational Check of Hydraulic Systems Reservoir. |  | 0.022917 | ACS | A-CHECK ITEM | ×, × | ×
59 | 29-33-01-001C-U | 100186104 | Operational Check of Hydraulic Systems No.1 & 2 Temperature Transducers. |  | 0.041667 | ACS | A-CHECK ITEM | ×, × | ×
60 | 29-33-01-001F-U | 100615838 | Operational Check of Hydraulic Systems Temperature Transducers. |  | 0.033333 | ACS | A-CHECK ITEM | ×, × | ×
61 | 29-33-01-001-U | 100794237 | Operational Check of Hydraulic Systems Temperature Transducers. |  | 0.014583 | ACS | A-CHECK ITEM | ×, × | ×
62 | 29-33-01-002C-U | 100356256 | Operational Check of No.3 Hydraulic Systems Temperature Transducers. |  | 0.077083 | ACS | A-CHECK ITEM | ×, × | ×
63 | 30-11-00-001F-LH | 100356266 | General Visual Inspection of Wing Anti-Ice Supply Ducts and Components for insulation integrity. |  | 0.061806 | ACS |  | ×, × | ×
64 | 30-11-00-001F-RH | 100356320 | General Visual Inspection of Wing Anti-Ice Supply Ducts and Components for insulation integrity. |  | 0.069444 | ACS |  | ×, × | ×
65 | 31-61-02-001-U | 100356352 | Operational Check of the reversion operation of PFD, MFD & EICAS Displays. |  | 0.031944 | REI | NHF TASK | ×, × | ×
66 | 32-11-00-002-LH | 100603543 | Servicing of MLG Shock Absorber Nitrogen Chamber. |  | 0.125 | ACS |  | ×, × | ×
67 | 32-11-00-002-RH | 100603594 | Servicing of MLG Shock Absorber Nitrogen Chamber. |  | 0.13194 | ACS |  | ×, × | ×
68 | 32-11-00-006-LH | 100186121 | Complete servicing of Main Landing Gear Shock Strut. |  | 0.19583 | ACS |  | ×, × | ×
69 | 32-11-00-006-RH | 100355663 | Complete servicing of Main Landing Gear Shock Strut. |  | 0.16806 | ACS |  | ×, × | ×
70 | 32-21-00-002-U | 100602205 | Servicing of NLG Shock Absorber Nitrogen Chamber. |  | 0.09375 | ACS |  | ×, × | ×
71 | 32-21-00-006-U | 100355687 | Complete servicing of Nose Landing Gear Shock Strut. |  | 0.17639 | ACS |  | ×, × | ×
72 | 32-41-17-001-U | 100494174 | Operational Check of Return Line Check Valve of Main Brake Control System. |  | 0.11667 | ACS |  | ×, ×
73 | 32-44-11-001-U | 100186137 | Operational Check of Return Line Check Valve of Emergency/Parking Brake System. |  | 0.05 | ACS |  | ×, × | ×
74 | 32-44-13-001-U | 100794179 | Functional Check of Emergency/Parking Brake Accumulator for Nitrogen Pre-Charge. |  | 0.027083 | ACS |  | ACS, × | ×
75 | 33-50-21-002-LH | 100186141 | General Visual Inspection of Photoluminescent Strip for missing pieces or polycarbonate covered track damage. |  | 0.041667 | CBN |  | ×, × | ×
76 | 33-50-21-002-RH | 100186146 | General Visual Inspection of Photoluminescent Strip for missing pieces or polycarbonate covered track damage. |  | 0.041667 | CBN |  | ×, × | ×
77 | 34-15-00-001-U | 100355728 | Functional check of the Pitot Static System ADS 1, ADS 2 and ADS 3 (altitude and airspeed). |  | 0.42708 | REI | NHF TASK | REI, × | ×
78 | 35-10-00-001-LH | 100355742 | Operational Check of Crew Oxygen Masks and Stowage Box. |  | 0.059028 | CBN |  | ×, × | ×
79 | 35-10-00-001-M | 100355746 | Operational Check of Crew Oxygen Masks and Stowage Box. |  | 0.049306 | CBN |  | ×, × | ×
80 | 35-10-00-001-RH | 100355750 | Operational Check of Crew Oxygen Masks and Stowage Box. |  | 0.048611 | CBN |  | ×, × | ×
81 | 35-30-01-002-U | 100355769 | Visual Check of Portable Oxygen Cylinders Pressure Gauge Indication. |  | 0.023611 | ACS |  | ×, × | ×
82 | 36-11-01-001-RH | 100572898 | Cleaning of High Stage Bleed Valve Wire Mesh Filter by Ultrasonic Method. |  | 0.041667 | ACS | FOR POS:RH P/N:1001246-3, S/N:2010050643 | ×, × | ×
83 | 36-11-02-002-LH | 100356361 | Functional Check of Low Stage Bleed Check Valve. |  | 0.29792 | ACS |  | ACS, × | ×
84 | 36-11-02-002-RH | 100356365 | Functional Check of Low Stage Bleed Check Valve. |  | 0.34028 | ACS |  | ACS, × | ×
85 | 36-11-03-001-RH | 800569025 | Cleaning of Nacelle Pressure-Regulating Shutoff-Valve Filter by ultrasonic method. |  | 0.041667 | ACS | FOR POS:RH P/N:1001246-3, S/N:2013100032 | ×, × | ×
86 | 36-14-01-002-LH | 100848311 | Functional Check of Bleed Overpressure Switch (set point). |  | 0.041667 | ACS |  | ×, × | ×
87 | 36-14-01-002-RH | 100848312 | Functional Check of Bleed Overpressure Switch (set point). |  | 0.041667 | ACS |  | ×, × | ×
88 | 38-41-00-001-U | 100356377 | Discard of Air Manifold Air Filter. |  | 0.10764 | CBN |  | ×, × | ×
89 | 49-91-01-001-U JAIR-E49-00-002 | 100356636 | Discard of APU Oil Filter Element. |  | 0.10417 | ACS |  | ×, × | ×
90 | 50-22-01-001-AFT | 100356398 | General Visual Inspection of Cargo Door Nets. |  | 0.035417 | ACS |  | ×, × | aft cargo door net
91 | 50-22-01-001-FWD | 100356402 | General Visual Inspection of Cargo Door Nets. |  | 0.033333 | ACS |  | ×, × | FWD cargo door net
92 | 50-32-00-001-AFT | 100356406 | Inspect (General Visual) FWD and AFT Cargo Compartments Partitions. |  | 0 | ACS |  | ×, × | aft cargo door net
93 | 50-32-00-001-FWD | 100186241 | Inspect (General Visual) FWD and AFT Cargo Compartments Partitions. |  | 0.020139 | ACS |  | ×, × | FWD cargo door net
94 | 52-30-005-0001-U | 100356504 | General Visual Inspection of Fwd Cargo Door C-Latch (Door) and Latch Fittings and Pins (Fuselage Cutout Area) - External Side of Door and at Fuselage Cutout Area. |  | 0.022917 | STR |  | ×, × | ×
95 | 52-30-005-0003-U | 100356508 | General Visual Inspection of Fwd Cargo Door Outer Skin Under Latch With Door Lining Removed - Internal Side of Door. |  | 0.024306 | STR |  | STR, × | ×
96 | 52-30-005-0005-AFTRH | 100356512 | General Visual Inspection of Aft Cargo Door C-Latch (Door) and Latch Fittings and Pins (Fuselage Cutout Area) - External Side of Door and at Fuselage Cutout Area. |  | 0.027083 | STR |  | ×, × | ×
97 | 52-30-005-0007-AFTRH | 100356516 | General Visual Inspection of Aft Cargo Door Outer Skin Under Latch With Door Lining Removed - Internal Side of Door. |  | 0.033333 | STR |  | STR, × | ×
98 | 52-30-005-0052-FWDRH | 100757852 | Detailed Inspection of Fwd Cargo Door Latch Shafts (at Door), Latch Pins and Fittings (at Fuselage) - External Side of Door and at Fuselage Cutout Area. |  | 0.025694 | STR |  | STR, × | ×
99 | 52-30-005-0062-U | 100356520 | Detailed Inspection of Aft Cargo Door Latch Shafts (at Door), Latch Pins and Fittings (at Fuselage) - External Side of Door and at Fuselage Cutout Area. |  | 0.028472 | STR |  | STR, × | ×
100 | 52-51-02-001-U | 100186267 | Operational Check of Reinforced Cockpit Door Control Panels and Electro-Mechanical Latch. |  | 0.10556 | ACS |  | ×, × | ×
101 | 54-50-003-0296-U | 100623690 | Detailed Inspection of Pylon Upper and Aft Links, Rods, Pins, Lugs and Fittings located at Wing and at Pylon, LH/RH - Internal Side of Pylon Fairings. |  | 0.041667 | STR |  | ACS/STR, × | ×
102 | 57-10-004-0850-U | 100648001 | Detailed Inspection of Aft Face of Wing Spar 2, from Rib 1 to Rib 4A, LH/RH - External Side at MLG compartment. |  | 0.041667 | STR |  | ×, I | ×
103 | 57-10-006-0730-U | 100647978 | Detailed Inspection of Wing Spar 2 to Wing Stub Attachments and Bolts, LH/RH - External Side at MLG Compartment. |  | 0.041667 | STR |  | ×, I | ×
104 | 57-40-005-0292-U | 100692866 | Detailed Inspection of all Slat Tracks Roller Paths Areas, LH/RH - External Side. |  | 0.041667 | STR | NOTE: Slats have to be fully extended. | ×, × | ×
105 | 57-40-08-001-LH | 100356883 | General Visual Inspection of Slat Aerodynamic and Weather Seals. |  | 0.055556 | ACS | Note: Inspect the aerodynamic and weather seals as visible with slats retracted. | ×, × | ×
106 | 57-40-08-001-RH | 100356778 | General Visual Inspection of Slat Aerodynamic and Weather Seals. |  | 0.0375 | ACS | Note: Inspect the aerodynamic and weather seals as visible with slats retracted. | ×, × | ×
107 | 57-50-031-0002-LH | 100721713 | Detailed Inspection of Main Carriage to Main Panel Attachments, including Panel Fittings, Main Carriage Fittings, Pins and Links, LH/RH - External area. |  | 0.061111 | STR | NOTE: Flaps have to be fully extended. | STR, × | ×
108 | 57-50-031-0002-RH | 100721702 | Detailed Inspection of Main Carriage to Main Panel Attachments, including Panel Fittings, Main Carriage Fittings, Pins and Links, LH/RH - External area. |  | 0.041667 | STR | NOTE: Flaps have to be fully extended. | STR, × | ×
109 | 73-11-09-001-RH | 100711457 | Remove and discard fuel filter element. |  | 0.1125 | ACS |  | ACS, × | ×
110 | JAIR-E00-00-001 | 100823485 | GVI - TO PREVENT PDA DUE TO HUMAN ERROR (FUSELAGE) |  | 0.083333 | GEN
111 | JAIR-E00-00-002 | 100823484 | GVI - TO PREVENT PDA DUE TO HUMAN ERROR (WING) |  | 0.083333 | GEN
112 | JAIR-E00-00-003 | 100823483 | GVI - TO PREVENT PDA DUE TO HUMAN ERROR (TAIL) |  | 0.041667 | GEN
113 | JAIR-E05-98-001 | 100823482 | GVI - PDA RELATED AREA (FUSELAGE) |  | 0.41667 | GEN
114 | JAIR-E05-98-002 | 100823487 | GVI - PDA RELATED AREA (WING) |  | 0.25 | GEN
115 | JAIR-E05-98-003 | 100823486 | GVI - PDA RELATED AREA (TAIL) |  | 0.16667 | GEN
116 | JAIR-E12-13-001 | 100721696 | Check - Engine Oil Level (LH Engine) |  | 0.041667 | ACS | 最終日実施 | ×, ×
117 | JAIR-E12-13-002 | 100721697 | Check - Engine Oil Level (RH Engine) |  | 0.041667 | ACS | 最終日実施 | ×, ×
118 | JAIR-E12-22-102 | 100358146 | 1/2 C C'K Cleaning |  | 0.31528 | CBN |  | ×, ×
119 | JAIR-E23-98-003 | 100707345 | INSPECTION - GGV COMPONENTS FOR PROPER MOUNTING |  | 0.25 | REI |  | ×, ×
120 | JAIR-E25-00-101 | 100721701 | Check - Loading of Loose and Emergency Equipment |  | 0.14583 | CBN |  | ×, ×
121 | JAIR-E25-62-001 | 100814917 | 60 DAYS CHECK |  | 0.041667 | CBN |  | ×, ×
122 | JAIR-E25-62-005 | 100723264 | Replace - First Aid Kit |  | 0.083333 | CBN |  | ×, ×
123 | JAIR-E29-11-002 | 100724805 | DET - ACMP UNION LOOSENESS |  | 0.125 | ACS | A-CHECK ITEM | ×, ×
124 | JAIR-E32-49-001 | 100721885 | SVC - NOSE LANDING GEAR (NLG) WHEEL TIRE |  | 0.027083 | ACS | 最終日実施 | ×, ×
125 | JAIR-E32-49-002 | 100721886 | SVC - MAIN LANDING GEAR (MLG) WHEEL TIRE |  | 0.029167 | ACS | 最終日実施 | ×, ×
126 | JAIR-E34-26-001 | 100794185 | Operation Check - Micro-IRU Switch on the pilot and co-pilot Reversionary Panel |  | 0.031944 | REI | NHF TASK | ×, ×
127 | JAIR-E36-10-001 | 100548567 | Replace - Cross Bleed Valve Supply Filter |  | 0.041667 | ACS | REPLACE P/N:1001248-2, S/N:2015080020
128 | JAIR-E36-11-009 | 100813903 | Inspection - Gasket between Precooler and Outlet Duct (LH) |  | 0.16667 | ACS
129 | JAIR-E36-11-010 | 100813944 | Inspection - Gasket between Precooler and Outlet Duct (RH) |  | 0.16667 | ACS
130 | JAIR-E72-00-004 | 100669432 | Water Wash - LH ENG |  | 0.24375 | ACS |  | ACS, ×
131 | JAIR-E72-00-006 | 100783195 | Lubrication - FAN Blade Pins of LH ENG |  | 0.16667 | ACS |  | ×, ×
132 | REQUEST JOB CARD | 100856135 | PERFORM - DOCK IN SAFETY |  | 0.5 | GEN
133 | REQUEST JOB CARD | 100856136 | PERFORM - ENGINEERING SUPPORT |  | 0.25 | GEN
134 | REQUEST JOB CARD | 100856137 | PERFORM - FLOOR INSPECTION (INSPECTOR) |  | 0.25 | INSP
135 | REQUEST JOB CARD | 100856138 | PERFORM - CPT INVENTORY CK |  | 0.16667 | GEN
136 | REQUEST JOB CARD | 100856139 | PERFORM - SQ SCREEN (GEN) |  | 0.5 | GEN
137 | REQUEST JOB CARD | 100856140 | PERFORM - SQ SCREEN (STR) |  | 0.5 | STR
138 | REQUEST JOB CARD | 100856141 | COND CK - REMOVED PARTS (GEN) |  | 1900-01-01 | GEN
139 | REQUEST JOB CARD | 100856142 | COND CK - REMOVED PARTS (STR) |  | 0.66667 | STR
140 | REQUEST JOB CARD | 100856143 | PERFORM - SELF FINAL CK |  | 1899-12-31 08:00 | GEN
141 | REQUEST JOB CARD | 100856144 | DEACTIVE/ACTIVE - ALL PAX & SVC DOOR PNEU ASSY |  | 0.083333 | GEN
142 | REQUEST JOB CARD | 100856145 | COND CK - BOTH ENG PNEU T-DUCT (E170) |  | 0.083333 | GEN
143 | REQUEST JOB CARD | 100856146 | PERFORM - APU PRESERVATION |  | 0.33333 | GEN
144 | REQUEST JOB CARD | 100856147 | CONFIRM - GREEN MARK DATA BASE |  | 0.33333 | STR
145 | REQUEST JOB CARD | 100856148 | COND CK - EXTERIOR POLYURETHANE FILMS (PPT) |  | 0.083333 | GEN
146 | REQUEST JOB CARD | 100856149 | PLZ CLEAN UP - CBN RMVED PARTS |  | 1899-12-31 08:00 | GEN
147 | REQUEST JOB CARD | 100856150 | PLZ RMV/INST - COCKPIT MISCELLAEOUS PARTS |  | 0.33333 | GEN
148 | REQUEST JOB CARD | 100856151 | PLZ RMV/INST - CBN MISCELLAEOUS PARTS |  | 1900-01-02 08:00 | GEN
149 | REQUEST JOB CARD | 100856152 | PLZ RMV/INST - FWD CGO MISCELLAEOUS PARTS |  | 0.66667 | GEN
150 | REQUEST JOB CARD | 100856153 | PLZ RMV/INST - AFT CGO MISCELLAEOUS PARTS |  | 0.33333 | GEN
151 | REQUEST JOB CARD | 100856154 | PLZ RMV/INST - FUSELAGE MISCELLAEOUS PARTS |  | 0.66667 | GEN
152 | REQUEST JOB CARD | 100856155 | PLZ RMV/INST - LH WING MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
153 | REQUEST JOB CARD | 100856156 | PLZ RMV/INST - RH WING MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
154 | REQUEST JOB CARD | 100856157 | PLZ RMV/INST - TAIL MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
155 | REQUEST JOB CARD | 100856158 | PLZ RMV/INST - LH ENG/PYL MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
156 | REQUEST JOB CARD | 100856159 | PLZ RMV/INST - RH ENG/PYL MISCELLAEOUS PARTS |  | 1899-12-31 08:00 | GEN
157 | REQUEST JOB CARD | 100856160 | PERFORM - CBN PRESS CK |  | 0.16667 | GEN
158 | REQUEST JOB CARD | 100856161 | PLZ RMV/INST - CBN WINDSCREEN FOR MAKE ACCESS |  | 0.5 | GEN
159 | REQUEST JOB CARD | 100856162 | PLZ RMV/INST - PAX SEAT FOR MAKE ACCESS |  | 1900-01-02 08:00 | GEN
160 | REQUEST JOB CARD | 100856163 | PLZ RMV/INST - CBN FLOOR CARPET FOR MAKE ACCESS |  | 1899-12-31 08:00 | GEN

## AP
JA227J _08S_AP List
No | Order | Event Description | Plan | Remarks
1 | 100855430 | OPEN THE PANEL(AFT CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.070833
2 | 100855431 | CLOSE THE PANEL(AFT CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.10833
3 | 100855432 | OPEN THE PANEL(AFT CARGO COMPARTMENT SIDEWALL - ACCESS DOORS AND PANELS) | 0.025
4 | 100855433 | CLOSE THE PANEL(AFT CARGO COMPARTMENT SIDEWALL - ACCESS DOORS AND PANELS) | 0.083333
5 | 100855434 | OPEN THE PANEL(AFT CARGO DOOR - ACCESS DOORS AND PANELS) | 0.016667
6 | 100855435 | CLOSE THE PANEL(AFT CARGO DOOR - ACCESS DOORS AND PANELS) | 0.025
7 | 100855436 | OPEN THE PANEL(AFT PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.033333
8 | 100855437 | CLOSE THE PANEL(AFT PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.075
9 | 100855438 | OPEN THE PANEL(AFT SERVICE DOOR - ACC DOORS AND PANELS) | 0.029167
10 | 100855439 | CLOSE THE PANEL(AFT SERVICE DOOR - ACC DOORS AND PANELS) | 0.054167
11 | 100855440 | OPEN THE PANEL(CENTER FUSELAGE I (FWD CARGO COMPT) - ACCESS DOORS AND PANEL) | 0.041667
12 | 100855441 | CLOSE THE PANEL(CENTER FUSELAGE I (FWD CARGO COMPT) - ACCESS DOORS AND PANEL) | 0.083333
13 | 100855442 | OPEN THE PANEL(CENTER FUSELAGE I CEILING - ACCESS DOORS AND PANELS) | 0.016667
14 | 100855443 | CLOSE THE PANEL(CENTER FUSELAGE I CEILING - ACCESS DOORS AND PANELS) | 0.041667
15 | 100855444 | OPEN THE PANEL(CENTER FUSELAGE I LH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.0041667
16 | 100855445 | CLOSE THE PANEL(CENTER FUSELAGE I LH LATERAL LINING - ACCESS DOORS AND PAN... | 0.0083333
17 | 100855446 | OPEN THE PANEL(CENTER FUSELAGE II (PASSENGER CABIN) - ACCESS DOORS AND PANELS) | 0.041667
18 | 100855447 | CLOSE THE PANEL(CENTER FUSELAGE II (PASSENGER CABIN) - ACCESS DOORS AND PA... | 0.058333
19 | 100855448 | OPEN THE PANEL(CENTER FUSELAGE II - ACCESS DOORS AND PANELS) | 0.0041667
20 | 100855449 | CLOSE THE PANEL(CENTER FUSELAGE II - ACCESS DOORS AND PANELS) | 0.0041667
21 | 100855450 | OPEN THE PANEL(CENTER FUSELAGE II CEILING - ACCESS DOORS AND PANELS) | 0.033333
22 | 100855451 | CLOSE THE PANEL(CENTER FUSELAGE II CEILING - ACCESS DOORS AND PANELS) | 0.083333
23 | 100855452 | OPEN THE PANEL(CENTER FUSELAGE II LH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.025
24 | 100855453 | CLOSE THE PANEL(CENTER FUSELAGE II LH LATERAL LINING - ACCESS DOORS AND PA... | 0.05
25 | 100855454 | OPEN THE PANEL(CENTER FUSELAGE II RH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.0083333
26 | 100855455 | CLOSE THE PANEL(CENTER FUSELAGE II RH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.016667
27 | 100855456 | OPEN THE PANEL(CENTER FUSELAGE III (PASSENGER CABIN) - ACCESS DOORS AND PANELS) | 0.029167
28 | 100855457 | CLOSE THE PANEL(CENTER FUSELAGE III (PASSENGER CABIN) - ACCESS DOORS AND PANELS) | 0.041667
29 | 100855458 | OPEN THE PANEL(CENTER FUSELAGE III CEILING - ACCESS DOORS AND PANELS) | 0.16667
30 | 100855459 | CLOSE THE PANEL(CENTER FUSELAGE III CEILING - ACCESS DOORS AND PANELS) | 0.41667
31 | 100855460 | OPEN THE PANEL(CENTER FUSELAGE III LH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.058333
32 | 100855461 | CLOSE THE PANEL(CENTER FUSELAGE III LH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.11667
33 | 100855462 | OPEN THE PANEL(CENTER FUSELAGE III RH LATERAL LINING - ACCESS DOORS AND PANELS) | 0.0625
34 | 100855463 | CLOSE THE PANEL(CENTER FUSELAGE III RH LATERAL LINING - ACCESS DOORS AND PANELS( | 0.091667
35 | 100855464 | OPEN THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - LH WING - ACCESS DOORS AND PANELS) | 0.0125
36 | 100855465 | CLOSE THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - LH WING - ACCESS DOORS AND PANELS) | 0.020833
37 | 100855466 | OPEN THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - RH WING - ACCESS DOORS AND PANELS) | 0.0125
38 | 100855467 | CLOSE THE PANEL(FLAP TRACKS AND ROOT FAIRINGS - RH WING - ACCESS DOORS AND PANELS) | 0.020833
39 | 100855468 | OPEN THE PANEL(FORWARD CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.016667
40 | 100855469 | CLOSE THE PANEL(FORWARD CARGO COMPARTMENT INTERNAL - ACCESS DOORS AND PANELS) | 0.041667
41 | 100855470 | OPEN THE PANEL(FORWARD CARGO DOOR - ACCESS DOORS AND PANELS) | 0.016667
42 | 100855471 | CLOSE THE PANEL(FORWARD CARGO DOOR - ACCESS DOORS AND PANELS) | 0.025
43 | 100855472 | OPEN THE PANEL(FORWARD FUSELAGE - ACCESS DOORS AND PANELS) | 0.0083333
44 | 100855473 | CLOSE THE PANEL(FORWARD FUSELAGE - ACCESS DOORS AND PANELS) | 0.0083333
45 | 100855474 | OPEN THE PANEL(FORWARD PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.033333
46 | 100855475 | CLOSE THE PANEL(FORWARD PASSENGER DOOR - ACCESS DOORS AND PANELS) | 0.058333
47 | 100855476 | OPEN THE PANEL(FORWARD SERVICE DOOR - ACCESS DOORS AND PANELS) | 0.029167
48 | 100855477 | CLOSE THE PANEL(FORWARD SERVICE DOOR - ACCESS DOORS AND PANELS) | 0.054167
49 | 100855478 | OPEN THE PANEL(FWD FUSELAGE LH LATERAL LINING(PAX CABIN) - ACCESS DOORS & PANELS) | 0.020833
50 | 100855479 | CLOSE THE PANEL(FWD FUSELAGE LH LATERAL LINING(PAX CABIN) - ACCESS DOORS & PANELS) | 0.025
51 | 100855480 | OPEN THE PANEL(LEADING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.175
52 | 100855481 | CLOSE THE PANEL(LEADING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.35
53 | 100855482 | OPEN THE PANEL(LEADING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.175
54 | 100855483 | CLOSE THE PANEL(LEADING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.35
55 | 100855484 | OPEN THE PANEL(LH PYLON - ACCESS DOORS AND PANELS) | 0.19167
56 | 100855485 | CLOSE THE PANEL(LH PYLON - ACCESS DOORS AND PANELS) | 0.37917
57 | 100855486 | OPEN THE PANEL(MAJOR SUB-ZONE 820 - DOORS - RH FUSELAGE SIDE) | 0.0013889
58 | 100855487 | CLOSE THE PANEL(MAJOR SUB-ZONE 820 - DOORS - RH FUSELAGE SIDE) | 0.0013889
59 | 100855488 | OPEN THE PANEL(PASSENGER CABIN INTERNAL - ACCESS DOORS AND PANELS) | 0.0083333
60 | 100855489 | CLOSE THE PANEL(PASSENGER CABIN INTERNAL - ACCESS DOORS AND PANELS) | 0.0125
61 | 100855490 | OPEN THE PANEL(REAR FUSELAGE - ACCESS DOORS AND PANELS) | 0.0083333
62 | 100855491 | CLOSE THE PANEL(REAR FUSELAGE - ACCESS DOORS AND PANELS) | 0.0083333
63 | 100855492 | OPEN THE PANEL(RH POWERPLANT - ACCESS DOORS AND PANELS) | 0.0125
64 | 100855493 | CLOSE THE PANEL(RH POWERPLANT - ACCESS DOORS AND PANELS) | 0.0125
65 | 100855494 | OPEN THE PANEL(RH PYLON - ACCESS DOORS AND PANELS) | 0.18333
66 | 100855495 | CLOSE THE PANEL(RH PYLON - ACCESS DOORS AND PANELS) | 0.29583
67 | 100855496 | OPEN THE PANEL(TRAILING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.016667
68 | 100855497 | CLOSE THE PANEL(TRAILING EDGE - LH WING - ACCESS DOORS AND PANELS) | 0.029167
69 | 100855498 | OPEN THE PANEL(TRAILING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.016667
70 | 100855499 | CLOSE THE PANEL(TRAILING EDGE - RH WING - ACCESS DOORS AND PANELS) | 0.029167
71 | 100855500 | OPEN THE PANEL(VERTICAL TAIL - ACCESS DOORS AND PANELS) | 0.05
72 | 100855501 | CLOSE THE PANEL(VERTICAL TAIL - ACCESS DOORS AND PANELS) | 0.125
73 | 100855502 | OPEN THE PANEL(WING INBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.025
74 | 100855503 | CLOSE THE PANEL(WING INBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.0625
75 | 100855505 | OPEN THE PANEL(WING INBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.025
76 | 100855506 | CLOSE THE PANEL(WING INBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.0625
77 | 100855507 | OPEN THE PANEL(WING OUTBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.0125
78 | 100855508 | CLOSE THE PANEL(WING OUTBOARD AREA - LH WING - ACCESS DOORS AND PANELS) | 0.020833
79 | 100855509 | OPEN THE PANEL(WING OUTBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.0125
80 | 100855510 | CLOSE THE PANEL(WING OUTBOARD AREA - RH WING - ACCESS DOORS AND PANELS) | 0.020833
81 | 100855511 | OPEN THE PANEL(WING-TO-FUSELAGE FAIRING - ACCESS DOORS AND PANELS) | 0.27917
82 | 100855512 | CLOSE THE PANEL(WING-TO-FUSELAGE FAIRING - ACCESS DOORS AND PANELS) | 0.34167

## COA
JA227J _08S_COA List
No | COA/ER | Order | Event Description | AD TCD | Work CAT | COA Rev. | ER Rev. | Plan | Remarks
1 | COA23-00013-ER01 | 100827504 | Replace - VHF-2 Antenna (E170) |  | MI | 0 | 0 | 0.16667
2 | COA23-00013-ER02 | 100827522 | Replace - VHF-3 Antenna (E170) |  | MI | 0 | 0 | 0.16667
3 | COA25-00040-ER01 | 100816558 | RPLC - Spacer of Toilet Shroud at FWD LAV (E170) |  | MI | 0 | A | 0.083333
4 | COA25-00040-ER03 | 100816617 | RPLC - Spacer of Toilet Shroud at AFT LAV (E170) |  | MI | 0 | A | 0.083333
5 | COA25-00043-ER01 | 100831347 | INSP - FWD LH Lavatory Mirror (E170) |  | MI | 0 | 0 | 0.041667
6 | COA27-00011-ER01 | 100819532 | INSP - Control Yoke Harness (ERJ170) |  | MI | 0 | A | 0.33333
7 | COA27-00013-ER01 | 100848133 | Modification - Control Column Wires (E170) |  | MI | 0 | 0 | 0.20833
8 | COA32-00024-ER01 | 100855063 | CK-EMER/PARK BRK PRESS SW |  | MI | 0 | 0 | 0.16667
9 | COA36-00011-ER01 | 100759516 | Install - Resistor to ODS (E170) |  | MI | 0 | A | 1899-12-31 12:00
10 | COA36-00012-ER01 | 100822781 | MOD - BLD SYS Reverse Flow Protection |  | MI | A | D | 1899-12-31 21:00
11 | COA36-00015-ER01 | 100828504 | INSP/RPLC - Sensing Elements (Part I) |  | MI | A | A | 1900-01-02 04:00
12 | COA36-00015-ER02 | 100828549 | INSP/RPLC - Sensing Elements (Part II) |  | MI | A | A | 1899-12-31 14:00
13 | COA36-00015-ER03 | 100818996 | INSP/RPLC - Sensing Elements (Part III) |  | MI | A | A | 1900-01-02
14 | COA36-00015-ER04 | 100837366 | INSP/RPLC - Sensing Elements (Part IV) |  | MI | A | B | 1899-12-31 02:00
15 | COA38-00004-ER01 | 100722511 | INSP - WTR Tank HTR Blanket Insulation |  | MI | 0 | 0 | 0.29167 | 実施前にPARTS確認をお願いいたします。
16 | COA38-00005-ER01 | 100791195 | MOD - WWSC Electrical Harness (E170) |  | MI | 0 | A | 0.5
17 | COA52-00011-ER01 | 100770380 | Re-TQ - PAX and SVC Door Hinge Arm Chain |  | MK | 0 | 0 | 0.41667
18 | COA52-00013-ER01 | 100748447 | CK/LUB-FWD PAX Door Handle and Ramp |  | MI | 0 | 0 | 0.16667
19 | COA53-00031-ER01 | 100733565 | Install - Nose Radome Bonding Bracket |  | MI | 0 | A | 0.20833
0:00
[10 empty] | 249J/H-18-2 | 0:00

## EV
JA227J _08S_EV List
No | EV | Order | Event Description | AD TCD | Work CAT | EV Rev. | Plan | Remarks
0:00
[9 empty] | 249J/H-18-2 | 0:00

## 経観CO
JA227J _08S_C/O SQ & Monitoring Inspection
Monitoring Inspection |  | C/O SQ |  | C'K
INSP Date | CLOSE Date | C/O Date | CLOSE Date | JALEC | No |  | Order | Extern.ID | Task Description | M/H | Remarks
[5 empty] | 1 | MI | EWS7259 | EWS7259-MI | ECI - SKIN AREA UNDER THE REPAIR DOUBLER ON RH FWD FUSE |  | NOT PLANNED | 40000FCごと 残34264
[5 empty] | 2 | MI | EWS7260 | EWS7260-MI | DETAIL INSP - RH FWD FUSE REPAIR DOUBLER INSTALLATION AREA |  | NOT PLANNED | 20000FCごと 残14264
[5 empty] | 3 | MI | EWS7356 | EWS7356-MI | EXTERNAL DET - APU FIRE WALL 351BZ UPPER AREA |  | NOT PLANNED | 10000FCごと 残7447
[5 empty] | 4 | MI | EWS7357 | EWS7357-MI | EXTERNAL DET - APU FIRE WALL 351BZ LOWER AREA |  | NOT PLANNED | 10000FCごと 残7447
0:00
0:00

## IO
JA226J _08S_Inspection Order
No | Date | Order | Event Description | Receipt | Completion
/
/
/
/
/
/
/
| / | [5 empty] | 0:00
/
| / |  |  |  |  | 249J/H-18-2 | 0:00
/
/
/
/
/
/
/