## RN
JA243J_2C_Revision Notice List 01
No | Date | ADD XLD | Task | Order | Task Description | Plan | Trade | Remarks | Receipt | STATUS
2 |  | ADD | COA21-00013-ER02 | 100845411 | Inst - AMS BL 16.0 (E190) | 0.083333 |  | WorkCategory:MI COA:Rev.0 ER:Rev.0
3 |  | ADD | COA50-00001-ER02 | 100845576 | INSP & REWORK - Blowout PNL in CGO COMPT | 0.3125 |  | WorkCategory:MI COA:Rev.0 ER:Rev.0
22 |  | ADD | 25-45-01-001-U | 100639174 | Detailed Inspection of the Lavatory Waste flap Door and Waste compartment Door. | 0.024306 | CBN | TCD/AD
23 |  | ADD | JAIR-E25-21-503 | 100712583 | Inspection – Leg of Class-J Double Seat | 0.041667 | CBN
24 |  | ADD | JAIR-E22-11-502 | 100829812 | Ground Check - CAT III of All Weather Operation | 0.125 | REI
25 |  | ADD | JAIR-E22-11-501 | 100829811 | Ground Check - CAT II of All Weather Operation | 0.125 | REI
26 |  | ADD | JAIR-E12-13-503 JAIR-E49-00-502 | 100827024 | Check - APU Oil Level Readout - APU Hour/Cycle | 0.039583 | ACS
27 |  | ADD | 21-27-03-001C-U | 100788170 | Operational Check of Fwd Cargo Compartment Check Valve. | 0.025694 | CBN
28 |  | ADD | 24-21-00-001-LH | 100788168 | Servicing of IDG as required. | 0.010417 | ACS
29 |  | ADD | 24-21-00-001-RH | 100788169 | Servicing of IDG as required. | 0.010417 | ACS
30 |  | ADD | JAIR-E23-98-501 | 100822701 | Wi-Fi Video Contents Update for Gogo Wi-Fi System | 0.020833 | REI
31 |  | ADD | 27-03-05-002-U | 100803291 | Functional Check of FBW Back-up Battery Charge. | 0.03125 | REI
32 |  | ADD | 27-32-01-001-LH | 100581633 | Lubrication of Elevator PCUs Toggle Links. | 0.097222 | ACS | A-CHECK ITEM
33 |  | ADD | 27-32-01-001-RH | 100581632 | Lubrication of Elevator PCUs Toggle Links. | 0.097222 | ACS | A-CHECK ITEM
34 |  | ADD | 27-36-01-001-U | 100696426 | Operational Check of Stick Shaker Motors. | 0.022917 | REI | NHF TASK A-CHECK ITEM
35 |  | ADD | 53-00-001-0001-LH | 100696428 | External General Visual Inspection of the Fuselage Polyurethane Films for Integrity. | 0.083333 | STR | A-CHECK ITEM
36 |  | ADD | 53-00-001-0001-RH | 100696427 | External General Visual Inspection of the Fuselage Polyurethane Films for Integrity. | 0.083333 | STR | A-CHECK ITEM
37 |  | ADD | 55-00-001-0001-LH | 100696425 | External General Visual Inspection of the Stabilizers Polyurethane Films for Integrity. | 0.054861 | STR | A-CHECK ITEM
38 |  | ADD | 55-00-001-0001-RH | 100696424 | External General Visual Inspection of the Stabilizers Polyurethane Films for Integrity. | 0.054861 | STR | A-CHECK ITEM
39 |  | ADD | 57-00-001-0001-LH | 100696422 | External General Visual Inspection of the Wing Polyurethane Films for Integrity. | 0.052083 | STR | A-CHECK ITEM
40 |  | ADD | 57-00-001-0001-RH | 100696423 | External General Visual Inspection of the Wing Polyurethane Films for Integrity. | 0.052083 | STR | A-CHECK ITEM
41 |  | ADD | JAIR-E32-53-501 | 100758213 | CK - Ramp Panel Steering Disarming Switch | 0.125 | ACS | A-CHECK ITEM
42 |  | ADD | 38-11-02-001-AFT | 100712448 | Discard of Water Filter. | 0.029167 | CBN | 6MO Package ITEM
43 |  | ADD | 38-11-02-001-FWD | 100712449 | Discard of Water Filter. | 0.029167 | CBN | 6MO Package ITEM
44 |  | ADD | 38-31-00-001-AFT | 100712447 | Flush of Gray Water Lines. | 0.041667 | CBN | 6MO Package ITEM
45 |  | ADD | 38-31-00-001-FWD | 100712450 | Flush of Gray Water Lines. | 0.041667 | CBN | 6MO Package ITEM
46 |  | ADD | COA32-00026-ER02 | 100844540 | INSP-NLG Wheel Bearings(E190) | 0.20833 |  | WorkCategory:MI COA:Rev.0, ER:Rev.0 |  | 緩急度11/30 11月中に完了処理必要
47 |  | ADD | EV-OSASE-01442 | 100847709 | Condition Check - Internal Springs of Overhead Bin Latches (JA243J) | 0.5 |  | EV Rev.0
48 |  | ADD | JAIR-E34-61-501 | 100846007 | Loading - Navigation Database | 0.030556 | REI | 11/25以降に実施
49 |  | ADD | COA46-00002-ER02 | 100846728 | LOAD - DATA TO PBS600 (E190) | 0.020833 |  | WorkCategory:MK COA:Rev.0 ER:Rev.0
50 |  | ADD | JAIR-E28-11-501 | 100841513 | SVC - FUEL TANK WATER DRAINAGE | 0.044444 | ACS | ROUTINE CHECK
51 |  | ADD | JAIR-E32-11-501 | 100841523 | GVI - MAIN LANDING GEAR (MLG) SHIMMY DAMPERS | 0.010417 | ACS | ROUTINE CHECK
52 |  | ADD | JAIR-E32-49-503 | 100841521 | GVI - NOSE LANDING GEAR (NLG) WHEEL ASSEMBLY | 0.013194 | ACS | ROUTINE CHECK
53 |  | ADD | JAIR-E32-49-504 | 100841522 | GVI - NOSE LANDING GEAR (NLG) WHEEL TIRE | 0.011806 | ACS | ROUTINE CHECK
54 |  | ADD | JAIR-E32-49-505 | 100841524 | GVI - MAIN LANDING GEAR (MLG) WHEEL ASSEMBLY | 0.022222 | ACS | ROUTINE CHECK
55 |  | ADD | JAIR-E32-49-506 | 100841518 | GVI - MAIN LANDING GEAR (MLG) WHEEL TIRE | 0.015278 | ACS | ROUTINE CHECK
56 |  | ADD | JAIR-E32-49-507 | 100841514 | GVI - BRAKE WEAR INDICATOR / BRAKE ASSEMBLY | 0.010417 | ACS | ROUTINE CHECK
57 |  | ADD | JAIR-E49-00-502 | 100841512 | Readout - APU Hour/Cycle | 0.11458 | ACS | ROUTINE CHECK (最終日実施)
58 |  | ADD | JAIR-E52-00-501 | 100841525 | Condition Check-Passenger and Service Door Elastic Pin | 0.03125 | CBN | ROUTINE CHECK
59 |  | ADD | JAIR-E52-11-501 | 100841515 | VCK - FWD PAX DOOR EMERG OPENING PNEUMATIC ASSY | 0.016667 | CBN | ROUTINE CHECK
60 |  | ADD | JAIR-E52-12-501 | 100841516 | VCK - AFT PAX DOOR EMERG OPENING PNEUMATIC ASSY | 0.019444 | CBN | ROUTINE CHECK
61 |  | ADD | JAIR-E52-41-501 | 100841517 | VCK - FWD SVC DOOR EMERG OPENING PNEUMATIC ASSY | 0.019444 | CBN | ROUTINE CHECK
62 |  | ADD | JAIR-E52-42-501 | 100841519 | VCK - AFT SVC DOOR PNEUMATIC ASSEMBLY GAUGE | 0.019444 | CBN | ROUTINE CHECK
63 |  | ADD | JAIR-E72-00-506 | 100841520 | VCK - MULTI FUNC DISPLAY (MFD) CHIP DETECTOR IND | 0.010417 | ACS | ROUTINE CHECK
64 |  | ADD | COA27-00013-ER02 | 100848137 | Modification - Control Column Wires (E190) | 0.20833 |  | WorkCategory:MI COA:Rev.0, ER:Rev.0